## 00_Summary
Custom RAG POC — Summary (read this sheet + 00_Visual_Flow)
One page for the whole analysis. Every row points to the detail sheet. All recommendations are PRELIMINARY until the POC records measured evidence.
1. What and why
Objective | Determine, with measured evidence, whether replacing some or all of the managed Vertex AI Search / Gemini Enterprise RAG (Discovery Engine) behind the Eva Knowledge Engine is justified, which architecture fits, and how to prove it in a structured GCP POC.
Status | PRELIMINARY. No architecture is selected. All recommendations below are expert hypotheses to be confirmed or rejected by the POC.
Hard rule | Source ACLs (SharePoint, ServiceNow) must be enforced BEFORE any content reaches the LLM, rerankers, caches, logs or A2A agents. Options that cannot meet this are UNSUITABLE.
Today | ADK 2.0.3 agents communicating via A2A call Discovery Engine (Vertex AI Search / Gemini Enterprise) for retrieval and answers. Content from SharePoint Online and ServiceNow via managed connectors; document ACLs enforced by the managed service with Entra ID identities via Workforce Identity Federation (exact configuration To Confirm - AQ-08).
2. How to read the IDs every sheet uses the same prefixes
Prefix | Meaning | Where | Sheet
AP | Architecture pattern (layer 00 — the first decision) | Who builds RAG: Google (managed) or us (custom) | 03a_Arch_Patterns
SP / SN / ID | SharePoint / ServiceNow / Identity (Entra ID) | Source extraction and ACL rules | 05a_Source_Connectors
ING | Ingestion | Pull, parse, OCR, clean, sync | 05_Ingestion
CHK | Chunking | How docs are cut into pieces | 06_Chunking
EMB | Embedding model | Turns text into vectors | 04_Embeddings
VDB | Vector database / store | Where vectors + keywords live | 07_Vector_Stores
ANN | Approximate nearest neighbour index | Fast vector search | 08_ANN_Algorithms
RET | Retrieval strategy | How candidate chunks are found | 09_Retrieval
RRK | Rerank / fusion | Re-order and merge hits | 10_Reranking
ADV | Advanced RAG technique | Only for a measured gap | 11_Advanced_RAG
ENF | ACL enforcement option | Where permissions are checked | 21b_ACL_Enforcement
EXP / M | Experiment / metric | What we run and how we score it | 14_Experiments
R / AQ | Risk / assumption or open question | What can go wrong / what we must confirm | 16_Risks
PH / G0-G4 | Roadmap phase / decision gate | Order of work and stop points | 18_Roadmap
3. Architecture choice (layer 00) the first decision — everything else follows
What it decides | Who runs retrieval: Google's managed Vertex AI Search (AP-A) or our own GCP-native pipeline (AP-B), or a mix.
Options | AP-A managed (baseline), AP-A2 managed retrieval + custom generation/rerank, AP-B GCP-native custom (AlloyDB or Vector Search), AP-C open-source on GCP, AP-D hybrid, AP-E fully custom, AP-F federated/delegated, AP-G Vertex AI RAG Engine (sheet 03a).
POC compares | AP-A (managed baseline) against AP-B (custom on AlloyDB). AP-A2 / AP-D are the hybrid middle paths.
Shortlist | A-01 (baseline), A-03 (managed retrieval + Ranking API + custom generation), B-01 (AlloyDB hybrid + ENF-04), B-05 (Vector Search + restricts + AlloyDB policy store), C-02 (Elasticsearch hybrid + DLS) as OSS/keyword-strong alternative, D-01 (managed SharePoint + custom ServiceNow), D-03 (federated delegated search as security reference / validation path).
Unsuitable | A-05, C-06, D-04, E-02 (fail mandatory ACL requirement); B-10 RAG Engine for ACL'd content unless per-user ACL is verified.
Managed (AP-A/A2) | + lowest effort, connector + ACL sync maintained by Google, Gemini Enterprise integration. - limited control of chunking/embedding/ANN, opaque relevance changes, per-query cost model, ACL fidelity only as good as connectors (must still be tested: EXP-ACL-19).
Hybrid (AP-D) | + targeted control where gaps are measured; keeps managed ACLs where proven. - two systems to operate and evaluate; cross-system fusion; dual ACL models.
Fully custom (AP-B/C/E) | + full control of every retrieval variable, per-app tuning, portability, cost transparency. - we own connectors, ACL extraction/normalisation/sync/revocation, on-call, upgrades; parity with managed connectors is a major project; security guarantees must be re-proven.
4. The ACL slice step 9 — first thin custom build, must pass gate G2
ACL | Access control list: who may see which document.
Slice | One thin path built end to end with simple defaults, no tuning: extract docs + permissions → normalise ACL → chunk → embed → AlloyDB vector + keyword index → search filtered to the user's groups → re-check final docs at source → Gemini answer with citations → exposed as an ADK tool.
Why first | Proves custom RAG never shows a user a document they cannot open in the source. If gate G2 fails, stop and fix ACLs before any quality tuning.
Options used | From step 9: ANN-10, AP-B, ING-26, ING-28, RET-04, RET-06, RET-16, VDB-05. Suggested defaults (swap freely): CHK-06, EMB-01, RRK-01.
Enforcement | Synchronised ACL-aware index (fast, scalable, but a parallel authorisation model) vs trusted policy service (central, auditable) vs delegating to source (truthful, slow, throttled) vs hybrid (index pre-filter + authoritative validation of final candidates before the LLM). Preliminary: hybrid ENF-04, confirm with EXP-ACL-12 and AQ-15.
Fail closed | Every stage drops content it cannot authorise: no ACL = not indexed; no filter = query refused; unverified doc = not sent to LLM; cache keys include the user's principal set. Detail: 21a_ACL_Pipeline.
5. Layers and how each is chosen pick one option per layer per experiment
Layer | What it decides | Slice start → how it is chosen | Detail sheet
00 Architecture pattern (8) | Managed vs custom vs hybrid | AP-B vs baseline AP-A → decision matrix at G4 | 03a_Arch_Patterns
01 Sources & identity (4) | Which content, which users | Fixed by scope (steps 1-6) → access checklist | 05a_Source_Connectors
02 Ingestion & preparation (28) | Parse, clean, sync, carry ACLs | ING-26, ING-28 (ACL propagation) → throughput + freshness tests | 05_Ingestion
03 Chunking (17) | Size and boundaries of pieces | CHK-06 heading-aware → chunk-size matrix on golden set (step 11) | 06_Chunking
04 Embedding model (20) | Text → vector model and dims | EMB-01 → compare models + dims on our corpus (step 11) | 04_Embeddings
05 Vector store (17) | Where the index lives | VDB-05 AlloyDB (PostgreSQL + pgvector + ScaNN) → compare with Vector Search / Elastic | 07_Vector_Stores
06 ANN index (10) | Speed vs recall of vector search | ANN-10 filtered ANN → recall vs exact under ACL filters (step 12) | 08_ANN_Algorithms
07 Retrieval (17) | How candidates are found | RET-04 hybrid + RET-06 ACL filter + RET-16 ADK → hybrid & glossary tests (step 13) | 09_Retrieval
08 Rerank & fusion (12) | Final order of candidates | RRK-01 Ranking API → rerank tests, also on managed A-03 (step 13) | 10_Reranking
09 Advanced RAG (31) | Extra fixes for hard queries | Only MUST items (ADV-19/27/28/30) → others only for a measured gap (step 14) | 11_Advanced_RAG
10 Generation & answer (4) | Answer, citations, integration | Gemini + citations + ADK tool → grounding and citation metrics | 02_Existing_vs_Target
11 Evaluate & decide (4) | Proof and final choice | Golden set + metrics → decision matrix + ADR (steps 16-17) | 15_Metrics
6. Delivery plan 17 steps in order — gate steps must pass before continuing
Step · phase | What to do | Done when | Owner
1 · 1. Discovery | Confirm scope: SharePoint sites/libraries and ServiceNow knowledge bases for the POC | In-scope source list signed off | Product owner
2 · 1. Discovery | Agree targets: latency, query volume, quality margin over baseline, revocation delay (SLA) | Targets recorded | Product owner + Security
3 · 1. Discovery | Document the current Vertex AI Search / Gemini Enterprise setup and how user identity flows (Entra ID, ADK 2.0.3, A2A) | Config export + identity flow diagram | App team + Identity
4 · 2. Access | Create POC project, budget alerts, enable APIs, service accounts with least-privilege roles | GCP checklist items GCP-01..27 closed | Cloud platform
5 · 2. Access | Get SharePoint/Entra app access (Sites.Selected, group read, OBO) and ServiceNow OAuth integration user | SRC-01..12 closed | M365 + ServiceNow teams
6 · 2. Access | Create test site, test KB and 10-20 test users with a known permission matrix | ACL truth table ready (DS-03) | M365 + ServiceNow admins
7 · 3. Data | Build POC corpus snapshot and golden query set (300-500 labelled queries) | Golden set v1 frozen; dev/held-out split | Evaluation lead + SMEs
8 · 4. Baseline | Measure current managed RAG: quality, latency, cost, and ACL behaviour | Baseline report (EXP-00, EXP-ACL-19) | RAG engineer
9 · 5. ACL foundation | Build thin custom slice: extract -> ACL model -> chunk -> embed -> AlloyDB hybrid -> Gemini, exposed as ADK tool | Working slice (B-01) | RAG + data engineers
10 · 5. ACL foundation | GATE G2: run ACL negative tests (unauthorised access, revocation, deletion, cache, A2A, spoofing) | Zero unauthorised exposure | Security + RAG team
11 · 6. Tuning | Compare embedding models, dimensions and chunking on our corpus | Chosen model + chunking (EXP-01..10) | RAG engineer
12 · 6. Tuning | Tune ANN index under permission filters | ANN config meeting recall + latency (EXP-11, 12, 39) | RAG engineer
13 · 6. Tuning | Test hybrid search, glossary expansion, reranking, context size, grounding (also on managed setup) | Best pipeline frozen (GATE G3) | RAG engineer
14 · 7. Advanced | Try advanced techniques only where a measured gap exists | Gain proven or technique rejected | RAG engineer
15 · 8. Validation | Load, ingestion throughput, freshness, prompt-injection and cost tests | NFR evidence pack | SRE + Security
16 · 9. Decision | Final blind comparison: best custom vs managed on held-out queries | EXP-35 results | Evaluation lead
17 · 9. Decision | GATE G4: score options in decision matrix (mandatory gates first), write ADR | Architecture decision recorded | Principal architect + sponsors
Gates | G0 scope agreed; G1 environment ready; G2 ACL gate (zero unauthorised exposure on DS-03); G3 configuration frozen for comparison; G4 architecture decision (measured improvement >= agreed margin AQ-26, all mandatory gates passed, ownership assigned).
7. How results are measured targets are hypotheses to agree, except ACL = zero tolerance
Area | Metric | Target / rule | Sheet
Security | Unauthorised exposures on ACL negative suite | 0 — hard gate (G2, G4) | 15_Metrics
Retrieval | NDCG@K (primary), Recall@K, Hit Rate | ≥ baseline + agreed margin (AQ-26) | 15_Metrics
Retrieval | ANN recall vs exact search | ≥ 0.95 at chosen settings (hypothesis) | 15_Metrics
Answer | Faithfulness, citation correctness / coverage | ≥ baseline; citations ≥ 95% / 90% (hypothesis) | 15_Metrics
Answer | Correct abstention on unanswerable | ≥ baseline | 15_Metrics
Performance | P50 / P95 latency per stage | Per AQ-07 targets | 15_Metrics
Cost | Run-rate cost per successful answer | From 17_Cost_Capacity with official prices | 15_Metrics
8. Decision rule 19_Decision_Matrix
Mandatory first | Zero unauthorised exposure · data residency · works with ADK 2.0.3 / A2A using end-user identity · named operational owner. Any fail = option EXCLUDED.
Then weighted | Retrieval quality 12 · Answer quality 12 · Latency 8 · Scalability 6 · Cost 8 · Operational complexity 8 · Security (ACL fidelity) 14 · Data governance 6 · Customisation flexibility 5 · Integration with ADK and A2A 4 · Migration effort 5 · Maintainability 5 · Vendor lock-in 3 · Reliability 4
Outcome | Stay managed / Hybrid / Custom — written up as an ADR with migration plan. | 19_Decision_Matrix
9. Top risks 16_Risks
Risk | Description | Mitigation | Sheet
R-01 | Stale permissions: ACL changes not synced before user queries | ACL-only sync; TTL caches; authoritative top-N validation; fail closed on stale acl_updated_at | 16_Risks
R-08 | ServiceNow scripted user criteria cannot be replicated statically | Index criteria IDs; evaluate matches per user in ServiceNow; requires_source_check flag | 16_Risks
R-03 | Incomplete inheritance handling (folder/site permission changes, broken inheritance) | Scope-based ACL references with fan-out; nightly reconciliation | 16_Risks
R-06 | A2A data leakage: agents forward restricted content to other users' sessions or agents | Identity-bound tool results; no shared state across users; A2A auth; output filtering | 16_Risks
R-36 | Custom build cannot reach parity with managed connectors/ACLs in time | Hybrid options (AP-A2, AP-D); decision gates | 16_Risks
R-24 | Golden set unrepresentative -> wrong decision | Stratified sampling; pooled labels; held-out split | 16_Risks
R-35 | ADK 2.0.3 incompatibilities (A2A auth headers, part conversion fixed in later 2.x) | Verify against 2.0.3; plan upgrade to latest 2.x if needed | 16_Risks
10. Run first, unknowns, outputs
Top 10 experiments | 1 EXP-00 baseline; 2 EXP-ACL-19 managed ACL fidelity; 3 EXP-ACL-01 ACL extraction correctness; 4 EXP-ACL-04 filtered retrieval negative suite; 5 EXP-ACL-05/06 revocation; 6 EXP-07 chunking; 7 EXP-01 embedding models; 8 EXP-13 dense vs hybrid; 9 EXP-19 reranking (also on managed A-03); 10 EXP-39 ACL filter selectivity vs ANN recall.
Critical unknowns | AQ-01/02 scope; AQ-03 ServiceNow ACL semantics; AQ-04 volume; AQ-07 load/latency targets; AQ-08 baseline config; AQ-12 sensitivity; AQ-13 residency; AQ-15 revocation SLA; AQ-17/18 identity propagation & mapping; AQ-19 sharing links; AQ-21 API access approval; AQ-24 ownership; AQ-26 quality bar.
Dependencies | Graph Sites.Selected + SharePoint REST access (SRC-01/02); ServiceNow OAuth integration user + per-user criteria evaluation (SRC-08/09); revocation SLA (AQ-15); baseline config export (AQ-08); test users/fixtures (SRC-07/11); quotas (GCP-12).
Deliverables | Baseline report; golden datasets v1; ACL negative-test suite; experiment results (sheet 14); NFR & cost evidence; decision matrix with measured scores; ADR and migration plan.
Key decisions | (1) Keep managed retrieval vs build; (2) ACL enforcement model (ENF-04 hybrid preliminary); (3) vector/keyword store; (4) embedding model + dims; (5) chunking per doc type; (6) reranker; (7) ADK/A2A integration contract and identity propagation; (8) operational ownership.
Verification | Volatile facts (ADK 2.0 release, gemini-embedding-001 limits, gemini-embedding-2-preview, Vector Search 2.0, Ranking API model names, Vertex AI Search ACL + WIF) were web-checked on 2026-10-26. Everything else is labelled 'Documented - re-verify', 'OSS/Third-party', 'Proposed pattern' or 'To Verify'. No prices, quotas or benchmark results are asserted.

## 00_Visual_Flow
Open a layer's detail sheet
00 Architecture pattern | 03a_Arch_Patterns ↗
01 Sources & identity | 05a_Source_Connectors ↗
02 Ingestion & preparation | 05_Ingestion ↗
03 Chunking | 06_Chunking ↗
04 Embedding model | 04_Embeddings ↗
05 Vector store | 07_Vector_Stores ↗
06 ANN index | 08_ANN_Algorithms ↗
07 Retrieval | 09_Retrieval ↗
08 Rerank & fusion | 10_Reranking ↗
09 Advanced RAG | 11_Advanced_RAG ↗
10 Generation & answer | 02_Existing_vs_Target ↗
11 Evaluate & decide | 15_Metrics ↗

## Summary_Steps
Custom RAG POC - summarised steps (details in Custom_RAG_Architecture_POC_Plan.xlsx)
Do the steps in order; GATE steps must pass before continuing.
Step | Phase | What to do | Why | Owner | Output / done when | Details in main workbook | Status | Notes
1 | 1. Discovery | Confirm scope: SharePoint sites/libraries and ServiceNow knowledge bases for the POC | Results are only valid on a representative corpus | Product owner | In-scope source list signed off | 20_Assumptions_Log (AQ-01, AQ-02) | Not started | -
2 | 1. Discovery | Agree targets: latency, query volume, quality margin over baseline, revocation delay (SLA) | Without targets no decision can be made | Product owner + Security | Targets recorded | AQ-07, AQ-15, AQ-26 | Not started | Revocation SLA is mandatory
3 | 1. Discovery | Document the current Vertex AI Search / Gemini Enterprise setup and how user identity flows (Entra ID, ADK 2.0.3, A2A) | Baseline and integration design depend on it | App team + Identity | Config export + identity flow diagram | AQ-08, AQ-17, AQ-20 | Not started | -
4 | 2. Access | Create POC project, budget alerts, enable APIs, service accounts with least-privilege roles | Engineering cannot start without it | Cloud platform | GCP checklist items GCP-01..27 closed | 12_GCP_Access_Checklist | Not started | Start early - approvals take weeks
5 | 2. Access | Get SharePoint/Entra app access (Sites.Selected, group read, OBO) and ServiceNow OAuth integration user | Needed to extract content and permissions | M365 + ServiceNow teams | SRC-01..12 closed | 12_GCP_Access_Checklist (SRC-*) | Not started | -
6 | 2. Access | Create test site, test KB and 10-20 test users with a known permission matrix | Needed for negative security tests | M365 + ServiceNow admins | ACL truth table ready (DS-03) | 15a_Datasets | Not started | Never use real users
7 | 3. Data | Build POC corpus snapshot and golden query set (300-500 labelled queries) | Every experiment is scored against it | Evaluation lead + SMEs | Golden set v1 frozen; dev/held-out split | 15a_Datasets, 15b_Golden_Set_Method | Not started | -
8 | 4. Baseline | Measure current managed RAG: quality, latency, cost, and ACL behaviour | Reference point for every comparison | RAG engineer | Baseline report (EXP-00, EXP-ACL-19) | 14_Experiments | Not started | -
9 | 5. ACL foundation | Build thin custom slice: extract -> ACL model -> chunk -> embed -> AlloyDB hybrid -> Gemini, exposed as ADK tool | Proves custom RAG can enforce permissions | RAG + data engineers | Working slice (B-01) | 03_Combination_Matrix, 21_ACL_Data_Model | Not started | -
10 | 5. ACL foundation | GATE G2: run ACL negative tests (unauthorised access, revocation, deletion, cache, A2A, spoofing) | Security is a hard gate | Security + RAG team | Zero unauthorised exposure | 14_Experiments (EXP-ACL-*) | Not started | Any failure stops further work
11 | 6. Tuning | Compare embedding models, dimensions and chunking on our corpus | Biggest drivers of retrieval quality | RAG engineer | Chosen model + chunking (EXP-01..10) | 04_Embeddings, 06_Chunking | Not started | Change one variable at a time
12 | 6. Tuning | Tune ANN index under permission filters | Filters can silently lower recall | RAG engineer | ANN config meeting recall + latency (EXP-11, 12, 39) | 08_ANN_Algorithms, 08a_ANN_Experiments | Not started | -
13 | 6. Tuning | Test hybrid search, glossary expansion, reranking, context size, grounding (also on managed setup) | Common quality gains | RAG engineer | Best pipeline frozen (GATE G3) | 09_Retrieval, 10_Reranking | Not started | -
14 | 7. Advanced | Try advanced techniques only where a measured gap exists | Avoid needless complexity | RAG engineer | Gain proven or technique rejected | 11_Advanced_RAG | Not started | -
15 | 8. Validation | Load, ingestion throughput, freshness, prompt-injection and cost tests | Production readiness | SRE + Security | NFR evidence pack | 14_Experiments, 17_Cost_Capacity | Not started | Fill unit prices from official pages
16 | 9. Decision | Final blind comparison: best custom vs managed on held-out queries | Evidence for decision | Evaluation lead | EXP-35 results | 14_Experiments | Not started | -
17 | 9. Decision | GATE G4: score options in decision matrix (mandatory gates first), write ADR | Choose managed / hybrid / custom | Principal architect + sponsors | Architecture decision recorded | 19_Decision_Matrix, 20_Assumptions_Log | Not started | Only measured scores count

## 00_Guide
Custom RAG Architecture - POC Plan (Eva Knowledge Engine)
Generated 2026-10-26. All recommendations are PRELIMINARY until POC evidence is recorded.
Purpose: options catalogue, experimentation matrix, GCP/SharePoint/ServiceNow access checklist and POC plan for evaluating custom vs managed RAG.
Mandatory constraint: source document ACLs (SharePoint, ServiceNow) must be enforced before any content reaches the LLM, rerankers, caches, logs or A2A agents. Options that cannot meet it are marked UNSUITABLE.
Stable IDs link sheets: EMB-, VDB-, ANN-, CHK-, RET-, RRK-, ADV-, AP-, ENF-, ING-, SP-/SN-/ID-, EXP-, AX-, CPX-, M-, GCP-/SRC-, API-, R-, PH-, AQ-, DS-, FR-, S-.
Nothing here is a price quotation or benchmark result. Unit prices in 17_Cost_Capacity are blank inputs to be filled from the linked official pricing pages.
Sheet | Purpose | Key IDs / notes
01_Summary | Summary (preliminary)
02_Existing_vs_Target | Existing vs target architecture, by component
03_Combination_Matrix | Architecture combination catalogue incl. ACL dimensions
03a_Arch_Patterns | Architecture patterns: component diagrams, data flow, failure modes
04_Embeddings | Embedding model catalogue
05_Ingestion | Large-scale ingestion & preprocessing techniques
05a_Source_Connectors | SharePoint / ServiceNow / Entra extraction & ACL workflows
06_Chunking | Chunking strategy catalogue
06a_Chunk_Param_Matrix | Chunk size / overlap / strategy test matrix
07_Vector_Stores | Vector database & search engine selection
08_ANN_Algorithms | ANN algorithms & index optimisation
08a_ANN_Experiments | ANN experiment matrix
08b_Clustering_vs_Index | Clustering vs indexing vs retrieval vs reranking
09_Retrieval | Retrieval strategy catalogue
10_Reranking | Reranking & relevance optimisation
11_Advanced_RAG | Advanced RAG techniques (tiered)
12_GCP_Access_Checklist | GCP, SharePoint/Entra and ServiceNow access checklist
13_API_SDK_Inventory | API, SDK & integration inventory
14_Experiments | POC experiment matrix & test plan
15_Metrics | Evaluation metrics & benchmarking
15a_Datasets | Test datasets
15b_Golden_Set_Method | How to build the golden dataset
16_Risks | Security, governance & operational risks
17_Cost_Capacity | Configurable cost & capacity model
18_Roadmap | POC implementation roadmap
19_Decision_Matrix | Architecture decision matrix
20_Assumptions_Log | Assumptions, open questions & decision log
21_ACL_Data_Model | ACL-aware document / chunk / principal schema
21a_ACL_Pipeline | ACL propagation through every pipeline stage
21b_ACL_Enforcement | ACL enforcement options (decision principle)
22_Layer_Analysis | Per-layer technical analysis
23_FR_Traceability | Eva FR requirement traceability
24_Source_Register | Source register
Legend
Editable input cell
Calculated / formula cell
Expert estimate or hypothesis (not measured)
Verification status contains 'Verified'
Verification status contains 'Documented'
Verification status contains 'Preview'
Verification status contains 'OSS'
Verification status contains 'Proposed'
Verification status contains 'Assumption'
Verification status contains 'To Verify'
UNSUITABLE - fails mandatory ACL requirement

## 01_Summary
Executive summary - PRELIMINARY (no final architecture selected)
Read with 19_Decision_Matrix and 20_Assumptions_Log.
Section | Item | Content
Objective | Project objective | Determine, with measured evidence, whether replacing some or all of the managed Vertex AI Search / Gemini Enterprise RAG (Discovery Engine) behind the Eva Knowledge Engine is justified, which architecture fits, and how to prove it in a structured GCP POC.
Objective | Status of recommendations | PRELIMINARY. No architecture is selected. All recommendations below are expert hypotheses to be confirmed or rejected by the POC.
Existing | Existing architecture summary | ADK 2.0.3 agents communicating via A2A call Discovery Engine (Vertex AI Search / Gemini Enterprise) for retrieval and answers. Content from SharePoint Online and ServiceNow via managed connectors; document ACLs enforced by the managed service with Entra ID identities via Workforce Identity Federation (exact configuration To Confirm - AQ-08).
Targets | Target alternatives | AP-A managed (baseline), AP-A2 managed retrieval + custom generation/rerank, AP-B GCP-native custom (AlloyDB or Vector Search), AP-C open-source on GCP, AP-D hybrid, AP-E fully custom, AP-F federated/delegated, AP-G Vertex AI RAG Engine (sheet 03a).
Decisions | Key decisions required | (1) Keep managed retrieval vs build; (2) ACL enforcement model (ENF-04 hybrid preliminary); (3) vector/keyword store; (4) embedding model + dims; (5) chunking per doc type; (6) reranker; (7) ADK/A2A integration contract and identity propagation; (8) operational ownership.
Risks | Highest-priority technical risks | R-01 stale permissions; R-08 ServiceNow scripted user criteria; R-03 SharePoint inheritance; R-06 A2A leakage; R-36 custom parity with managed connectors/ACLs; R-24 unrepresentative golden set; R-35 ADK 2.0.3 A2A gaps.
Scope | Recommended POC scope | Phase-gated (sheet 18): baseline (EXP-00) -> ACL foundation + thin custom slice B-01 (gate G2: zero ACL failures) -> embedding/chunking -> ANN under ACL filters -> hybrid + rerank (and the same levers on managed retrieval A-02/A-03) -> problem-triggered advanced techniques -> NFR/security/cost validation -> decision (EXP-35, gate G4).
Shortlist | Preliminary shortlist | A-01 (baseline), A-03 (managed retrieval + Ranking API + custom generation), B-01 (AlloyDB hybrid + ENF-04), B-05 (Vector Search + restricts + AlloyDB policy store), C-02 (Elasticsearch hybrid + DLS) as OSS/keyword-strong alternative, D-01 (managed SharePoint + custom ServiceNow), D-03 (federated delegated search as security reference / validation path).
Shortlist | Explicitly unsuitable | A-05, C-06, D-04, E-02 (fail mandatory ACL requirement); B-10 RAG Engine for ACL'd content unless per-user ACL is verified.
Criteria | Decision criteria | Mandatory gates first: ACL zero-tolerance metrics = 0, residency, ADK/A2A integrability, operational ownership. Then weighted: retrieval quality, answer quality, latency, scalability, cost, operational complexity, security, governance, flexibility, ADK/A2A integration, migration effort, maintainability, lock-in, reliability (sheet 19).
Dependencies | Dependencies & blockers | Graph Sites.Selected + SharePoint REST access (SRC-01/02); ServiceNow OAuth integration user + per-user criteria evaluation (SRC-08/09); revocation SLA (AQ-15); baseline config export (AQ-08); test users/fixtures (SRC-07/11); quotas (GCP-12).
Deliverables | Expected deliverables | Baseline report; golden datasets v1; ACL negative-test suite; experiment results (sheet 14); NFR & cost evidence; decision matrix with measured scores; ADR and migration plan.
Gates | Architecture decision gates | G0 scope agreed; G1 environment ready; G2 ACL gate (zero unauthorised exposure on DS-03); G3 configuration frozen for comparison; G4 architecture decision (measured improvement >= agreed margin AQ-26, all mandatory gates passed, ownership assigned).
Trade-offs | Managed (AP-A/A2) | + lowest effort, connector + ACL sync maintained by Google, Gemini Enterprise integration. - limited control of chunking/embedding/ANN, opaque relevance changes, per-query cost model, ACL fidelity only as good as connectors (must still be tested: EXP-ACL-19).
Trade-offs | Hybrid (AP-D) | + targeted control where gaps are measured; keeps managed ACLs where proven. - two systems to operate and evaluate; cross-system fusion; dual ACL models.
Trade-offs | Fully custom (AP-B/C/E) | + full control of every retrieval variable, per-app tuning, portability, cost transparency. - we own connectors, ACL extraction/normalisation/sync/revocation, on-call, upgrades; parity with managed connectors is a major project; security guarantees must be re-proven.
Trade-offs | ACL enforcement | Synchronised ACL-aware index (fast, scalable, but a parallel authorisation model) vs trusted policy service (central, auditable) vs delegating to source (truthful, slow, throttled) vs hybrid (index pre-filter + authoritative validation of final candidates before the LLM). Preliminary: hybrid ENF-04, confirm with EXP-ACL-12 and AQ-15.
Top10 | Top 10 experiments to run first | 1 EXP-00 baseline; 2 EXP-ACL-19 managed ACL fidelity; 3 EXP-ACL-01 ACL extraction correctness; 4 EXP-ACL-04 filtered retrieval negative suite; 5 EXP-ACL-05/06 revocation; 6 EXP-07 chunking; 7 EXP-01 embedding models; 8 EXP-13 dense vs hybrid; 9 EXP-19 reranking (also on managed A-03); 10 EXP-39 ACL filter selectivity vs ANN recall.
Unknowns | Critical unknowns | AQ-01/02 scope; AQ-03 ServiceNow ACL semantics; AQ-04 volume; AQ-07 load/latency targets; AQ-08 baseline config; AQ-12 sensitivity; AQ-13 residency; AQ-15 revocation SLA; AQ-17/18 identity propagation & mapping; AQ-19 sharing links; AQ-21 API access approval; AQ-24 ownership; AQ-26 quality bar.
Method | Verification approach | Volatile facts (ADK 2.0 release, gemini-embedding-001 limits, gemini-embedding-2-preview, Vector Search 2.0, Ranking API model names, Vertex AI Search ACL + WIF) were web-checked on 2026-10-26. Everything else is labelled 'Documented - re-verify', 'OSS/Third-party', 'Proposed pattern' or 'To Verify'. No prices, quotas or benchmark results are asserted.

## 02_Existing_vs_Target
Existing vs target architecture - component responsibilities
Component / concern | Current managed (Vertex AI Search / Gemini Enterprise) | GCP-native custom (AP-B) | Hybrid (AP-D) | Open-source on GCP (AP-C) | Fully custom (AP-E) | Migration / integration notes
Source connectors (SharePoint, ServiceNow) | Managed connectors; Google maintains API changes | We build Graph + ServiceNow extractors | Keep managed for one or both sources | We build | We build | Connector parity is the largest hidden cost; start by measuring baseline connector ACL fidelity
Parsing & OCR | Managed (digital / OCR / layout parser options) | Document AI Layout Parser / OCR | Either | Unstructured / Docling / Tika on GKE | Own | Parsing quality drives everything downstream; measure on our file mix
Chunking | Managed options (layout-based chunking config) | Fully configurable | Configurable on custom side | Configurable | Configurable | Gain: per-app/per-doc-type chunking
Embedding | Managed, not selectable in all modes - To Verify | Vertex embeddings (choice of model & dims) | Either | Self-hosted OSS | Any | Re-embedding cost on every model change
Vector + keyword indexing | Managed blended retrieval | AlloyDB / Vector Search + FTS | Mixed | Qdrant / Elastic / OpenSearch | Own | Gain: ANN/hybrid tuning; Lose: managed relevance work
Document ACL sync | Managed via connectors (acl_info) | We build ACL extraction, normalisation, sync, reconciliation | Managed side keeps it; custom side builds it | We build | We build | MANDATORY gate: ACL fidelity tests before any quality comparison
Identity | Workforce Identity Federation with Entra ID | Entra token validation + Graph group expansion | Both | Same as custom | Same | Identity propagation through ADK/A2A needed in all options
Query-time security trimming | Managed inside search | Pre-filter in DB + validation | Per system | DB / DLS | Own | Lose managed guarantee - must re-prove with negative tests
Metadata filters (FR-FLT) | Filter expressions on indexed fields | SQL / engine filters | Mixed syntax -> need a common filter DSL | Engine filters | Own DSL | Gain: one filter DSL across both APIs (FR-FLT-02)
Glossary / acronyms (FR-GLO) | Limited (synonym/serving controls - To Verify) | Custom query expansion service | Custom layer in front of both | Same | Same | Glossary layer is reusable across all options - build once
Reranking | Managed in pipeline | Ranking API or OSS | Either | OSS | OSS | -
Generation & prompts (FR-CFG-03) | Answer API with prompt preamble options | Gemini via own prompt registry (versioned) | Custom | Gemini | Gemini | Gain: prompt versioning per app_id
Citations / deep links | Managed | Own mapping chunk->source_url | Mixed | Own | Own | Must re-check ACL of every cited document
Evaluation & feedback | Our responsibility today | Our responsibility | Same | Same | Same | Build once; used to compare all options (FR-RET-05/06)
Monitoring / SLOs | Service metrics + our app metrics | All ours (Cloud Monitoring, Trace) | Mixed | All ours | All ours | -
Operational ownership | Google runs retrieval; we run app | We run retrieval + ingestion + ACL sync | Split | We run everything incl. clusters | Everything | On-call and runbooks are a hard prerequisite for production
Functionality lost if replaced | - | Managed connectors, managed ACL sync, managed relevance updates, Gemini Enterprise UI integration | Partial | Same + managed models | All managed capabilities | List explicitly in decision log before decision gate G4
Functionality gained | - | Model/chunk/ANN/hybrid control; per-app tuning; cost transparency; portability | Targeted control | Portability; no per-call fees | Total control | Only count gains measured in the POC

## 03_Combination_Matrix
Architecture combination matrix (rows marked UNSUITABLE fail the mandatory ACL requirement)
Component refs point to catalogue sheets (EMB-/VDB-/ANN-/CHK-/RRK-/ENF-). Defaults per category, overridden where the combination differs.
Architecture ID | Architecture category | Pattern ref | Name / summary | Why technically meaningful / how it differs | Ingestion approach | SharePoint integration method | ServiceNow integration method | Document extraction | Preprocessing | Chunking strategy (ref) | Embedding provider | Embedding model (ref) | Embedding dimensions | Vector DB / index (ref) | ANN algorithm / index type (ref) | Keyword search engine | Hybrid search approach | Metadata filtering strategy | Reranking approach (ref) | Context assembly | Generation model | Orchestration framework | Deployment model | ACL extraction approach | ACL normalisation model | Identity resolution approach | Authorisation policy store | Authorisation enforcement point | ACL-aware vector filtering | Keyword-search authorisation | Reranker authorisation boundary | ACL synchronisation strategy | Revocation strategy | Source authorisation fallback | Meets mandatory ACL requirement? | Expected advantages | Known limitations | Implementation complexity | Relative cost | Latency considerations | Security considerations | Scalability considerations | Required GCP services | POC priority | Prerequisites | Validation method | Evidence source | Verification status
A-01 | A. GCP-native managed | AP-A | Current baseline as-is: Vertex AI Search + connectors + Answer API | Reference point for every comparison | Vertex AI Search connectors (managed sync) | Vertex AI Search SharePoint Online connector | Vertex AI Search ServiceNow connector | Managed parser (digital/OCR/layout - per data store config) | Managed | Managed (layout-based chunking if configured) | Google (managed) | Managed (not selectable - To Verify) | Managed | VDB-01 | Managed (not exposed) | Managed | Managed blended retrieval | Filter expressions on indexed metadata | Managed (built-in ranking) | Managed (Answer API) | Answer API managed Gemini model | ADK 2.0.3 agent tool (VertexAiSearchTool / custom FunctionTool) + A2A | Managed service + existing app | Connector-managed ACL sync | acl_info readers (users/groups) per document | Workforce Identity Federation (Entra ID); end-user identity in search request | Managed (inside data store) | Inside Vertex AI Search (pre-results) | Managed | Managed | n/a (managed) | Connector schedule (managed) | Connector ACL refresh cadence - To Verify | To Verify: ServiceNow scripted user criteria + SharePoint sharing-link fidelity | Candidate - validate fidelity (EXP-ACL-01) | No build; managed ACLs | Limited tuning | Low | Medium | Managed; measure P95 | Relies on connector ACL fidelity + WIF mapping | Managed quotas | Discovery Engine, IAM/WIF, Vertex AI | P0 | Access to current app/data store config | Baseline metrics + ACL negative tests | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Verified (web check 2026-10-26)
A-02 | A. GCP-native managed | AP-A2 | Vertex AI Search Search API + custom Gemini generation with versioned prompts | Isolates generation/prompt control while retrieval + ACL stay managed | Vertex AI Search connectors (managed sync) | Vertex AI Search SharePoint Online connector | Vertex AI Search ServiceNow connector | Managed parser (digital/OCR/layout - per data store config) | Managed | Managed (layout-based chunking if configured) | Google (managed) | Managed (not selectable - To Verify) | Managed | VDB-01 | Managed (not exposed) | Managed | Managed blended retrieval | Filter expressions on indexed metadata | Managed (built-in ranking) | Custom context builder (citations, glossary) | Gemini via Vertex AI (prompt registry per app_id) | ADK 2.0.3 agent tool (VertexAiSearchTool / custom FunctionTool) + A2A | Managed service + existing app | Connector-managed ACL sync | acl_info readers (users/groups) per document | Workforce Identity Federation (Entra ID); end-user identity in search request | Managed (inside data store) | Inside Vertex AI Search (pre-results) | Managed | Managed | n/a (managed) | Connector schedule (managed) | Connector ACL refresh cadence - To Verify | To Verify: ServiceNow scripted user criteria + SharePoint sharing-link fidelity | Candidate - validate fidelity (EXP-ACL-01) | FR-CFG-03 prompt versioning; streaming control | Retrieval unchanged | Low-Medium | Medium | Managed; measure P95 | Relies on connector ACL fidelity + WIF mapping | Managed quotas | Discovery Engine, IAM/WIF, Vertex AI | P1 | Access to current app/data store config | Baseline metrics + ACL negative tests | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Verified (web check 2026-10-26)
A-03 | A. GCP-native managed | AP-A2 | Search API + Vertex Ranking API rerank + Gemini + Check Grounding | Tests whether a second-stage reranker and grounding check add measurable value on managed retrieval | Vertex AI Search connectors (managed sync) | Vertex AI Search SharePoint Online connector | Vertex AI Search ServiceNow connector | Managed parser (digital/OCR/layout - per data store config) | Managed | Managed (layout-based chunking if configured) | Google (managed) | Managed (not selectable - To Verify) | Managed | VDB-01 | Managed (not exposed) | Managed | Managed blended retrieval | Filter expressions on indexed metadata | RRK-01 on trimmed top-50 | Custom; grounding check (ADV-20) | Gemini via Vertex AI | ADK 2.0.3 agent tool (VertexAiSearchTool / custom FunctionTool) + A2A | Managed service + existing app | Connector-managed ACL sync | acl_info readers (users/groups) per document | Workforce Identity Federation (Entra ID); end-user identity in search request | Managed (inside data store) | Inside Vertex AI Search (pre-results) | Managed | Managed | Ranking API receives only trimmed results | Connector schedule (managed) | Connector ACL refresh cadence - To Verify | To Verify: ServiceNow scripted user criteria + SharePoint sharing-link fidelity | Candidate - validate fidelity (EXP-ACL-01) | Cheap uplift test | Extra latency per call | Low-Medium | Medium | Managed; measure P95 | Relies on connector ACL fidelity + WIF mapping | Managed quotas | Discovery Engine, IAM/WIF, Vertex AI | P1 | Access to current app/data store config | Baseline metrics + ACL negative tests | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Verified (web check 2026-10-26)
A-04 | A. GCP-native managed | AP-A2 | Managed retrieval + custom glossary query expansion (FR-GLO) | Tests if acronym/synonym gaps are fixable without replacing retrieval | Vertex AI Search connectors (managed sync) | Vertex AI Search SharePoint Online connector | Vertex AI Search ServiceNow connector | Managed parser (digital/OCR/layout - per data store config) | Managed | Managed (layout-based chunking if configured) | Google (managed) | Managed (not selectable - To Verify) | Managed | VDB-01 | Managed (not exposed) | Managed | Managed + expanded query terms | Filter expressions on indexed metadata | Managed (built-in ranking) | Custom; glossary definitions in prompt | Answer API managed Gemini model | ADK 2.0.3 agent tool (VertexAiSearchTool / custom FunctionTool) + A2A | Managed service + existing app | Connector-managed ACL sync | acl_info readers (users/groups) per document | Workforce Identity Federation (Entra ID); end-user identity in search request | Managed (inside data store) | Inside Vertex AI Search (pre-results) | Managed | Managed | n/a (managed) | Connector schedule (managed) | Connector ACL refresh cadence - To Verify | To Verify: ServiceNow scripted user criteria + SharePoint sharing-link fidelity | Candidate - validate fidelity (EXP-ACL-01) | Addresses FR-GLO-01..06 cheaply | Expansion quality depends on glossary curation | Low-Medium | Medium | Managed; measure P95 | Relies on connector ACL fidelity + WIF mapping | Managed quotas | Discovery Engine, IAM/WIF, Vertex AI | P1 | Access to current app/data store config | Baseline metrics + ACL negative tests | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Verified (web check 2026-10-26)
A-05 | A. GCP-native managed | AP-A | Vertex AI Search with ACL disabled + application-side filtering | Included only to document why it is rejected | Vertex AI Search connectors (managed sync) | Vertex AI Search SharePoint Online connector | Vertex AI Search ServiceNow connector | Managed parser (digital/OCR/layout - per data store config) | Managed | Managed (layout-based chunking if configured) | Google (managed) | Managed (not selectable - To Verify) | Managed | VDB-01 | Managed (not exposed) | Managed | Managed blended retrieval | Filter expressions on indexed metadata | Managed (built-in ranking) | Managed (Answer API) | Answer API managed Gemini model | ADK 2.0.3 agent tool (VertexAiSearchTool / custom FunctionTool) + A2A | Managed service + existing app | Connector-managed ACL sync | acl_info readers (users/groups) per document | Workforce Identity Federation (Entra ID); end-user identity in search request | Managed (inside data store) | Post-filter in application (ENF-05) | Managed | Managed | n/a (managed) | Connector schedule (managed) | Connector ACL refresh cadence - To Verify | To Verify: ServiceNow scripted user criteria + SharePoint sharing-link fidelity | UNSUITABLE - fails mandatory ACL requirement | None for security | Unauthorised content retrieved before filtering | Low | Medium | Managed; measure P95 | Leakage risk via counts, rerank, logs | Managed quotas | Discovery Engine, IAM/WIF, Vertex AI | Excluded | Access to current app/data store config | Baseline metrics + ACL negative tests | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Verified (web check 2026-10-26)
B-01 | B. GCP-native custom | AP-B | AlloyDB pgvector HNSW + FTS hybrid (RRF) + gemini-embedding-001@768 + Ranking API | Primary custom candidate: vectors, keyword and ACL in one transactional store | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Single store = consistent ACL across branches; SQL expressiveness | We own connectors + ACL fidelity | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P1 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
B-02 | B. GCP-native custom | AP-B | As B-01 with AlloyDB ScaNN index | Isolates ANN algorithm (ScaNN vs HNSW) on the same data | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-06 ScaNN (alloydb_scann) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Lower memory, faster builds at scale (to measure) | Filtered-ScaNN behaviour must be verified | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
B-03 | B. GCP-native custom | AP-B | As B-01 with 3072-dim embeddings (halfvec) | Isolates embedding dimensionality; pgvector HNSW on 'vector' type is limited to 2000 dims, so 3072 needs halfvec (verify version) | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 3072 stored as halfvec | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Tests whether full dims improve recall on our corpus | ~2x storage/memory vs 1536; index type constraints | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | To Verify
B-04 | B. GCP-native custom | AP-B | Cloud SQL for PostgreSQL + pgvector (smaller footprint) | Same model as B-01 on cheaper managed Postgres; validates scale ceiling | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-06 Cloud SQL | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Lower cost floor | Scale ceiling | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | Vertical only; check corpus size | Vertex AI, Cloud SQL, Cloud Run, GCS, Pub/Sub, Secret Manager | P3 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/sql/docs/postgres/work-with-vectors | Proposed pattern - validate in POC
B-05 | B. GCP-native custom | AP-B | Vertex AI Vector Search (Tree-AH) + restricts for ACL + AlloyDB policy/chunk store | Separates ANN serving from policy store; tests restricts as ACL filter at scale | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-02 Vector Search + VDB-05 (policy/chunks) | ANN-06 Tree-AH | Sparse BM25 vectors in Vector Search hybrid index | Vector Search native hybrid (dense+sparse) | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | AlloyDB tables; restricts derived from them | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Token restricts: allow namespace = principal tokens, deny namespace = denied tokens | Same restricts apply to hybrid query | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Very low latency at large scale | Restrict token limits per datapoint & per query - verify; streaming update lag; two stores to reconcile | High | Medium-High (always-on endpoint) | DB + rerank + Gemini; measure P95 | Restrict-token fidelity + consistency between Vector Search and policy store | Excellent | Vertex AI Vector Search, AlloyDB, Cloud Run, GCS, Pub/Sub | P1 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/vertex-ai/docs/vector-search/filtering | Documented - re-verify before use
B-06 | B. GCP-native custom | AP-B | Vector Search hybrid with bge-m3 dense+sparse | Tests learned sparse vs BM25 sparse in managed hybrid ANN | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Self-hosted (GKE/Cloud Run GPU) | EMB-07 bge-m3 | 1024 dense + sparse | VDB-02 | ANN-06 | bge-m3 sparse vectors | Vector Search hybrid (RRF/alpha) | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Token restricts | Same restricts | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | One model for dense+sparse; multilingual | GPU serving ops | High | Medium-High | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
B-07 | B. GCP-native custom | AP-B | Vertex AI Vector Search 2.0 collections with auto-embeddings | Lower-ops managed custom index if GA and filter semantics meet ACL needs | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-03 | Managed (ScaNN family) | To Verify | To Verify | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | To Verify | To Verify | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | To Verify - blocked until filter semantics documented | Less pipeline code | Preview features; unknown ACL filter capacity | Medium | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://docs.cloud.google.com/vertex-ai/docs/vector-search-2/embeddings/autogenerating-embeddings | Preview/Experimental - re-verify
B-08 | B. GCP-native custom | AP-B | BigQuery VECTOR_SEARCH (IVF/TreeAH) for offline evaluation & ground truth | Exact/ANN ground truth and large-scale offline experiments; also BigQuery-sourced content (FR-CON-04) | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-04 BigQuery | ANN-01 exact + ANN-03 IVF / ANN-06 TreeAH | BigQuery SEARCH() text index | SQL fusion | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | JOIN to ACL table / row-level security | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate for offline/eval only | Cheap exact ground truth; analytics | Seconds-class latency - not for interactive serving | High | Low-Medium (slots/bytes) | Seconds-class | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P1 (eval tooling) | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/bigquery/docs/vector-search-intro | Proposed pattern - validate in POC
B-09 | B. GCP-native custom | AP-B | Spanner vector + full-text search | Only meaningful if global distribution / very high write scale is required | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-07 Spanner | ANN-06 ScaNN-based ANN index | Spanner full-text search | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Horizontal scale, transactional ACLs | Cost floor; fewer RAG examples | High | High | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P4 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/spanner/docs/find-approximate-nearest-neighbors | Proposed pattern - validate in POC
B-10 | B. GCP-native custom | AP-G | Vertex AI RAG Engine (RagManagedDb) prototype | Fast way to test chunk/embedding choices with managed orchestration | RAG Engine import from GCS | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-10 RagManagedDb | Managed KNN/ANN | n/a | n/a | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | None | None documented | Not documented per-user | n/a | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | UNSUITABLE for ACL'd content unless per-user ACL verified | Low effort prototype | No document ACL model (verify) | Low | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 (non-sensitive prototype only) | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/vertex-ai/generative-ai/docs/rag-engine/rag-overview | Documented - re-verify before use
B-11 | B. GCP-native custom | AP-B | As B-01 with self-hosted EmbeddingGemma | Isolates managed vs self-hosted embedding cost/quality | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Self-hosted (Cloud Run GPU) | EMB-06 embeddinggemma-300m | 768 (MRL 256-768) | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | No per-token fees; in-VPC | Serving ops; quality to measure | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
C-01 | C. Open-source on GCP | AP-C | Qdrant on GKE + bge-m3 dense+sparse + bge-reranker-v2-m3 | Fully OSS hybrid stack with in-graph filtered HNSW | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Self-hosted | EMB-07 bge-m3 | 1024 + sparse | VDB-13 Qdrant | ANN-02 HNSW (filterable) + ANN-05 SQ8 | Qdrant sparse vectors | Qdrant Query API fusion (RRF) | Payload indexes | RRK-02 bge-reranker-v2-m3 | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | GKE (Autopilot/Standard) + GPU node pool | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | AlloyDB/Cloud SQL ACL tables (system of record) projected to payloads | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Payload filter: should match principal tokens; must_not denied tokens; status=ok | Same filter on sparse branch | Self-hosted reranker inside VPC | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Portable; no per-call model fees | Ops burden: upgrades, backups, GPU capacity | High | Medium (infra) / High (ops) | DB + rerank + Gemini; measure P95 | Payload ACL projection consistency | AlloyDB vertical + read pools | GKE, GCS, Artifact Registry, Cloud SQL/AlloyDB, Secret Manager | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://qdrant.tech/documentation/ | OSS/Third-party - verify licence & version
C-02 | C. Open-source on GCP | AP-C | Elasticsearch (Elastic Cloud on GCP) BM25 + kNN + RRF + DLS + Vertex embeddings | Keyword-first enterprise search with native document-level security | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-11 Elasticsearch | ANN-02 HNSW (Lucene) + int8 | Elasticsearch BM25 (language analyzers, synonyms) | Native RRF retriever | Query DSL filters | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Elastic Cloud (GCP region) via PSC | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | AlloyDB ACL tables projected to index fields | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | kNN filter clause with principal terms + DLS role query as backstop | Same filter + DLS | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Best-in-class keyword relevance + synonyms (FR-GLO) | Subscription tier for DLS; JVM ops | High | Medium-High | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://www.elastic.co/guide/en/elasticsearch/reference/current/document-level-security.html | OSS/Third-party - verify licence & version
C-03 | C. Open-source on GCP | AP-C | OpenSearch on GKE (k-NN Lucene engine) + Security plugin DLS | Apache-2.0 alternative to C-02 | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-12 OpenSearch | ANN-02 HNSW (Lucene engine efficient filtering) | OpenSearch BM25 | Hybrid query + normalisation processor | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | GKE | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Filtered k-NN + DLS | DLS | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | No licence cost | Highest self-ops | High | Medium (infra) / High (ops) | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://opensearch.org/docs/latest/search-plugins/knn/index/ | OSS/Third-party - verify licence & version
C-04 | C. Open-source on GCP | AP-C | Weaviate hybrid (BM25F + HNSW) with Vertex embeddings | Tests built-in hybrid with minimal tuning | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-14 Weaviate | ANN-02 HNSW | Weaviate BM25F | Native hybrid (alpha / fusion) | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | GKE or Weaviate Cloud | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Where filter on principal arrays | Same | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Easy hybrid | Large IN-list filter performance to measure | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://weaviate.io/developers/weaviate | OSS/Third-party - verify licence & version
C-05 | C. Open-source on GCP | AP-C | Milvus on GKE with DiskANN (very large corpora) | Only meaningful if vectors exceed RAM budget | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-15 Milvus | ANN-07 DiskANN | Milvus BM25 function / sparse | Milvus hybrid search | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | GKE + SSD | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Array/tag scalar filters | Same | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Billion-scale | Many components | High | High (ops) | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P4 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://milvus.io/docs | OSS/Third-party - verify licence & version
C-06 | C. Open-source on GCP | AP-C | In-process FAISS index with post-filtering | Included only to document why it is rejected for serving | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-16 FAISS | ANN-02/03 | None | None | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-05 post-filter | None - post-filter | n/a | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | UNSUITABLE - fails mandatory ACL requirement | Fast benchmarking | No persistence/ACL model | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | Excluded (benchmark tool only) | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | OSS/Third-party - verify licence & version
C-07 | C. Open-source on GCP | AP-B | As B-01 built with LlamaIndex (or LangChain) abstractions | Isolates framework value vs plain Python + SQL (maintainability, speed of experimentation) | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | LlamaIndex retrievers/postprocessors behind RAG API; ADK agent calls API | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Faster experimentation with ready components | Abstraction churn; ACL filter must still be enforced server-side, not via framework defaults | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | OSS/Third-party - verify licence & version
C-08 | C. Open-source on GCP | AP-C | Qdrant + Qwen3-Embedding-8B (quality ceiling) | Upper bound on embedding quality for cost/benefit comparison | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Self-hosted (large GPU) | EMB-09 Qwen3-Embedding-8B | 4096 (or MRL 1024) | VDB-13 Qdrant | ANN-02 + ANN-05 | Qdrant sparse (BM25) | RRF | SQL WHERE on typed metadata columns | RRK-03 Qwen3-Reranker | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | GKE GPU | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Payload filter | Same | In VPC | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Quality ceiling | Expensive ingestion | High | High | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | OSS/Third-party - verify licence & version
D-01 | D. Hybrid | AP-D | Vertex AI Search for SharePoint + custom AlloyDB index for ServiceNow (user-criteria tokens), fused by RRF | Keeps managed ACLs where proven; custom where source semantics (scripted criteria) need control | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Vertex AI Search SharePoint connector (managed) | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF across systems (each already trimmed) | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | Each system trims before fusion | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Targeted custom effort | Two systems; cross-system score fusion | Medium-High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
D-02 | D. Hybrid | AP-D | Custom parsing/chunking pushed into Vertex AI Search (custom-chunk data store with acl_info) | Tests if custom chunking alone closes the quality gap while keeping managed retrieval + ACL enforcement | Custom extractors -> Discovery Engine document import with acl_info | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-01 | Managed | Managed | Managed | SQL WHERE on typed metadata columns | Managed (+ optional RRK-01) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | Managed + our ACL extraction | Inside Vertex AI Search | acl_info readers (managed) | Managed | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Own chunking with managed serving | We still own ACL extraction for pushed docs; import limits | Medium | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Documented - re-verify before use
D-03 | D. Hybrid | AP-F | Federated delegated search: Graph Search API + ServiceNow KM API with user identity, then rerank + Gemini | No index: source systems enforce ACL in real time | None (query-time only) | Microsoft Graph Search API (delegated, OBO) | Knowledge Management REST API as the user | n/a | n/a | Source snippets / fetched content | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | None | n/a | Source engines | RRF across sources | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | Source systems | ENF-03 delegated | n/a | Source-enforced | Only trimmed candidates sent to Ranking API | n/a | Real time | n/a | Candidate - strongest fidelity; validate latency/throttling | No ACL replication | Relevance control weak; throttling under concurrency; user consent flows | Medium | Medium | High / variable | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P2 (security reference + validation path) | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
D-04 | D. Hybrid | AP-B | Index WITHOUT ACL pre-filter; live source check on top-N only | Documents the limits of post-retrieval validation alone | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | Post-retrieval source check only | None | None | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | UNSUITABLE - fails mandatory ACL requirement (no trimming inside retrieval; unauthorised chunks reach service memory/reranker) |  |  | High | Medium | DB + rerank + Gemini; measure P95 | Counts/relevance distorted; potential side channels | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | Excluded | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
D-05 | D. Hybrid | AP-D | Graph-augmented retrieval (Spanner Graph / BigQuery graph) + vector | Only if relationship/multi-hop questions are a measured gap | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 + graph store | ANN-02 | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Relationship answers | ACL per node/edge; summaries crossing ACL boundaries | Very High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P4 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
D-06 | D. Hybrid | AP-D | Multi-index by document type with query routing (KB in managed, long docs in AlloyDB parent-child) | Different doc types may need different chunking/retrieval | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | KB: whole-article; long docs: CHK-10 | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | Router (ADV-25) + RRF | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Per-type optimisation | Router errors; two systems | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
E-01 | E. Fully custom | AP-E | Fully custom: Docling/Unstructured parsing, bge-m3 on GKE, OpenSearch hybrid + DLS, own reranker, Gemini, own eval & monitoring | Maximum control; benchmark of full ownership cost | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Docling / Unstructured on GKE (+ Tesseract/Document AI OCR) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Self-hosted | EMB-07 bge-m3 | 1024 + sparse | VDB-12 OpenSearch | ANN-02 | OpenSearch BM25 | Hybrid + normalisation | SQL WHERE on typed metadata columns | RRK-02 | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | GKE | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-04: pre-filter inside retrieval + authoritative re-check of top-N before LLM | Filtered k-NN + DLS | DLS | In VPC | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Total control, portability | Very high TCO | Very High | High | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 (cost model only unless evidence) | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
E-02 | E. Fully custom | AP-E | Per-user index partitions | Included only to document why it is rejected | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | ACL tables in AlloyDB (document_acl, principal_membership, identity_map) | ENF-06 | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | UNSUITABLE - fails mandatory ACL requirement at scale (sync infeasible; revocation lag) |  |  | High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | Users x documents explosion | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | Excluded | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Proposed pattern - validate in POC
E-03 | E. Fully custom | AP-E | Custom index + external ReBAC policy engine (OpenFGA / SpiceDB) as authorisation service | Tests a dedicated policy service vs ACL tables in the DB | Custom extractors on Cloud Run Jobs; Pub/Sub fan-out; GCS raw/parsed zones; Cloud Scheduler | Microsoft Graph delta + driveItem permissions; SharePoint REST for role assignments & SP groups | Table API (kb_knowledge, user criteria tables) + Attachment API; sys_updated_on watermark | Document AI Layout Parser (PDF/Office) + HTML parser (pages/KB) | Normalise, boilerplate removal, language detect, MinHash dedup (per ACL set), DLP inspect | CHK-06 heading-aware + CHK-10 parent-child | Google Vertex AI | EMB-01 gemini-embedding-001 | 768 (MRL) - sweep 768/1536/3072 in EXP-03 | VDB-05 AlloyDB | ANN-02 HNSW (pgvector) | PostgreSQL full-text (tsvector) | RRF (RRK-07) in SQL | SQL WHERE on typed metadata columns | RRK-01 Vertex Ranking API (default-004) | Parent expansion, dedup (RRK-09), token budget, citation IDs, glossary definitions | Gemini GA Flash/Pro tier (verify current model IDs) | ADK 2.0.3 agent calls RAG API as tool (FunctionTool/OpenAPI toolset); A2A for remote agents | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | SP: item/scope permissions + SP group membership; SN: KB + article can/cannot-read user criteria | Principal tokens (aad:user, aad:group, sp:group, sn:uc) in allow + deny sets per document; chunks reference document ACL | Validate Entra token; Graph transitiveMemberOf (TTL cache); SP group expansion; SN user-criteria match per user (TTL cache) | OpenFGA / SpiceDB (self-hosted on GKE) | Pre-filter via ListObjects / lookup for user + validation | allowed && principal_set AND NOT denied && principal_set AND status='ok' in same SQL query | Same predicate on FTS branch | Only trimmed candidates sent to Ranking API | ACL-only sync more frequent than content + nightly full reconciliation | acl_version bump invalidates caches; principal cache TTL <= revocation SLA; tombstones on delete | Stale/missing ACL -> exclude (fail closed); requires_source_check -> Graph OBO / SN KM API check | Candidate - validate (EXP-ACL-*) | Expressive relationship model; central audit | List-objects cost at scale; another system to sync | Very High | Medium | DB + rerank + Gemini; measure P95 | We own ACL fidelity end to end | AlloyDB vertical + read pools | Vertex AI, AlloyDB, Cloud Run, GCS, Pub/Sub, Scheduler, Secret Manager, Document AI, DLP | P3 | Graph + ServiceNow API access; Entra app registrations | EXP matrix vs AP-A baseline on same golden set | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | OSS/Third-party - verify licence & version

## 03a_Arch_Patterns
Architecture patterns (textual component diagrams)
Pattern ID | Pattern | Category | Textual component diagram | Data flow | Managed by GCP | Owned by our engineering team | Dependencies | Failure modes | Benefits | Limitations | Suitable use cases | ACL approach | Engineering effort (relative) | Verification status
AP-A | Managed RAG (current baseline): Vertex AI Search / Gemini Enterprise + connectors + Search/Answer API | A. GCP-native managed | [SharePoint, ServiceNow] -> [Vertex AI Search connectors] -> [Data store (aclEnabled)] -> [Search API / Answer API] -> [ADK agent tool] -> [A2A clients] | Connector sync -> managed parse/chunk/embed/index -> query with end-user identity -> trimmed results -> managed answer with citations | Connectors, parsing, chunking, embedding, indexing, ranking, ACL trimming, answer generation | Agent orchestration, prompts (where configurable), app_id config layer, glossary, eval harness | Discovery Engine API, Workforce Identity Federation (Entra ID), connector licences/APIs | Connector sync lag; ACL fidelity gaps (e.g. scripted ServiceNow criteria); opaque relevance regressions on service updates; quota limits | Lowest build/ops effort; ACL model provided; connectors maintained by Google | Limited control of chunking/embedding/ranking internals; harder to tune per app_id; cost model per query | Baseline; production default if custom cannot prove measurable benefit | Connector-synced acl_info + identity provider mapping (managed) | Low | Verified (web check 2026-10-26)
AP-A2 | Managed retrieval + custom post-retrieval (rerank, context, generation) | A. GCP-native managed | [Vertex AI Search Search API] -> [Ranking API / own reranker] -> [Context builder + glossary] -> [Gemini] -> [Check Grounding] -> [ADK] | Managed trimmed retrieval -> custom fusion/rerank -> custom prompt per app_id -> Gemini -> grounding check -> citations | Retrieval + ACL trimming | Rerank, prompts, citations, answer metadata, streaming | As AP-A + Vertex AI Gemini + Ranking API | As AP-A plus custom code defects | Keeps managed ACLs; full control of generation/prompt versioning (FR-CFG-03) | Retrieval quality ceiling still managed | Most likely low-risk improvement path | Managed (unchanged); reranker receives only trimmed results | Low-Medium | Documented - re-verify before use
AP-B | GCP-native custom RAG | B. GCP-native custom | [Graph / ServiceNow extractors on Cloud Run Jobs] -> [GCS raw] -> [Parse (Document AI) / normalise / DLP] -> [Chunk] -> [Vertex embeddings] -> [AlloyDB (vectors + FTS + ACL tables) or Vector Search + AlloyDB policy store] -> [RAG API on Cloud Run] -> [Ranking API] -> [Gemini] -> [ADK tool] | Scheduled/delta extraction -> staged files -> chunks with ACL refs -> embeddings -> index; query: validate Entra token -> resolve principals -> ACL pre-filtered hybrid retrieval -> rerank -> context -> Gemini -> citations | Embedding/generation/ranking models, managed DBs, serverless compute | Connectors, ACL extraction + normalisation + sync, identity resolution, chunking, retrieval, fusion, prompts, eval, monitoring | Graph API + ServiceNow API access, Entra app registration, AlloyDB/Vector Search, Vertex AI | ACL drift; connector throttling; partial sync; index inconsistency between vector and keyword branches | Full control of every retrieval variable; per-app tuning; portable PostgreSQL model | Large engineering & on-call ownership; we must re-implement connector + ACL fidelity | Primary custom candidate | Synchronised ACL-aware index + authoritative validation (hybrid) | High | Proposed pattern - validate in POC
AP-C | Open-source RAG hosted on GCP | C. Open-source on GCP | [Extractors] -> [Unstructured/Docling parse] -> [OSS embeddings on GKE GPU] -> [Qdrant / OpenSearch / Elastic / Milvus on GKE] -> [OSS reranker] -> [Gemini] -> [ADK] | As AP-B but with self-hosted models and stores | GKE control plane, GPUs, storage | Everything above infrastructure incl. upgrades, CVEs, backups | GKE, GPU quota, container supply chain, OSS licences | Cluster/ops failures; library CVEs; model serving saturation | Maximum portability; no per-call model cost; data never leaves VPC | Highest ops burden; GPU capacity; security plugin config errors | Data-residency- or cost-driven cases; teams with platform SRE | DB-native filtering or DLS (Elastic/OpenSearch) + validation | High | OSS/Third-party - verify licence & version
AP-D | Hybrid managed + custom | D. Hybrid | Variants: (1) Vertex AI Search for SharePoint + custom index for ServiceNow fused by RRF; (2) custom ingestion pushing chunks with acl_info into Vertex AI Search; (3) custom retrieval + managed Ranking/Gemini; (4) multiple indexes by document type with routing | Per variant; fusion layer merges trimmed result lists from each system | Whatever stays managed | Fusion, routing, consistent citation model across systems | Both stacks | Inconsistent scoring across systems; double ACL models | Use managed where it is proven (ACLs, connectors), custom where measurable gaps exist | Two systems to operate and evaluate | Most pragmatic if baseline fails on specific query types only | Each system trims independently before fusion | Medium-High | Proposed pattern - validate in POC
AP-E | Fully custom | E. Fully custom | Every box in AP-B/AP-C built and operated by us: ingestion, parsing, normalisation, chunking, embedding, vector + keyword indexes, filtering, rerank, context, prompt mgmt, generation calls, citations, eval, monitoring, re-index | Same as AP-B with no managed retrieval | Only infra primitives | Everything | Many | Every failure mode is ours | Total control | Very high TCO; slow time-to-value; parity with managed connectors/ACLs is a major project | Only with strong evidence of quality/cost gains + platform team | Synchronised index + policy service + validation | Very High | Proposed pattern - validate in POC
AP-F | Federated / delegated retrieval (no central index) | D. Hybrid (security fallback) | [ADK agent] -> [Graph Search API with user OBO token] + [ServiceNow KM API as user] -> [Fusion + rerank] -> [Gemini] | Query fan-out to sources with the user's delegated identity; sources enforce ACLs | Generation | Fan-out, OBO, fusion | Entra OBO, ServiceNow OAuth per user | Source latency/throttling; inconsistent relevance; source outage = no answer | Source is the authorisation source of truth; no ACL replication | Weaker relevance control; latency; rate limits under concurrency | Authoritative validation step; low-volume sensitive content | Delegated to source | Medium | Proposed pattern - validate in POC
AP-G | Vertex AI RAG Engine | B. GCP-native custom (managed orchestration) | [GCS / Drive import] -> [RAG Engine corpus (RagManagedDb or Vector Search)] -> [retrieveContexts] -> [Gemini] | Managed import/chunk/embed; retrieval API | Corpus management, chunking options, embedding | ACL layer (not provided - verify) | Vertex AI | No per-user document ACL model documented - security gap | Fast prototype of custom chunk/embed choices | ACL requirement likely unmet | Prototype / non-sensitive corpora only | To Verify - default UNSUITABLE for ACL'd content | Low | Documented - re-verify before use

## 04_Embeddings
Embedding model catalogue - compare on OUR corpus (EXP-01..06), not public leaderboards
Model ID | Provider | Exact model name | Model type | Modality / language | Max input | Output dims & configuration | Normalisation | Query/doc encoding & prefixes | Similarity metric | Batch / online | Deployment model | Regional availability | Pricing basis | Fine-tuning / adaptation | Licence | Strengths | Limitations | Integration effort | Security & data residency | Official documentation | Lifecycle / version | Verification status | POC priority | Date checked
EMB-01 | Google Vertex AI | gemini-embedding-001 | Dense text embedding (Matryoshka-style truncation) | Text; multilingual; code | 2048 tokens per input (excess silently truncated); 250 texts and 20k tokens per request limits apply to other models - gemini-embedding-001 allows 1 instance per request | 3072 default; output_dimensionality lets you request smaller (e.g. 768 / 1536) | Full-size output is normalised; re-normalise if you truncate client-side or request reduced dims (To Verify per docs) | task_type parameter: RETRIEVAL_DOCUMENT for chunks; RETRIEVAL_QUERY / QUESTION_ANSWERING for queries; title field optional for documents | Cosine or dot product on normalised vectors | Online: 1 input per request (throughput bound by quota); batch prediction - To Verify | Fully managed API (aiplatform.googleapis.com) | Multiple regions + global - check model location page for your residency region | Per input token / character - see Vertex AI generative AI pricing page | Not self-tunable today - To Verify; adapt via contextual chunk text instead | Google Cloud service terms | Strongest Google text model; unifies text-embedding-005 and multilingual-002; configurable dims | 1-instance-per-request limits ingestion throughput (quota planning critical); 3072 dims raise storage/ANN memory | Low | Data stays in GCP; regional endpoint selection; CMEK n/a for stateless call | https://cloud.google.com/vertex-ai/generative-ai/docs/embeddings/get-text-embeddings | GA - check model versions & lifecycle page | Verified (web check 2026-10-26) | P1 - primary candidate | 2026-10-26
EMB-02 | Google Vertex AI | gemini-embedding-2-preview | Dense multimodal interleaved embedding | Text, image, video, PDF (interleaved) | 8192 tokens (per Vector Search 2.0 docs) | 3072 max | To Verify | To Verify | Cosine | To Verify | Managed (Preview) | To Verify | To Verify | No | Google Pre-GA terms | Long input; PDF-native embedding could reduce parsing dependence | Preview - no SLA; behaviour and name may change | Low-Medium | Pre-GA data terms must be reviewed by security | https://docs.cloud.google.com/vertex-ai/docs/vector-search-2/embeddings/autogenerating-embeddings | Preview | Preview/Experimental - re-verify | P3 - watch / optional spike | 2026-10-26
EMB-03 | Google Vertex AI | text-embedding-005 | Dense text embedding | English + code | 2048 tokens | 768 default; output_dimensionality supported | Normalised | task_type (RETRIEVAL_DOCUMENT / RETRIEVAL_QUERY) | Cosine / dot | Online (batched up to 250 inputs / 20k tokens per request) and batch | Managed | Multiple regions - check | Per character/token - pricing page | Embedding tuning historically supported for some versions - To Verify | Google Cloud terms | Cheap, fast, high request batching; good English baseline | English-focused; superseded by gemini-embedding-001 per docs | Low | As EMB-01 | https://cloud.google.com/vertex-ai/generative-ai/docs/embeddings/get-text-embeddings | Check deprecation schedule | Documented - re-verify before use | P2 - cost/throughput baseline | 2026-10-26
EMB-04 | Google Vertex AI | text-multilingual-embedding-002 | Dense text embedding | Multilingual text | 2048 tokens | 768 | Normalised | task_type | Cosine / dot | Online batched + batch | Managed | Multiple regions | Pricing page | To Verify | Google Cloud terms | Multilingual at 768 dims | Superseded by gemini-embedding-001 | Low | As EMB-01 | https://cloud.google.com/vertex-ai/generative-ai/docs/embeddings/get-text-embeddings | Check deprecation schedule | Documented - re-verify before use | P3 - only if multilingual corpus confirmed | 2026-10-26
EMB-05 | Google Vertex AI | multimodalembedding@001 | Dense multimodal (shared text/image/video space) | Image, text (short), video | Text input is short (token limit small - To Verify); image size limits | 1408 default; lower dims selectable (To Verify list) | To Verify | Same space for text query and image | Cosine | Online | Managed | Limited regions - To Verify | Per image / text / video second - pricing page | No | Google Cloud terms | Enables image/diagram retrieval | Short text limit makes it unsuitable for text chunks | Medium | As EMB-01 | https://cloud.google.com/vertex-ai/generative-ai/docs/embeddings/get-multimodal-embeddings | GA - verify | Documented - re-verify before use | P4 - only if image retrieval is a requirement | 2026-10-26
EMB-06 | Google (open weights) | google/embeddinggemma-300m | Dense text embedding, small open model | 100+ languages | 2048 tokens | 768; Matryoshka truncation to 512/256/128 | Normalise after truncation | Prompt templates e.g. 'task: search result / query: ...' and 'title: ... / text: ...' | Cosine | Both (self-hosted) | Self-host: Cloud Run GPU, GKE, Vertex AI endpoint | Any region you deploy | Compute (GPU/CPU hours) - no per-token fee | Full fine-tuning via Sentence Transformers | Gemma Terms of Use (review) | Small, cheap self-hosted; on-device-capable; fine-tunable on domain data | Lower quality than large models; you own serving | Medium | Full control of data path; nothing leaves VPC | https://ai.google.dev/gemma/docs/embeddinggemma | Released 2025 - verify current version | OSS/Third-party - verify licence & version | P2 - self-hosted contender | 2026-10-26
EMB-07 | BAAI (open weights) | BAAI/bge-m3 | Dense + learned sparse + multi-vector (ColBERT-style) in one model | 100+ languages | 8192 tokens | 1024 dense; sparse lexical weights; multi-vector | Normalised dense output | No instruction prefix required | Cosine (dense); dot (sparse) | Both (self-hosted) | Self-host GPU (Cloud Run GPU / GKE / Vertex endpoint) | Any | Compute | Fine-tunable (FlagEmbedding) | MIT | Hybrid dense+sparse from one pass; long input; strong multilingual | 568M params - GPU recommended; sparse output needs an engine that stores sparse vectors | Medium | Full control | https://huggingface.co/BAAI/bge-m3 | v1 (2024) - verify | OSS/Third-party - verify licence & version | P1 - open-source hybrid contender | 2026-10-26
EMB-08 | Microsoft (open weights) | intfloat/multilingual-e5-large-instruct | Dense text embedding (instruction-tuned) | Multilingual | 512 tokens | 1024 | Normalise | Queries need 'Instruct: <task>\nQuery: ' prefix; documents no prefix | Cosine | Both | Self-host | Any | Compute | Fine-tunable | MIT | Mature, well-understood, multilingual | 512-token limit forces small chunks | Medium | Full control | https://huggingface.co/intfloat/multilingual-e5-large-instruct | Stable | OSS/Third-party - verify licence & version | P3 | 2026-10-26
EMB-09 | Alibaba Qwen (open weights) | Qwen/Qwen3-Embedding-0.6B / -4B / -8B | Dense LLM-based embedding (MRL) | 100+ languages; code | 32k tokens | Up to 1024 / 2560 / 4096; user-defined lower dims | Normalise | Instruction on the query side recommended | Cosine | Both | Self-host GPU; vLLM / TEI serving | Any | Compute (4B/8B need larger GPUs) | Fine-tunable | Apache-2.0 | Top-tier public benchmark scores; long context | Large variants expensive to serve at ingestion scale | Medium-High | Full control | https://huggingface.co/Qwen/Qwen3-Embedding-0.6B | 2025 release - verify | OSS/Third-party - verify licence & version | P2 - quality ceiling test | 2026-10-26
EMB-10 | Snowflake (open weights) | Snowflake/snowflake-arctic-embed-l-v2.0 | Dense text embedding (MRL) | Multilingual | 8192 tokens | 1024; MRL to 256 | Normalise | 'query: ' prefix for queries | Cosine | Both | Self-host | Any | Compute | Fine-tunable | Apache-2.0 | Retrieval-focused; compressible dims | Smaller community than BGE/E5 | Medium | Full control | https://huggingface.co/Snowflake/snowflake-arctic-embed-l-v2.0 | v2.0 | OSS/Third-party - verify licence & version | P3 | 2026-10-26
EMB-11 | Nomic (open weights) | nomic-ai/nomic-embed-text-v1.5 | Dense text embedding (MRL) | Mainly English | 8192 tokens | 768; MRL 64-768 | Normalise after truncation | Prefixes 'search_query: ' / 'search_document: ' mandatory | Cosine | Both | Self-host (CPU feasible) | Any | Compute | Fine-tunable | Apache-2.0 | Cheap, long context, CPU-servable | English focus; prefix misuse silently degrades quality | Low-Medium | Full control | https://huggingface.co/nomic-ai/nomic-embed-text-v1.5 | v1.5 | OSS/Third-party - verify licence & version | P3 | 2026-10-26
EMB-12 | Sentence Transformers | sentence-transformers/all-MiniLM-L6-v2 | Small dense bi-encoder | English | 256 word pieces (longer input truncated) | 384 | Normalise | None | Cosine | Both | Self-host CPU | Any | Compute | Fine-tunable | Apache-2.0 | Very fast; useful as a floor baseline and for dedup | Low quality on domain retrieval; short input | Low | Full control | https://huggingface.co/sentence-transformers/all-MiniLM-L6-v2 | Stable | OSS/Third-party - verify licence & version | P4 - floor baseline only | 2026-10-26
EMB-13 | Alibaba (open weights) | Alibaba-NLP/gte-multilingual-base | Dense (+ sparse) encoder | 70+ languages | 8192 tokens | 768 (elastic dims) | Normalise | None | Cosine | Both | Self-host | Any | Compute | Fine-tunable | Apache-2.0 | Encoder-only, fast for long docs | Requires trust_remote_code (supply-chain review) | Medium | Review remote code before use | https://huggingface.co/Alibaba-NLP/gte-multilingual-base | Verify | OSS/Third-party - verify licence & version | P4 | 2026-10-26
EMB-14 | Jina AI | jinaai/jina-embeddings-v3 | Dense with task LoRA adapters (MRL) | Multilingual | 8192 tokens | 1024; MRL down to 32 | Normalise | task parameter (retrieval.query / retrieval.passage) | Cosine | Both / Jina API | Self-host or Jina API | Any / Jina API region | Compute or Jina per-token | Yes | CC BY-NC 4.0 - commercial use needs a licence | Strong long-doc + late-chunking support | Licence blocks commercial self-hosting without agreement | Medium | API option sends data outside GCP | https://huggingface.co/jinaai/jina-embeddings-v3 | Verify | OSS/Third-party - verify licence & version | Excluded unless licence acquired | 2026-10-26
EMB-15 | Cohere | Cohere Embed v4 (embed-v4.0) | Dense multimodal embedding (MRL; int8/binary output) | Multilingual text + images | Long context - To Verify | Configurable (e.g. 256-1536) - To Verify | Normalised | input_type: search_document / search_query | Cosine | Both | Cohere API; availability via Vertex AI Model Garden - To Verify | Cohere API regions / Model Garden regions - To Verify | Per token - Cohere / Marketplace pricing | No | Commercial | Native quantised outputs reduce storage | Third-party processor; cross-cloud egress unless via Model Garden | Low | DPA, residency and egress review required | https://docs.cohere.com/docs/cohere-embed | Verify | To Verify | P4 | 2026-10-26
EMB-16 | OpenAI | text-embedding-3-large | Dense text embedding (MRL) | Multilingual | 8191 tokens | 3072; dimensions parameter to shorten | Normalised | None | Cosine | Online + Batch API | OpenAI / Azure OpenAI API | OpenAI / Azure regions | Per token - official pricing page | No | Commercial | Widely benchmarked reference | Data leaves GCP; adds second cloud dependency | Low | DPA + cross-cloud network review | https://platform.openai.com/docs/guides/embeddings | Verify | OSS/Third-party - verify licence & version | P4 - reference only if policy allows | 2026-10-26
EMB-17 | Voyage AI | voyage-3.5 / voyage-context-3 | Dense; contextualised chunk embeddings (context-3) | Multilingual | 32k tokens - To Verify | 256-2048 configurable - To Verify | Normalised | input_type query / document | Cosine | Both | Voyage API (also marketplace offerings - To Verify) | To Verify | Per token | Custom models on request | Commercial | context-3 embeds chunk with document context natively | Third-party processor | Low | DPA + egress review | https://docs.voyageai.com/docs/embeddings | Verify | To Verify | P4 | 2026-10-26
EMB-18 | Own (Sentence Transformers) | Fine-tuned bi-encoder (e.g. EMB-06/07 base + domain pairs) | Domain-adapted dense model | As base model | As base model | As base model | Normalise | As base model | Cosine | Both | Self-host; training on Vertex AI custom training / GKE | Any | Training + serving compute | Contrastive fine-tuning with mined hard negatives from KB/SharePoint | Inherits base licence | Learns company acronyms / jargon; can beat larger generic models in-domain | Needs labelled/synthetic pairs; retraining = full re-embed | High | Training data may include sensitive content - govern it | https://sbert.net/docs/sentence_transformer/training_overview.html | Pattern | Proposed pattern - validate in POC | P3 - only if EXP shows vocabulary gap | 2026-10-26
EMB-19 | Naver (open weights) | naver/splade-v3 | Learned sparse (lexical expansion) | English | 512 tokens | Vocabulary-sized sparse vector | n/a | Separate query/doc encoders in some variants | Dot product | Both | Self-host GPU | Any | Compute | Fine-tunable | Licence CC BY-NC-SA - To Verify (commercial restriction likely) | Better than BM25 on vocabulary mismatch; interpretable | Licence; needs sparse-capable index | Medium | Full control | https://huggingface.co/naver/splade-v3 | Verify | OSS/Third-party - verify licence & version | P4 - consider BM25 or bge-m3 sparse first | 2026-10-26
EMB-20 | Answer.AI / Stanford (open weights) | answerdotai/answerai-colbert-small-v1 (ColBERT late interaction) | Multi-vector late interaction | English | 512 tokens | 96-128 dims per token vector | Normalised | Query/doc markers handled by library | MaxSim | Both | Self-host (RAGatouille / PyLate / Vespa/Qdrant multivector) | Any | Compute + much larger storage | Fine-tunable | Apache-2.0 - verify | High precision; good as reranker over candidates | Storage grows per token; few managed GCP stores support multivector natively | High | Full control | https://huggingface.co/answerdotai/answerai-colbert-small-v1 | Verify | OSS/Third-party - verify licence & version | P4 - reranker use only | 2026-10-26

## 05_Ingestion
Large-scale ingestion & preprocessing (Dimension separates volume, complexity, update frequency, security)
Ingest ID | Technique | Dimension | Problem addressed | Implementation pattern (GCP) | Prerequisites | Trade-offs | Failure scenarios | POC experiment | Priority
ING-01 | Full initial ingestion | Volume | Bootstrap index from all in-scope content | Cloud Run Jobs (parallel tasks) or Dataflow; GCS raw zone; manifest table of doc IDs | Source API access; quotas | Long runtime; throttling | Throttling stalls; partial loads | EXP-30 throughput & cost per 10k docs | P1
ING-02 | Incremental ingestion (delta) | Update frequency | Keep index fresh without full reloads | Graph delta tokens per drive; ServiceNow sys_updated_on watermark; checkpoint table | Change tokens persisted | Delta token expiry -> resync | Lost delta token; clock skew on watermarks | EXP-31 freshness lag | P1
ING-03 | Batch vs streaming | Update frequency | Latency of updates vs cost | Batch: Cloud Scheduler -> Cloud Run Job; Near-real-time: Graph change notifications / ServiceNow business rule -> Pub/Sub | Webhook endpoint (public HTTPS with validation) | Streaming adds complexity; webhooks still need reconciliation | Missed notifications | Measure freshness need vs FR-GLO-06-like targets | P2
ING-04 | Parallel / distributed processing | Volume | Throughput at millions of docs | Pub/Sub fan-out to Cloud Run workers; Dataflow for heavy transforms; Batch for GPU parsing | Quotas for embeddings + Document AI | Parallelism bounded by source & model quotas | Quota exhaustion -> 429 storms | EXP-30 | P2
ING-05 | GCS staging zones | Volume | Replayability, lineage, reprocessing without re-extraction | raw/ (as extracted) -> parsed/ (JSON) -> chunks/ ; object versioning; CMEK | Bucket policy, retention | Storage cost; sensitive copies must be governed + deleted on source delete | Orphaned copies after source deletion | Verify deletion propagation (EXP-ACL-07) | P1
ING-06 | Document parsing & extraction | Complexity | PDF/Office/HTML -> clean text + structure | Document AI Layout Parser (layout + tables + chunking); HTML via BeautifulSoup/trafilatura; XLSX via openpyxl/pandas | File type inventory | Cost per page vs quality | Encrypted (sensitivity label/IRM) files unparseable | EXP-32 parser comparison | P1
ING-07 | OCR for scanned documents | Complexity | Image-only PDFs | Document AI OCR processor | Volume of scanned docs (AQ) | Per-page cost | Low-quality scans | Subset test | P2
ING-08 | Layout, headings, tables, page structure | Complexity | Preserve structure for heading-aware/table chunking | Layout Parser output -> heading_path, page_no, table blocks | - | - | Mis-detected headings | CPX-05 | P1
ING-09 | Metadata extraction | Complexity | Filters (FR-FLT-01), citations, ranking boosts | Map source fields: title, author/owner, created/modified, site/library/path, KB, category, workflow_state, language | Field mapping per source | - | Missing/inconsistent fields | Metadata completeness metric | P1
ING-10 | Document classification | Complexity | Route doc types to chunkers/indexes; sensitivity tagging | Rules first; Gemini Flash classification if needed | Label taxonomy | LLM cost | Misclassification | Optional | P3
ING-11 | Language detection | Complexity | Choose analyzers and multilingual models | fastText/lingua or Cloud Translation detect | - | - | Mixed-language docs | Corpus profile | P2
ING-12 | Duplicate & near-duplicate detection | Complexity | Same content in many libraries / KB versions | SHA-256 for exact; MinHash/LSH (datasketch) for near-dup; keep per-ACL copies | - | Never collapse docs with different ACLs | False merges hiding authorised copy | Dedup rate + answer diversity | P2
ING-13 | Content normalisation & boilerplate removal | Complexity | Navigation, footers, signatures pollute chunks | Readability/trafilatura for HTML; header/footer detection from layout | - | Over-stripping | Lost content | Spot-check sample | P2
ING-14 | Versioning | Update frequency | Track content_version; avoid serving superseded text | Store source version/etag + content hash; replace chunks atomically per document | - | - | Mixed old/new chunks served | EXP-31 | P1
ING-15 | Change-data detection | Update frequency | Skip unchanged docs | Content hash comparison; Graph eTag/cTag; sys_mod_count | - | - | Hash over volatile fields causes churn | Re-embed rate | P1
ING-16 | Idempotency | Volume | Safe retries | Deterministic chunk IDs = hash(document_id, content_version, chunk_index); upserts | - | - | Duplicate chunks after retries | Retry test | P1
ING-17 | Retry & dead-letter handling | Volume | Transient errors, poison docs | Pub/Sub retry policy + dead-letter topic; error table with reason | - | - | Silent drops | Inject failures | P1
ING-18 | Data validation | Complexity | Garbage in index | Schema checks: non-empty text, ACL present, valid IDs, size limits; reject = quarantine (never index without ACL) | - | - | Docs without ACL indexed as public (MUST NOT) | EXP-ACL-08 | P0
ING-19 | Backpressure & rate limits | Volume | Graph 429 / ServiceNow rate rules / Vertex quotas | Token-bucket per API; honour Retry-After; Cloud Tasks rate limits | Quota values | Slower ingestion | Throttling bans | Throughput test | P1
ING-20 | Batch sizing | Volume | Embedding & DB write efficiency | Batch per model limits (gemini-embedding-001: 1 instance/request; text-embedding-005: up to 250 texts / 20k tokens) | Model choice | - | Request rejects | EXP-30 | P2
ING-21 | Checkpointing | Volume | Resume long runs | Per-source checkpoint table (delta token, watermark, page cursor) committed after durable writes | - | - | Checkpoint ahead of data = data loss | Kill-and-resume test | P1
ING-22 | Reprocessing | Complexity | Change parser/chunker/model | Re-run from GCS parsed/ zone; blue/green index with alias switch | Storage of parsed zone | Double storage during switch | Partial switch | Re-index drill | P2
ING-23 | Incremental embedding updates | Update frequency | Only re-embed changed chunks | Chunk hash -> skip unchanged embeddings | - | - | Model version mix in one index (MUST NOT) | Track embedding_model_version per row | P1
ING-24 | Index consistency | Update frequency | Vector, keyword and ACL stores agree | Single transaction (AlloyDB) or outbox pattern + consistency checker job | - | Multi-store designs need reconciliation | Chunk in vector index without ACL row | Consistency checker metric | P1
ING-25 | Data lineage | Security | Trace answer -> chunk -> document -> source version | Lineage columns + BigQuery audit table; Dataplex lineage optional | - | - | Untraceable citations | Audit sampling | P2
ING-26 | Access-control metadata propagation | Security | ACL must follow content through every stage | ACL extracted in same run as content; chunks reference document ACL by document_id + acl_version (never copied loosely) | ACL model (sheet 21) | - | Chunk-level ACL drift | EXP-ACL-01..03 | P0
ING-27 | PII & sensitive-data handling | Security | FR-SEC-08 | Sensitive Data Protection (DLP) inspect/de-identify per data-set policy; keep text out of logs | Data-set policies | Cost per GB inspected | PII in logs/traces | EXP-ACL-15 | P1
ING-28 | Separate ACL-only sync | Security | ACL changes without content change | Permission-change detection (Graph delta with sharing-change headers - verify; ServiceNow user criteria table watermarks) + group membership delta | - | More API calls | Revocation lag | EXP-ACL-05/06 | P0

## 05a_Source_Connectors
Source-specific extraction & ACL workflows (SharePoint, ServiceNow, Entra ID)
Source ID | Source | Topic | Options / APIs | Details & semantics | Depends on our tenant/instance? | ACL impact | Failure recovery / reconciliation | Recommended POC approach | Documentation | Verification status | Date checked
SP-01 | SharePoint Online | Supported content types | Document libraries (driveItems: PDF, DOCX, PPTX, XLSX, TXT, HTML), modern site pages, lists/list items, news | FR-CON-01 scope: sites, libraries, lists, pages | Yes - site inventory | Each type has its own permission scope | - | Inventory in-scope sites first (AQ-01) | https://learn.microsoft.com/en-us/graph/api/resources/sharepoint | Documented - re-verify before use | 2026-10-26
SP-02 | SharePoint Online | Authentication | Entra ID app registration; application permissions (Sites.Selected preferred, or Sites.Read.All / Files.Read.All); certificate credential; delegated (OBO) for user-context checks | Sites.Selected requires per-site grant by admin - least privilege | Yes - tenant admin consent | Ingestion app identity must never be used to answer user queries | Cert rotation | Request Sites.Selected for POC sites only | https://learn.microsoft.com/en-us/graph/permissions-selected-overview | Documented - re-verify before use | 2026-10-26
SP-03 | SharePoint Online | APIs & connectors | Microsoft Graph v1.0 (sites, drives, driveItem, listItem, permissions, delta); SharePoint REST (/_api/web/roleassignments, sitegroups); Vertex AI Search SharePoint Online connector | Graph does not expose all SharePoint-group membership details - SharePoint REST needed | Partly | SP groups are site-local principals | - | Compare connector ACL output vs direct API extraction (EXP-ACL-01) | https://cloud.google.com/generative-ai-app-builder/docs/connect-sharepoint | Documented - re-verify before use | 2026-10-26
SP-04 | SharePoint Online | Full extraction | Enumerate sites -> drives -> items (paged with @odata.nextLink); download content | Large libraries; 5000-item list view threshold applies to REST queries on lists | Yes | - | Manifest + checkpoint per drive | Cloud Run Job per site | https://learn.microsoft.com/en-us/graph/api/driveitem-list-children | Documented - re-verify before use | 2026-10-26
SP-05 | SharePoint Online | Incremental extraction | driveItem delta (per drive) returns changed + deleted items and a deltaLink token | Token can expire -> full resync of that drive (handle 410/resyncRequired) | No | Content delta does not reliably signal permission changes by default | Store deltaLink per drive | Use delta for content; separate permission sync (SP-11) | https://learn.microsoft.com/en-us/graph/api/driveitem-delta | Documented - re-verify before use | 2026-10-26
SP-06 | SharePoint Online | Metadata | name, webUrl, createdBy, lastModifiedBy, lastModifiedDateTime, eTag/cTag, parentReference (site/drive/path), listItem fields, sensitivity label (To Verify API) | Map to filter fields (FR-FLT-01) | Custom columns: yes | parentReference used for inheritance tracing | - | Mapping workshop | https://learn.microsoft.com/en-us/graph/api/resources/driveitem | Documented - re-verify before use | 2026-10-26
SP-07 | SharePoint Online | IDs, URLs, versions | driveItem id + driveId (stable), webUrl (changes on move/rename), eTag/cTag for change detection; version history API | Use (driveId, itemId) as source_document_id - never URL | No | Moves change URL and possibly inherited ACL | Re-resolve webUrl on each sync | Store both | https://learn.microsoft.com/en-us/graph/api/driveitem-list-versions | Documented - re-verify before use | 2026-10-26
SP-08 | SharePoint Online | Pagination, throttling, limits | @odata.nextLink paging; HTTP 429/503 with Retry-After; resource-unit based app throttling per tenant | Decorate traffic (User-Agent); use $select; batch ($batch, max 20 requests) | Yes - tenant load | Throttling delays ACL sync -> revocation lag | Back-off + resume from checkpoint | Token bucket in extractor | https://learn.microsoft.com/en-us/sharepoint/dev/general-development/how-to-avoid-getting-throttled-or-blocked-in-sharepoint-online | Documented - re-verify before use | 2026-10-26
SP-09 | SharePoint Online | Deletes & updates | delta returns 'deleted' facet; recycle bin; site deletion | Delete -> tombstone document + all chunks immediately, purge copies in GCS | No | Deleted doc must disappear from all paths | Periodic full ID reconciliation per drive | EXP-ACL-07 | https://learn.microsoft.com/en-us/graph/api/driveitem-delta | Documented - re-verify before use | 2026-10-26
SP-10 | SharePoint Online | ACL extraction | Graph driveItem permissions (roles, grantedToV2, grantedToIdentitiesV2, link, inheritedFrom); SharePoint REST RoleAssignments + HasUniqueRoleAssignments; site groups (Owners/Members/Visitors) membership | Principals: Entra users, Entra (incl. M365) groups, SharePoint groups (may contain Entra groups), special claims (e.g. 'Everyone except external users'), sharing links (anyone / organisation / specific people) | Yes - sharing policy | Sharing-link semantics are the hardest: 'organisation' link grants access only to holders of the link; recommend NOT treating as org-wide (fail closed) unless security approves (FR-CON-01 open question) | Per-item fetch is expensive: fetch only for items with unique permissions; inherit from parent otherwise | Extract via REST + Graph; compare with connector (EXP-ACL-01) | https://learn.microsoft.com/en-us/graph/api/driveitem-list-permissions | Documented - re-verify before use | 2026-10-26
SP-11 | SharePoint Online | Permission inheritance & change sync | Inheritance site -> library -> folder -> item; broken inheritance per item; permission changes on a folder affect all descendants | Detecting permission-only changes: delta with sharing-change headers (Prefer: deltashowsharingchanges / hierarchicalsharing - To Verify) or periodic ACL re-scan | No | Folder ACL change must fan out to all child chunks (acl_version bump) | Nightly full ACL reconciliation for POC sites | Measure detection latency (EXP-ACL-05) | https://learn.microsoft.com/en-us/graph/api/driveitem-delta | To Verify | 2026-10-26
SP-12 | SharePoint Online | Explicit deny | SharePoint Online item permissions are grant-based; explicit deny not typical (policies / sensitivity labels / conditional access can still restrict) | Model deny set anyway for ServiceNow and future sources | Yes | Sensitivity-label-encrypted files: decide exclude vs rights-aware extraction | - | Exclude encrypted files in POC (AQ-12) | https://learn.microsoft.com/en-us/purview/sensitivity-labels | To Verify | 2026-10-26
SP-13 | SharePoint Online | Audit & lineage | Store source item id, eTag, extraction run id, permission snapshot hash | - | No | Proves which ACL version was enforced at answer time | Audit table in BigQuery | Required for FR-SEC-07 | - | Proposed pattern - validate in POC | 2026-10-26
SN-01 | ServiceNow | Supported content types | Knowledge articles (kb_knowledge) in knowledge bases (kb_knowledge_base); attachments (sys_attachment); optionally catalog items (sc_cat_item) and resolved incidents | FR-CON-02 open question: which tables beyond KB | Yes - instance config | Each table has different ACLs; incidents carry PII | - | KB only in POC phase 1 (AQ-02) | https://developer.servicenow.com/dev.do#!/reference/api/latest/rest/c_TableAPI | Documented - re-verify before use | 2026-10-26
SN-02 | ServiceNow | Authentication | OAuth 2.0 (inbound OAuth client; grant types available depend on release - verify client credentials support), basic auth (avoid), mutual TLS | Dedicated integration user with least roles needed to read KB + user criteria tables | Yes | Integration user must be able to read ALL in-scope articles, so its rights must never be used for end users | Credential rotation | OAuth with Secret Manager | https://www.servicenow.com/docs/ (OAuth inbound - release-specific path) | To Verify | 2026-10-26
SN-03 | ServiceNow | APIs & connectors | Table API (/api/now/table/{table}); Attachment API (/api/now/attachment); Knowledge Management REST API (/api/sn_km_api/knowledge/articles) evaluates access for the calling user; Vertex AI Search ServiceNow connector | KM API usable as authoritative 'can this user read' check if called with user identity (To Verify plugin availability) | Yes - plugins | KM API = delegated authorisation option | - | Table API for ingestion; KM API for validation spike | https://cloud.google.com/generative-ai-app-builder/docs/connect-servicenow | Documented - re-verify before use | 2026-10-26
SN-04 | ServiceNow | Full & incremental extraction | sysparm_query with workflow_state=published^ORDERBYsys_updated_on; sysparm_fields; sysparm_limit + sysparm_offset paging; watermark on sys_updated_on | Use sys_id as source_document_id; number (KBxxxx) as display ID; version fields if KM versioning enabled | Yes | - | Overlapping watermark window + idempotent upserts | Cloud Run Job + checkpoint | https://developer.servicenow.com/dev.do#!/reference/api/latest/rest/c_TableAPI | Documented - re-verify before use | 2026-10-26
SN-05 | ServiceNow | Deletes & state changes | Hard deletes (sys_audit_delete if audited); retired / outdated workflow_state; valid_to expiry | Treat retired/outdated/expired as delete | Yes | Must remove from index promptly | Periodic full sys_id reconciliation | EXP-ACL-07 | - | To Verify | 2026-10-26
SN-06 | ServiceNow | Rate limits | Instance rate-limit rules (per user/role/endpoint), semaphores, transaction quotas; HTTP 429 | Coordinate with ServiceNow platform team | Yes | Throttled ACL sync -> revocation lag | Back-off + resume | Agree limits with platform owners | - | To Verify | 2026-10-26
SN-07 | ServiceNow | ACL semantics - user criteria | KB level: can read / cannot read user criteria (kb_uc_can_read_mtom, kb_uc_cannot_read_mtom); article level: can_read_user_criteria / cannot_read_user_criteria fields; user_criteria records match users, groups, roles, companies, departments, locations, with 'match all' option and optional advanced script | 'Cannot read' overrides 'can read' (explicit deny); empty-criteria default behaviour depends on instance properties - To Verify | Yes | Scripted user criteria CANNOT be faithfully replicated statically | Store criteria IDs as principals; resolve per user | Recommended: index user-criteria sys_ids as principal tokens (sn:uc:<sys_id>) on articles; at query time resolve which criteria the user matches (evaluated in ServiceNow, cached with TTL) | https://www.servicenow.com/docs/ (Knowledge user criteria - release-specific path) | To Verify | 2026-10-26
SN-08 | ServiceNow | ACL semantics - table/record ACLs | sys_security_acl rules on kb_knowledge (read), roles, conditions, scripts; query business rules; domain separation if enabled | Record ACLs can further restrict beyond user criteria | Yes | Must be checked or proven not to restrict in-scope KBs | - | Confirm with ServiceNow admins which ACLs apply (AQ-03) | - | To Verify | 2026-10-26
SN-09 | ServiceNow | User, group, role resolution | sys_user (user_name, email, maybe Entra objectId via SSO mapping), sys_user_grmember, sys_user_has_role (incl. inherited), sys_group_has_role, cmn_department, cmn_location, core_company | Identity mapping Entra UPN/email -> sys_user required (FR-SEC-02 open question) | Yes | Unmapped user = no ServiceNow results (fail closed) | Reconcile mapping table daily | Mapping table + coverage metric (M-SEC-08) | - | To Verify | 2026-10-26
SN-10 | ServiceNow | Permission change sync | Watermarks on user_criteria, kb_uc_*_mtom, sys_user_grmember, sys_user_has_role | Membership change changes which criteria a user matches -> handled at query time via per-user criteria cache TTL | Yes | Revocation delay = cache TTL + sync lag | Nightly full reconciliation | EXP-ACL-06 | - | Proposed pattern - validate in POC | 2026-10-26
SN-11 | ServiceNow | Audit & lineage | sys_id, sys_mod_count, sys_updated_on, extraction run id, criteria snapshot hash | - | No | Proves enforcement | BigQuery audit table | FR-SEC-07 | - | Proposed pattern - validate in POC | 2026-10-26
ID-01 | Entra ID | User identity at RAG API | Validate Entra ID access token (issuer, audience, signature, expiry) at RAG service; extract oid/upn | Calling apps authenticate with app registrations; app_id bound to calling client (FR-SEC-06) | Yes | Never accept user identity from an unsigned header or agent text | - | Token validation middleware | https://learn.microsoft.com/en-us/entra/identity-platform/access-tokens | Documented - re-verify before use | 2026-10-26
ID-02 | Entra ID | Group membership incl. nested | Graph /users/{id}/transitiveMemberOf; groups claim in token has overage limit (large group counts require Graph call) | Cache per user with TTL <= agreed revocation SLA | Yes | Stale cache = revocation lag | Group delta query for proactive invalidation | EXP-ACL-05 | https://learn.microsoft.com/en-us/graph/api/user-list-transitivememberof | Documented - re-verify before use | 2026-10-26
ID-03 | Entra ID | Delegated checks (OBO) | OAuth 2.0 On-Behalf-Of to call Graph as the user (authoritative access check: GET driveItem as user -> 200/403) | Adds latency per candidate; batch top-N | Yes - consent | Authoritative validation option | Fallback to fail-closed on errors | Spike EXP-ACL-12 | https://learn.microsoft.com/en-us/entra/identity-platform/v2-oauth2-on-behalf-of-flow | Documented - re-verify before use | 2026-10-26
ID-04 | Google Cloud | Workforce Identity Federation (for managed baseline) | Vertex AI Search ACLs with Entra ID require WIF (or synced Google identities); google.subject mapped to email for third-party connectors | Baseline already depends on this - confirm current config | Yes | Mapping mismatch = missing results or leakage | - | Document current WIF config (AQ-08) | https://cloud.google.com/iam/docs/workforce-identity-federation | Verified (web check 2026-10-26) | 2026-10-26

## 06_Chunking
Chunking strategy catalogue (sizes are starting hypotheses - select empirically via 06a)
Chunk ID | Strategy | Recommended use cases | Starting chunk size (hypothesis) | Overlap (hypothesis) | Tokenizer dependency | Metadata requirements | Advantages | Limitations | Storage impact | Embedding cost impact | Precision / recall considerations | Context fragmentation risk | Boundary preservation | Fit: SharePoint / ServiceNow | Implementation options | Experiment design | POC priority
CHK-01 | Fixed-size (characters) | Quick baseline; uniform text | 1000-2000 chars | 10-15% | None | doc_id, offset, ACL ref | Simple, deterministic | Cuts sentences/tables; ignores structure | Baseline | Baseline | Unpredictable - boundaries random | High | Poor | Weak for both | LangChain CharacterTextSplitter; 20 lines of Python | Control arm for CPX experiments | P1 (control)
CHK-02 | Token-based fixed | Model-limit-aware baseline | 256 / 512 / 1024 tokens | 0 / 10% / 20% | Yes - use the embedding model tokenizer | doc_id, token span | Guarantees fit in model window | Same structural blindness | Baseline | Predictable | Size is the main lever | High | Poor | Weak | tiktoken / HF tokenizers; LlamaIndex TokenTextSplitter | CPX-01..03 size/overlap sweeps | P1
CHK-03 | Sentence-based | Prose, KB answers | 3-8 sentences (~200-400 tokens) | 1 sentence | Sentence segmenter (language-specific) | sentence span | Clean boundaries | Very short or very long sentences; lists | Slightly more chunks | Slightly higher | Higher precision | Medium | Good at sentence level | Good for KB prose | spaCy / NLTK / LlamaIndex SentenceSplitter | Compare vs CHK-02 at equal mean size | P2
CHK-04 | Paragraph-based | Well-authored docs, KB articles | 1-3 paragraphs, capped at max tokens | 0-1 paragraph | Max-token cap | paragraph index | Respects author intent | Paragraph sizes vary a lot | Varies | Varies | Good topical coherence | Medium | Good | Good | Custom HTML/DOCX parser splitter | Compare vs CHK-06 | P2
CHK-05 | Recursive character splitting | General mixed text | 512-1024 tokens equivalent | 10-15% | Optional token length fn | separators used | Good default; tries paragraph > sentence > word | Still structure-unaware for headings/tables | Baseline | Baseline | Reasonable | Medium | Medium | Medium | LangChain RecursiveCharacterTextSplitter | Strong default control arm | P1
CHK-06 | Structure / heading-aware (section chunking) | SharePoint pages, DOCX, PDF with headings, KB articles with H2/H3 | Section; split oversized sections recursively to <= 512-1024 tokens | Prepend heading path instead of overlap | Max-token cap | heading_path, section_id, page_no, doc title | Semantic units; heading path gives context for embedding | Needs reliable layout extraction | Similar | Similar | Typically higher precision for Q&A - measure | Low | High | Strong for both sources | Document AI Layout Parser chunking; Vertex AI Search layout parser; Unstructured / Docling; custom HTML parser | CPX-05 vs CHK-05 with same model | P1
CHK-07 | Page-aware | Scanned PDFs, slide decks (PPTX), forms | 1 page / 1 slide (split if large) | 0 | Max cap | page_no, slide_no | Citations to page; natural for slides | Pages cut across sections | Similar | Similar | Good for citation correctness | Medium | Medium | Good for PPTX/PDF in SharePoint | Document AI OCR / Layout Parser | Citation correctness metric (M-AQ-04) | P2
CHK-08 | Semantic chunking | Long unstructured text with topic shifts | Variable (breakpoint on embedding distance) | 0 | Needs embedding model at chunk time | breakpoint scores | Topic-coherent | Extra embedding cost; unstable; often no better than structure-aware | Similar | +1 embedding pass | Mixed evidence - must prove | Low-Medium | Medium | Weak advantage when structure exists | LlamaIndex SemanticSplitterNodeParser; LangChain SemanticChunker | Only if CHK-06 underperforms on unstructured docs | P3
CHK-09 | Sliding window | Dense technical text where answers straddle boundaries | 256-512 tokens | 25-50% | Yes | window index | Reduces boundary misses | Many near-duplicate chunks; ranking redundancy | High (+30-100%) | High | Recall up; precision and diversity down | Low | High | Medium | Any splitter with stride | CPX-04 overlap sweep | P3
CHK-10 | Parent-child (small-to-big) | Precise matching but rich context for generation | Child 128-256 tokens; parent 1024-2048 or section | Child 0-10% | Yes | parent_id, child_id, ACL inherited from document | Precise retrieval + coherent context | Two-level storage; context budget grows | Medium (+children) | Children embedded only | Precision from child, completeness from parent | Low | High | Strong for long SharePoint docs | LlamaIndex HierarchicalNodeParser + AutoMergingRetriever; custom SQL | CPX-07 vs CHK-06 on answer completeness | P1
CHK-11 | Hierarchical (multi-level) | Very long docs, manuals, policies | Levels: doc summary / section / paragraph | 0 | Yes | level, parent chain | Supports coarse-to-fine retrieval | Complexity; summary cost | Higher | Higher (+summaries) | Good for broad questions | Low | High | Policies, manuals | LlamaIndex; RAPTOR-style trees | Only if broad/overview queries fail (ADV-05) | P3
CHK-12 | Document / section summary indexing | Routing and overview questions | 1 summary per doc / section (100-300 tokens) | n/a | LLM | summary_of, model/prompt version | Finds the right document for vague queries | LLM cost at ingestion; summaries can hallucinate | Low | + LLM generation cost | Helps recall@doc level | n/a | n/a | Good for SharePoint libraries | Gemini Flash batch summarisation | EXP on vague-query subset | P3
CHK-13 | Table-aware | Spreadsheets (XLSX), PDF tables, ServiceNow catalog tables | Row groups with header repeated; or table as markdown <= max tokens | Repeat header row | Yes | table_id, header, sheet name | Keeps header-value relationships | Big tables; numeric Q&A still hard | Medium | Medium | Large gains on table questions | Medium | High | XLSX/CSV in SharePoint; structured BigQuery/Cloud SQL sources (FR-CON-03/04) | Document AI Layout Parser tables; pandas for XLSX/CSV | Table-question subset of golden set | P2
CHK-14 | Code-aware | Code snippets in KB, scripts | Function/class level | 0 | Language parser | language, symbol | Preserves syntax units | Only relevant if code content exists | Low | Low | Good for code questions | Low | High | Probably rare | LangChain language splitters; tree-sitter | Only if code content confirmed (AQ-05) | P4
CHK-15 | Layout-aware / multimodal | Scanned PDFs, diagrams, slides with images | Region/block level | 0 | Layout model | bounding boxes, figure captions | Captures figures, captions, reading order | Costly parsing; image retrieval needs multimodal embeddings | Medium | Medium-High | Needed when key facts are in images | Medium | High | PPTX/PDF with diagrams | Document AI Layout Parser / OCR; Gemini document understanding | Only if scanned/visual docs are significant | P3
CHK-16 | Contextual chunk enrichment | Any chunk that is ambiguous out of context | Same as base strategy | Same | LLM | context_prefix, generator version | Adds doc/section context to each chunk before embedding + BM25 | LLM cost per chunk at ingest and re-index | +10-20% text | + LLM pass | Reported recall gains in literature - measure on our corpus | Reduces fragmentation | High | Strong for terse KB snippets | Gemini Flash prompt with document + chunk | ADV-01 experiment | P2
CHK-17 | Late chunking | Long documents with cross-chunk references | Embed full doc with long-context model then pool per chunk | 0 | Long-context embedding model | token spans | Chunk vectors carry document context without LLM cost | Needs long-context model with token outputs (self-hosted); not supported by Vertex APIs | Same | One long pass | Promising; immature | Low | High | Long SharePoint docs | jina / bge-m3 self-hosted pooling code | Optional research spike | P4

## 06a_Chunk_Param_Matrix
Chunk parameter matrix - vary ONE factor at a time
CPX ID | Factor under test | Levels | Held constant | Corpus / query subset | Metrics | Selection rule
CPX-01 | Chunk size (token-based) | 256 / 512 / 1024 tokens | Strategy CHK-02, overlap 10%, model, exact search | DS-01, DS-02 dev | Recall@20, NDCG@10, chunks count, storage | Smallest size within 1 NDCG point of best
CPX-02 | Chunk size (heading-aware cap) | max 512 / 1024 / 2048 | Strategy CHK-06, overlap 0 + heading path | Same | Same | Same
CPX-03 | Chunk size per doc type | KB articles vs long docs vs slides | Best strategy per type | Stratified subsets | Same per stratum | Per-type setting allowed if gain >= 2 points
CPX-04 | Overlap | 0% / 10% / 20% / 50% | Size fixed at CPX-01 winner | Same | Recall@20, storage, embed cost | Keep 0 unless >= 1 point recall
CPX-05 | Strategy | CHK-05 vs CHK-06 vs CHK-03 vs CHK-08 | Mean chunk size matched (+-10%) to avoid size confound | Same | Recall, NDCG, completeness | Simplest strategy within noise of best
CPX-06 | Heading path prefix | None / title only / full heading path | CHK-06 | Same | Recall, NDCG | Adopt if gain
CPX-07 | Parent-child sizes | child 128/256 x parent section/1024/2048 | Retrieval stack | Long-doc stratum | Completeness, faithfulness, tokens | Best completeness per token
CPX-08 | Table handling | Plain text vs markdown table vs row-group with header | Parser fixed | Table stratum | Recall on table questions | Adopt if gain

## 07_Vector_Stores
Vector store / search engine selection (product features vs underlying library noted separately)
Store ID | Product | Category | Managed vs self-managed | Underlying engine / library | Index types / ANN | Metadata filtering | Hybrid (keyword+vector) | Update / delete behaviour | Scaling & HA | Backup / DR | Multi-tenancy | Platform access control | Fit for document-ACL filtering (our mandatory req.) | Data residency | Capacity / latency considerations | Operational complexity | Pricing basis (see link) | Lock-in | Best fit | Official documentation | Verification status | POC priority | Date checked
VDB-01 | Vertex AI Search (Discovery Engine) data store - CURRENT BASELINE | Managed search + RAG service | Fully managed | Google proprietary search/ranking stack | Not exposed (managed semantic + keyword retrieval) | Filter expressions on structured / indexed metadata fields | Built-in (keyword + semantic blended) | Connector/API driven re-index; managed | Managed by Google | Managed; export/re-import via API - To Verify | Per app/data store; Gemini Enterprise apps | IAM on project/app; aclEnabled data stores with Google Identity or Workforce Identity Federation (Entra ID supported via WIF) | STRONG for connector-sourced data (acl_info readers per doc; third-party connectors sync ACLs) - must verify ServiceNow user criteria + SharePoint fidelity | Multi-region: global / us / eu locations - verify | Google-managed; no ANN tuning | Low | Per query / per GB indexed / per connector - see AI Applications pricing | High (proprietary relevance, connectors, ACL model) | Baseline; managed ACL-aware search | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Verified (web check 2026-10-26) | P0 - baseline (mandatory) | 2026-10-26
VDB-02 | Vertex AI Vector Search (indexes + endpoints) | Managed ANN service | Fully managed | ScaNN-based (Tree-AH) + brute force | TREE_AH (ScaNN), BRUTE_FORCE; shard size; approximateNeighborsCount, leafNodesToSearchPercent | Token restricts (namespace allow/deny lists) + numeric restricts applied during search | Hybrid dense + sparse vectors in one index; you supply sparse (e.g. BM25/SPLADE) vectors | Batch rebuild or streaming upserts/removes (streaming has freshness lag - measure) | Autoscaling replicas on deployed endpoints; private endpoints / PSC | Rebuild from source of truth (GCS) | Via restricts or separate indexes | IAM on index/endpoint; no row-level ACL concept | GOOD if ACL principals are encoded as restrict tokens (allow + deny namespaces); group expansion & token count per datapoint limits must be verified | Regional | Very low latency at large scale; endpoint is always-on (cost floor) | Medium | Node-hours for deployed endpoints + build/update GiB - pricing page | Medium (index format proprietary; vectors portable) | Large-scale, low-latency dense/hybrid ANN | https://cloud.google.com/vertex-ai/docs/vector-search/filtering | Documented - re-verify before use | P1 | 2026-10-26
VDB-03 | Vertex AI Vector Search 2.0 (collections) | Managed vector DB (newer generation) | Fully managed | Google ScaNN family | To Verify (managed indexes; auto-embedding generation) | Data objects with metadata - To Verify filter semantics | To Verify | CRUD on data objects - To Verify | Managed | To Verify | To Verify | IAM | To Verify - evaluate once filter semantics confirmed | To Verify | To Verify | Low-Medium | To Verify | Medium-High | Simpler managed custom RAG if GA and filters meet ACL needs | https://docs.cloud.google.com/vertex-ai/docs/vector-search-2/embeddings/autogenerating-embeddings | Preview/Experimental - re-verify | P2 - verify GA status first | 2026-10-26
VDB-04 | BigQuery vector search | Analytical warehouse with vector functions | Fully managed (serverless) | BigQuery engine | VECTOR_SEARCH with brute force or CREATE VECTOR INDEX (IVF, TREE_AH) | SQL WHERE pre-filter on stored columns of the indexed table (check pre- vs post-filter semantics) | SEARCH() text index + VECTOR_SEARCH combined in SQL; you build fusion | DML; index refreshes asynchronously | Serverless | Time travel + snapshots | Datasets / row-level security / authorized views | IAM, row-level access policies, column policy tags | MEDIUM: SQL join to ACL table is expressive; query latency is seconds-class - better for batch eval / offline than interactive | Dataset location | Seconds-class latency; slot consumption per query | Low | On-demand bytes scanned or slot reservations; storage - pricing page | Medium | Offline evaluation, ground-truth exact search, analytics, BigQuery-sourced content (FR-CON-04) | https://cloud.google.com/bigquery/docs/vector-search-intro | Documented - re-verify before use | P2 - eval/ground-truth + BigQuery source | 2026-10-26
VDB-05 | AlloyDB for PostgreSQL (pgvector + ScaNN index) | Managed PostgreSQL with vector extensions | Fully managed | PostgreSQL + pgvector + alloydb_scann | HNSW, IVFFlat (pgvector); ScaNN index (alloydb_scann); exact scan | Full SQL WHERE, joins to ACL tables; filtered vector search (inline filtering - verify) | PostgreSQL full-text (tsvector) + vector in one SQL; RRF in SQL | Transactional insert/update/delete; index maintenance online | Primary + read pools; HA; cross-region replicas | Automated backups, PITR | Schemas / RLS | IAM DB auth, PostgreSQL roles, Row-Level Security | STRONG: transactional ACL tables, RLS, joins to principal sets, consistent deletes; best fit for complex normalised ACL model | Regional | Low-ms latency at millions of vectors; memory sizing matters for HNSW | Medium | vCPU/memory hours + storage - pricing page | Low-Medium (PostgreSQL-compatible) | Custom RAG with ACL policy co-located with vectors | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Documented - re-verify before use | P1 | 2026-10-26
VDB-06 | Cloud SQL for PostgreSQL + pgvector | Managed PostgreSQL | Fully managed | PostgreSQL + pgvector | HNSW, IVFFlat; exact | Full SQL; iterative index scans in pgvector >= 0.8 reduce over-filtering (verify version on Cloud SQL) | PostgreSQL FTS + vector | Transactional | HA (regional), read replicas | Backups, PITR | Schemas / RLS | IAM DB auth, roles, RLS | STRONG (same reasoning as AlloyDB) at smaller scale | Regional | Good to low millions of vectors; vertical scaling | Medium | Instance hours + storage - pricing page | Low | Smaller corpora; teams already on Cloud SQL (FR-CON-03) | https://cloud.google.com/sql/docs/postgres/work-with-vectors | Documented - re-verify before use | P2 | 2026-10-26
VDB-07 | Spanner (vector search) | Globally distributed SQL | Fully managed | Spanner | Exact KNN distance functions; ANN vector indexes (ScaNN-based) | SQL filters (ANN + filter semantics - verify) | Spanner full-text search + vector | Transactional | Horizontal, multi-region | Backups, PITR | Databases / fine-grained access control | IAM, fine-grained access control | GOOD for scale + transactional ACLs; higher cost floor | Regional / multi-region | Scales horizontally | Medium | Compute capacity (PU/nodes) + storage | Medium | Very large, globally distributed, transactional workloads | https://cloud.google.com/spanner/docs/find-approximate-nearest-neighbors | Documented - re-verify before use | P4 | 2026-10-26
VDB-08 | Firestore vector search | Document DB with KNN | Fully managed | Firestore | Flat KNN vector index | Pre-filter with equality filters + composite index | No native BM25 | Document writes | Serverless | Managed backups/PITR | Collections | IAM / Security Rules | WEAK at scale: limits on results/dims - small corpora only | Location | Limited result count and dims - verify | Low | Reads/writes/storage | Medium | Small app-local knowledge, not enterprise corpus | https://cloud.google.com/firestore/docs/vector-search | Documented - re-verify before use | Not shortlisted | 2026-10-26
VDB-09 | Memorystore (Valkey / Redis) vector search | In-memory store | Fully managed | Valkey/Redis search module | HNSW, FLAT | Tag/numeric filters | Text search features - verify | Real-time | Cluster | Snapshots (verify) | Key prefixes | IAM + AUTH | Use for SEMANTIC CACHE keyed by permission-set hash, not as system of record | Regional | Sub-ms; memory-bound capacity | Medium | Node capacity hours | Low | Semantic/answer cache, session memory | https://cloud.google.com/memorystore/docs/valkey/about-vector-search | To Verify | P3 - cache only | 2026-10-26
VDB-10 | Vertex AI RAG Engine (RagManagedDb or BYO vector DB) | Managed RAG orchestration layer | Managed | RagManagedDb (Spanner-backed - To Verify) or Vector Search / third-party backends | KNN or ANN depending on backend | Metadata filter support - To Verify | Backend dependent | Corpus file import/delete APIs | Managed | Re-import | Corpora | IAM on corpus | WEAK-TO-VERIFY: no documented per-user document ACL model comparable to Vertex AI Search - must verify before any production consideration | Regional | Managed | Low | Per backend + embedding + parsing usage | High | Rapid prototype of custom-chunking pipeline | https://cloud.google.com/vertex-ai/generative-ai/docs/rag-engine/rag-overview | Documented - re-verify before use | P3 - prototype only unless ACL verified | 2026-10-26
VDB-11 | Elasticsearch (Elastic Cloud on GCP Marketplace or ECK on GKE) | Search engine (BM25 + vector) | Managed (Elastic Cloud) or self-managed | Lucene | HNSW (Lucene), int8/bbq quantisation, exact | Rich filters; filter applied during kNN | Native BM25 + kNN + RRF retriever; ELSER sparse | Near-real-time refresh; deletes via tombstones/merge | Sharding, replicas | Snapshots to GCS | Index-per-tenant or filtered aliases | Native Document-Level Security (DLS) + field-level security (licensed tier) | STRONG: DLS role queries can enforce ACL terms server-side; licensing tier must be confirmed | Deployment region | Mature at billions of docs; JVM tuning | Medium-High | Elastic subscription or self-managed compute | Medium | Hybrid-first architecture with strong keyword needs (acronyms, IDs) | https://www.elastic.co/guide/en/elasticsearch/reference/current/document-level-security.html | OSS/Third-party - verify licence & version | P2 | 2026-10-26
VDB-12 | OpenSearch (self-managed on GKE) | Search engine (BM25 + vector) | Self-managed | Lucene + k-NN plugin (Lucene / FAISS / nmslib engines) | HNSW, IVF, PQ (FAISS engine) | Efficient filtering (Lucene engine) | BM25 + neural/hybrid query with normalisation processor | NRT refresh | Sharding, replicas | Snapshots to GCS | Indices / tenants | Security plugin with DLS | STRONG technically; you operate the security plugin | Your region | Mature; ops heavy | High | GKE compute + storage | Low (Apache-2.0) | Teams preferring OSS Elastic-compatible stack | https://opensearch.org/docs/latest/search-plugins/knn/index/ | OSS/Third-party - verify licence & version | P3 | 2026-10-26
VDB-13 | Qdrant (self-managed on GKE or Qdrant Cloud on GCP) | Vector database | Both | Qdrant (Rust) | HNSW; scalar/binary/product quantisation; exact | Payload filters integrated into HNSW traversal (filterable HNSW); payload indexes | Sparse vectors + dense; server-side fusion (RRF/DBSF) via Query API | Real-time upsert/delete | Sharding, replication | Snapshots | Payload-based multitenancy (is_tenant) or collections | API keys / JWT RBAC (verify edition) | GOOD: principal ids as indexed keyword payload with 'should match any' filter; deny list via must_not | Your region | High QPS with filters; RAM sizing for HNSW | Medium (self-managed) | Compute or Qdrant Cloud pricing | Low (Apache-2.0) | OSS hybrid vector DB with strong filtered search | https://qdrant.tech/documentation/ | OSS/Third-party - verify licence & version | P2 | 2026-10-26
VDB-14 | Weaviate (self-managed or Weaviate Cloud) | Vector database | Both | Weaviate (Go) | HNSW, flat, dynamic; PQ/BQ/SQ compression | Pre-filtering with inverted index | Native BM25F + vector hybrid with fusion | Real-time CRUD | Sharding, replication | Backups to GCS module | Native multi-tenancy | RBAC (recent versions - verify) | GOOD: filter on principal arrays; verify performance with large IN-lists | Your region | Good to large scale | Medium | Compute or Weaviate Cloud | Low (BSD-3) | Built-in hybrid with less tuning effort | https://weaviate.io/developers/weaviate | OSS/Third-party - verify licence & version | P3 | 2026-10-26
VDB-15 | Milvus (self-managed on GKE or Zilliz Cloud) | Vector database | Both | Milvus (Knowhere: FAISS/HNSW/DiskANN/cuVS) | HNSW, IVF_FLAT, IVF_PQ, IVF_SQ8, DiskANN, GPU CAGRA, SCANN | Scalar filtering; partition key | Sparse vectors + BM25 function (2.5+) + hybrid search | Upsert/delete with compaction | Distributed, cloud-native | Backup tool to object storage | Partition key / databases | RBAC | GOOD: array/tag filters; many components to operate | Your region | Billion-scale capable | High | Compute + object storage, or Zilliz pricing | Low (Apache-2.0) | Very large corpora; index-type experimentation | https://milvus.io/docs | OSS/Third-party - verify licence & version | P3 | 2026-10-26
VDB-16 | FAISS (library) | ANN library (not a database) | In-process library | FAISS | Flat, IVF, IVF-PQ, HNSW, OPQ, GPU indexes | ID-selector during search; no metadata store | None | Add/remove by ID (index dependent); no durability | You build it | You build it | None | None | UNSUITABLE ALONE: no persistence, no ACL model; usable for offline ANN benchmarking / ground truth | n/a | Fastest for benchmarking | High if used in prod | Compute only | None | ANN experiments, exact ground truth | https://github.com/facebookresearch/faiss | OSS/Third-party - verify licence & version | P1 - benchmarking tool only | 2026-10-26
VDB-17 | hnswlib / ScaNN (libraries) | ANN libraries | In-process library | hnswlib; Google ScaNN | HNSW (hnswlib); ScaNN (partitioning + anisotropic quantisation + reordering) | Limited / none | None | hnswlib supports mark-delete | You build it | You build it | None | None | UNSUITABLE ALONE (same as FAISS) | n/a | Benchmarking | High if prod | Compute | None | Algorithm-level experiments | https://github.com/nmslib/hnswlib | OSS/Third-party - verify licence & version | P3 - benchmarking only | 2026-10-26

## 08_ANN_Algorithms
ANN algorithms & index optimisation
Algo ID | Algorithm / index type | Core principle | Available in (shortlisted platforms) | Index build complexity | Query latency considerations | Recall trade-off | Memory footprint | Disk footprint | Update behaviour | Filtering considerations | Large-dataset suitability | Main tunable parameters | Operational complexity | Limitations | POC experiment | Reference
ANN-01 | Exact / brute-force (flat) KNN | Compute distance to every vector | All (FAISS IndexFlat, pgvector no-index scan, BigQuery brute force, Vector Search BRUTE_FORCE) | None | Linear in N; fine < ~100k vectors or with highly selective filters | 100% (ground truth) | N x d x bytes | Same | Trivial | Pre-filter is exact and simple | Poor beyond millions for online use | None | Low | Cost/latency at scale | Generate ground truth for Recall@K of every ANN config (AX-01) | n/a
ANN-02 | HNSW | Multi-layer proximity graph; greedy search from top layer | pgvector, AlloyDB, Cloud SQL, Qdrant, Weaviate, Milvus, Elastic/OpenSearch, FAISS, hnswlib | O(N log N); slow-ish builds; memory hungry | Very low latency; ef_search trades latency for recall | High (0.95-0.99 typical when tuned - measure) | High (vectors + graph links ~ M x 2 x 4 bytes per node) | Persisted by DB | Incremental inserts OK; deletes leave tombstones / degrade | Restrictive filters can break graph connectivity -> low recall; use in-graph filtering (Qdrant), iterative scans (pgvector 0.8+) or exact fallback | Good to hundreds of millions with RAM | M, ef_construction, ef_search | Medium | RAM cost; filter-recall cliff | AX-03/04: sweep M {16,32}, ef_construction {64,200}, ef_search {40,100,200} | arXiv:1603.09320
ANN-03 | IVF-Flat | k-means partitions (lists); probe nearest lists, exact within | pgvector IVFFlat, Milvus, FAISS, BigQuery IVF, OpenSearch | Needs training (k-means) on representative sample | Linear in probes x list size | Depends on probes; drops if data drifts from centroids | Low (vectors + centroids) | Same | Inserts go to nearest list; periodic retrain/rebuild needed as corpus evolves | Post-filtering within lists can under-fill results | Good; rebuild cost grows | lists (nlist), probes (nprobe) | Medium | Build before data loaded = poor centroids | AX-05: nlist ~ sqrt(N) .. 4 sqrt(N); probes sweep | Jegou et al. 2011 (PQ/IVF)
ANN-04 | IVF-PQ | IVF + product quantisation of residuals (compressed codes) | FAISS, Milvus, OpenSearch (FAISS engine) | Training of centroids + codebooks | Very fast, small memory | Lower recall; usually needs exact re-rank of top candidates | Very low (m bytes per vector) | Low | Retrain for drift | As IVF | Excellent for billion scale | nlist, nprobe, m (sub-quantisers), nbits | High | Quality loss; tuning-heavy | AX-06 only if memory cost becomes the constraint | Jegou et al. IEEE TPAMI 2011
ANN-05 | Scalar / binary quantisation (SQ8, int8, BQ) | Reduce precision per dimension; rescore with full vectors | Qdrant, Weaviate, Milvus, Elastic (int8/bbq), pgvector halfvec/bit | Cheap | Faster, less RAM | Small loss for SQ8; larger for binary unless rescored with oversampling | 4x (int8) to 32x (binary) reduction | Full vectors often kept on disk for rescoring | Same as base index | As base index | Excellent cost lever | quantisation type, oversampling, rescore on/off | Low-Medium | Binary needs high-dim models to work well | AX-07: float32 vs int8 vs binary+rescore on same HNSW | Vendor docs
ANN-06 | ScaNN (Tree-AH / anisotropic VQ) | Partition tree + anisotropic vector quantisation + exact reordering | Vertex AI Vector Search (TREE_AH), AlloyDB alloydb_scann, BigQuery TREE_AH, Spanner ANN, ScaNN library | Partition training; managed in GCP products | Very low latency at scale | High with reordering | Compressed | Managed | Vector Search: streaming updates; AlloyDB: index maintenance - verify rebuild guidance | Vector Search restricts applied in search; AlloyDB filtered ScaNN - verify | Excellent (billions) | leafNodeEmbeddingCount, leafNodesToSearchPercent, approximateNeighborsCount (Vector Search); num_leaves, leaves_to_search (AlloyDB) | Low (managed) - Medium | Fewer knobs exposed; product-specific behaviour | AX-08: leaves_to_search sweep vs exact | arXiv:1908.10396
ANN-07 | DiskANN / Vamana (incl. StreamingDiskANN) | Graph index stored on SSD with compressed vectors in RAM | Milvus DiskANN; pgvectorscale (self-managed Postgres - availability on managed GCP DBs To Verify) | Heavy build | Low-ms with SSD | High | Low RAM | High (SSD) | Streaming variants support updates | Filtered DiskANN variants exist - engine-specific | Excellent for > RAM datasets | R, L_build, L_search, PQ bytes | High | Self-managed only on GCP today (verify) | Only if corpus exceeds RAM budget (AX-09) | Microsoft Research DiskANN (NeurIPS 2019)
ANN-08 | GPU ANN (CAGRA / cuVS, FAISS-GPU) | GPU-built graph / IVF | Milvus GPU indexes, FAISS-GPU | Fast builds on GPU | Very high throughput at batch | High | GPU memory | - | Rebuild-oriented | Limited filtering | For massive batch workloads | graph_degree, itopk | High | GPU cost; ops | Not in initial POC; only for re-index time constraints | NVIDIA cuVS docs
ANN-09 | Matryoshka truncation + two-stage rescoring | Search with short prefix of embedding; rescore with full vector | Any store storing two vectors (gemini-embedding-001 dims, nomic, arctic, Qwen3) | Two indexes or stored full vectors | Faster first stage | Near full-dim recall after rescoring - measure | Reduced | Full vectors stored | Same | Same as base | Good | first-stage dims (256/768), rescore depth | Medium | Only for MRL-trained models | AX-10: 768-dim first stage + 3072 rescore vs 3072 direct | arXiv:2205.13147
ANN-10 | Filtered ANN strategy (pre / in-graph / post) | Where the ACL/metadata predicate is applied relative to ANN | pgvector iterative scan; Qdrant filterable HNSW; Vector Search restricts; Elastic kNN filter | n/a | Post-filter: fast but under-fills k; pre-filter exact: slow for broad sets | Post-filter recall collapses with selective ACLs | n/a | n/a | n/a | SECURITY: post-filter alone means unauthorised chunks are retrieved by the engine - must never leave the trusted retrieval service | Critical at enterprise scale | filter selectivity, oversampling factor, k | Medium | Engine-specific semantics | AX-11: selectivity 50% / 10% / 1% / 0.1% users' visible fraction | Engine docs

## 08a_ANN_Experiments
ANN experiment matrix - Recall@K measured against exact-search ground truth (AX-01)
AX ID | Comparison | Platform(s) | Fixed variables | Factor levels | Corpus sizes | Filter selectivity | Concurrency | Metrics | Notes
AX-01 | Exact vs ANN baseline | FAISS IndexFlat / pgvector exact | Embedding model + dims | Exact only | 100k / 1M | None | 1 | Ground-truth top-100 per query | Ground truth for all other AX runs
AX-02 | HNSW default vs exact | pgvector (AlloyDB) | Vectors | HNSW m=16, ef_construction=64, ef_search=40 | 100k / 1M / 10M | None | 1, 10 | Recall@10/20 vs AX-01, P50/P95, build time, memory | -
AX-03 | HNSW graph params | pgvector, Qdrant | Vectors | m {16, 32} x ef_construction {64, 200} | 1M | None | 1 | Recall, build time, index size | Build-time vs quality
AX-04 | HNSW search breadth | pgvector, Qdrant | Index fixed | ef_search {40, 100, 200, 400} | 1M / 10M | None | 1, 50 | Recall vs P95 curve | Main runtime knob
AX-05 | IVF partitions/probes | pgvector IVFFlat, BigQuery IVF | Vectors | lists ~ sqrt(N) and 4*sqrt(N); probes {1%, 5%, 10% of lists} | 1M / 10M | None | 1 | Recall, P95, build | Requires training on loaded data
AX-06 | IVF-PQ compression | FAISS / Milvus | Vectors | m {16, 32, 64}, nbits 8, with/without re-rank | 10M | None | 1 | Recall, memory | Only if memory-bound
AX-07 | Quantisation | Qdrant SQ8 / BQ; pgvector halfvec | HNSW params | float32 vs int8 vs binary+rescore (oversampling 2-4x) | 1M / 10M | None | 1, 50 | Recall, memory, P95 | -
AX-08 | ScaNN / Tree-AH | AlloyDB alloydb_scann; Vertex Vector Search | Vectors | leaves_to_search / leafNodesToSearchPercent sweep; approximateNeighborsCount | 1M / 10M | None | 1, 50, peak | Recall, P95, cost/hour | Managed vs self-tuned comparison
AX-09 | Disk-based ANN | Milvus DiskANN | Vectors | search_list {50, 100, 200} | 10M+ | None | 1, 50 | Recall, P95, RAM | Only if corpus > RAM budget
AX-10 | Dimension effect on ANN | Any shortlisted | Model | 768 / 1536 / 3072 (MRL two-stage) | 1M | None | 1 | Recall vs own exact GT, memory | Separate from EXP-03 (quality vs labels)
AX-11 | Filter selectivity (ACL) | pgvector (iterative scan), Qdrant, Vector Search restricts, Elastic | Index tuned per platform | visible fraction 50% / 10% / 1% / 0.1% | 1M / 10M | As levels | 1, 50 | Filtered Recall@20 vs filtered exact GT, P95, under-filled result rate | Most important AX for our ACL requirement
AX-12 | Concurrency scaling | Shortlisted platforms | Best config | 1 / 10 / 50 / peak QPS | 10M | Realistic distribution | As levels | P95/P99, error rate, autoscaling time, cost/hour | -

## 08b_Clustering_vs_Index
Clustering vs vector indexing vs nearest-neighbour retrieval vs reranking
Concept ID | Concept | Problem it solves | Typical algorithms | Where it appears in our pipeline | Needed for the initial POC? | Notes
CON-01 | Clustering documents into groups | Discover topics, near-duplicate families, corpus coverage | K-means, HDBSCAN, agglomerative / hierarchical | Corpus analysis; dedup families; golden-set stratification; RAPTOR-style summary trees | Optional: only for dedup analysis (ING-12) and golden-set stratified sampling | Clustering is NOT required for retrieval; do not add it unless a use case is proven
CON-02 | Organising vectors into index structures | Make nearest-neighbour search sub-linear | IVF (uses k-means internally), HNSW graphs, ScaNN trees, PQ codebooks | Inside the vector store | Yes - but managed by the chosen store; tune parameters only | IVF's k-means is an implementation detail of indexing, not document clustering
CON-03 | Retrieving nearest neighbours for a query | Find candidate chunks similar to the query embedding | Exact KNN, ANN (HNSW, ScaNN, IVF) | Retrieval layer (first stage) | Yes | Quality bounded by embedding + chunking, not only by ANN recall
CON-04 | Reranking retrieved candidates | Re-order top-N candidates with a stronger, slower relevance model | Cross-encoders, Vertex Ranking API, LLM rerank, RRF fusion | Second stage after retrieval and AFTER authorisation trimming | Yes (P1 experiment) | Reranker must only receive candidates the user is authorised to see
CON-05 | Near-duplicate detection | Remove repeated content that wastes context and skews ranking | MinHash/LSH, SimHash, embedding cosine threshold | Ingestion (ING-12) and result-level dedup (RRK-09) | Yes - lightweight | Duplicates with DIFFERENT ACLs must not be merged across permission boundaries

## 09_Retrieval
Retrieval strategy catalogue - combine only strategies that fix a measured failure
Retrieval ID | Strategy | Mechanism | Best use case | Data prerequisites | Implementation requirements | Advantages | Limitations | Latency implications | Cost implications | Failure modes | Relevant metrics | Suggested experiment | POC priority
RET-01 | Dense vector retrieval | Embed query; ANN over chunk embeddings | Paraphrased natural-language questions | Chunk embeddings | Embedding model + vector store | Semantic matching | Misses exact IDs, codes, acronyms, rare terms | Low | Query embedding + ANN | Confident wrong matches on jargon; acronyms | Recall@K, NDCG@10 | EXP-01..04 | P1
RET-02 | BM25 / keyword | Inverted index with term weighting | IDs, error codes, KB numbers, product names, acronyms | Tokenised text + field boosts | Search engine or PostgreSQL FTS / BigQuery SEARCH | Precise on exact terms; explainable | Vocabulary mismatch | Very low | Low | Stop-word/stemming issues; language analyzers | Recall@K on keyword subset | EXP-13 | P1
RET-03 | Learned sparse (SPLADE / bge-m3 sparse / ELSER) | Model-expanded sparse term weights | Vocabulary mismatch with exact-term precision | Sparse vectors | Sparse-capable store (Vector Search hybrid, Qdrant, Milvus, Elastic) | Better than BM25 on paraphrase | Model serving; licence of some models | Low-Medium | Model inference | Domain drift | Recall@K | EXP-14 | P3
RET-04 | Hybrid (dense + BM25) with fusion | Run both; fuse via RRF or weighted scores | Enterprise mixed queries (default recommendation to test) | Both indexes, same ACL metadata on both | Two retrievers + fusion | Robust across query types | Two indexes to keep consistent (incl. ACL sync) | Parallel calls - max of both | ~2x retrieval | Weight mis-tuning; ACL drift between indexes | Recall@K, NDCG, per-query-type breakdown | EXP-13 | P1
RET-05 | Metadata-filtered retrieval | Apply filters (source, type, date, app data-set entitlement) with the query | FR-FLT-01..05; app_id data-set scoping (FR-CFG-06) | Clean, typed metadata | Filter translation per store | Precision; compliance with app entitlements | Over-filtering empties results; filter syntax divergence across stores | Depends on selectivity | Low | Wrong field mapping; stale metadata | Filter correctness (M-RQ-08) | EXP-15 | P1
RET-06 | ACL-filtered retrieval (security trimming) | Inject user's effective principal set as a mandatory filter inside the retrieval engine | Mandatory for all queries (FR-SEC-03) | Normalised ACL per chunk; user principal expansion | Trusted identity + principal resolver + engine filter | Enforces access early; keeps counts/relevance correct | Large principal sets; group expansion freshness | Selective filters may slow ANN | Principal resolution calls (cache with TTL) | Stale ACLs; post-filter-only leakage to rerankers/logs | Unauthorised retrieval rate = 0 | EXP-ACL-* | P0 (mandatory)
RET-07 | Query expansion (glossary / synonyms / acronyms) | Expand acronyms and synonyms before retrieval | FR-GLO-02: company glossary | Glossary store scoped global / data set / app_id | Expansion service; keep original + expanded | Fixes jargon misses without re-index | Over-expansion reduces precision; ambiguous acronyms | +ms | Negligible | Wrong sense chosen | Recall on acronym subset; precision delta | EXP-16 | P1
RET-08 | Query rewriting (LLM) | Rewrite conversational / vague query into standalone search query | Multi-turn chat; under-specified questions | Conversation history (user-scoped) | LLM call + prompt | Better recall for follow-ups | Added latency/cost; drift from intent | +LLM call | LLM tokens | Rewrites that add assumptions | Recall@K on conversational subset | EXP-17 | P2
RET-09 | Multi-query retrieval | Generate N query variants; union results | Ambiguous, broad questions | - | LLM + fusion | Recall up | N x retrieval cost; noise | +LLM + parallel retrievals | N x | Duplicate flood | Recall, latency P95 | EXP-18 | P3
RET-10 | HyDE (hypothetical document) | Embed an LLM-drafted answer as the query | Short queries vs long docs | - | LLM | Helps asymmetric matching | Hallucinated content steers retrieval | +LLM | LLM tokens | Bias to model priors | Recall | Only if RET-08 insufficient | P4
RET-11 | Query decomposition | Split complex question into sub-questions; retrieve per sub-question | Comparative / multi-part questions | - | Planner LLM + aggregation | Handles compound questions | Latency; error compounding | High | High | Bad decomposition | Answer completeness | EXP-25 | P3
RET-12 | Multi-hop / iterative retrieval | Retrieve, read, retrieve again using found entities | Questions needing chained facts | - | Agent loop with stop criteria | Answers chained questions | Unbounded loops; latency | High | High | Loop drift | Multi-hop accuracy subset | EXP-26 | P4
RET-13 | Parent-child retrieval | Match small child chunks, return parent context | Long structured docs | CHK-10 structure | Parent lookup (ACL re-checked on parent) | Precision + completeness | Context bloat | Low | Low | Parent of different ACL scope (must be same document) | Completeness, context precision | EXP-08 | P1
RET-14 | Hierarchical / coarse-to-fine | Retrieve docs/sections by summary, then chunks within | Large libraries; overview questions | CHK-11/12 | Two-stage retrieval | Scales routing | Summary errors cascade | Medium | Summary generation | Wrong doc chosen | Recall@doc | EXP-27 | P3
RET-15 | Contextual retrieval | Embed and BM25-index chunks with LLM-generated context prefix | Terse chunks | CHK-16 | Ingestion LLM pass | Recall gains reported in literature | Ingestion cost; re-index on prompt change | None at query | Ingestion | Context hallucination | Recall@K | ADV-01 / EXP-20 | P2
RET-16 | Agentic retrieval (ADK tool-driven) | Agent chooses tools/filters/sources and iterates | Multi-source, tool-rich questions | Tool descriptions; user identity in tool context | ADK agent + RAG tools | Flexible | Non-deterministic; harder to evaluate; identity propagation risk | High / variable | High | Agent leaks restricted data across A2A hops | Task success, tool-call correctness | EXP-28 | P3
RET-17 | Graph-based retrieval (GraphRAG / KG) | Entity-relation graph traversal + community summaries | Relationship questions across docs | Entity extraction, graph store | Graph pipeline (Spanner Graph / Neo4j / BigQuery) | Answers relationship / global questions | High build cost; ACL per node/edge is hard | Medium-High | High ingestion | Summaries mixing restricted sources = leakage | Multi-hop accuracy | Only if relationship questions are a proven gap | P4

## 10_Reranking
Reranking & relevance optimisation (rerank only authorised candidates)
Rerank ID | Approach | Model / mechanism | Deployment | Candidate depth (start) | Latency considerations | Cost basis | Expected benefit (hypothesis) | Authorisation boundary | Evaluation method | Limitations | Documentation | Verification status | POC priority
RRK-01 | Vertex AI Ranking API (managed cross-encoder) | semantic-ranker-default-004 (accuracy) / semantic-ranker-fast-004 (latency); pin versions | Managed (Discovery Engine RankService; discoveryengine.googleapis.com) | Top 20-50 | Google states low latency; measure P95 in region | Per 1k ranking requests/records - pricing page | NDCG@10 uplift over first stage | Send only authorised candidates; content leaves the RAG service to Google API (same trust boundary as Gemini) | NDCG@10, MRR before/after; latency delta | Max records/tokens per request; region availability | https://cloud.google.com/generative-ai-app-builder/docs/ranking | Verified (web check 2026-10-26) | P1
RRK-02 | Open-source cross-encoder | BAAI/bge-reranker-v2-m3 (Apache-2.0, multilingual) | Self-host GPU (Cloud Run GPU / GKE) | Top 20-50 | ~linear in candidates; GPU needed for P95 | Compute | Comparable to managed - measure | Runs inside VPC | Same | Serving ops | https://huggingface.co/BAAI/bge-reranker-v2-m3 | OSS/Third-party - verify licence & version | P2
RRK-03 | LLM-based reranker | Qwen3-Reranker (Apache-2.0) / mxbai-rerank-v2 (verify licence) | Self-host GPU | Top 20-50 | Larger models slower | Compute | Potential quality ceiling | Inside VPC | Same | Heavier serving | https://huggingface.co/Qwen/Qwen3-Reranker-0.6B | OSS/Third-party - verify licence & version | P3
RRK-04 | Lightweight cross-encoder | cross-encoder/ms-marco-MiniLM-L-6-v2 | Self-host CPU | Top 20-100 | Fast on CPU | Compute | Cheap floor baseline | Inside VPC | Same | English; MS MARCO domain | https://huggingface.co/cross-encoder/ms-marco-MiniLM-L-6-v2 | OSS/Third-party - verify licence & version | P3
RRK-05 | Gemini listwise / pointwise rerank | Gemini Flash prompted to score/sort candidates | Managed | Top 10-30 | Slowest; token heavy | Input+output tokens | Handles nuance; can also judge sufficiency | Same as generation boundary | Same + cost per query | Position bias; non-determinism; cost | https://cloud.google.com/vertex-ai/generative-ai/docs/models | Proposed pattern - validate in POC | P3
RRK-06 | Third-party rerank API | Cohere Rerank 3.5 / Voyage rerank | Third-party API (Cohere via Vertex Model Garden - To Verify) | Top 20-50 | Network hop | Per search unit | Reference quality | Data leaves GCP unless Model Garden-hosted | Same | DPA / egress | https://docs.cohere.com/docs/rerank | To Verify | P4
RRK-07 | Reciprocal Rank Fusion (RRF) | score = sum 1/(k + rank_i), k typically 60 | In code / engine (Elastic, Qdrant, Weaviate, SQL) | All candidates from each retriever | Negligible | None | Robust hybrid fusion without score calibration | n/a | Recall/NDCG vs weighted | Ignores score magnitude | https://dl.acm.org/doi/10.1145/1571941.1572114 | Documented - re-verify before use | P1
RRK-08 | Weighted score combination | alpha * norm(dense) + (1-alpha) * norm(sparse) | In code / engine | All | Negligible | None | Better than RRF when calibrated | n/a | alpha sweep 0.3-0.8 | Needs score normalisation; drift with model change | Engine docs | Proposed pattern - validate in POC | P2
RRK-09 | Duplicate / near-duplicate suppression | Collapse same doc_id or cosine > threshold | In code | Final list | Negligible | None | More diverse context; fewer wasted tokens | Never merge duplicates across different ACL sets | Context precision; unique-doc ratio | Over-suppression of legit variants | - | Proposed pattern - validate in POC | P1
RRK-10 | Maximal Marginal Relevance (MMR) | Trade relevance vs novelty (lambda) | In code / LangChain / LlamaIndex | Top 20-50 -> 5-10 | Small | None | Diversity for broad questions | n/a | lambda sweep; completeness | Can drop the single best evidence | https://dl.acm.org/doi/10.1145/290941.291025 | Documented - re-verify before use | P3
RRK-11 | ColBERT late-interaction rerank | MaxSim over token vectors (EMB-20) | Self-host | Top 50-100 | Moderate | Compute + storage | High precision | Inside VPC | Same | Ops + storage | arXiv:2004.12832 | OSS/Third-party - verify licence & version | P4
RRK-12 | Metadata/business boosting | Boost recency, authoritative sources, published KB state | In code / engine | All | Negligible | None | Aligns with FR-FLT-04 defaults | n/a | Ablation | Over-boost stale-but-authoritative | - | Proposed pattern - validate in POC | P2

## 11_Advanced_RAG
Advanced RAG - 'Broadly applicable' vs 'Problem-triggered' (test only after baseline shows the problem)
Tech ID | Technique | Tier | What it does | Problem solved | When to use | When NOT to use | Architecture dependencies | Data preparation | Implementation complexity | Cost / latency implications | Evaluation metrics | POC priority | Reference
ADV-01 | Contextual chunking / contextual retrieval | Problem-triggered | LLM writes a short context prefix per chunk before embedding and BM25 indexing | Ambiguous chunks lose document context | Baseline shows chunks retrieved without enough context | Chunks already carry heading path and title | Ingestion LLM; re-index on prompt change | Doc + chunk to LLM | Medium | Ingestion cost per chunk; none at query | Recall@20, NDCG | P2 | https://www.anthropic.com/news/contextual-retrieval
ADV-02 | Parent-child retrieval | Broadly applicable | Retrieve small chunks, return parent | Precision vs completeness tension | Long structured documents | Short KB articles (whole article fits) | Parent store; ACL identical per document | CHK-10 | Low-Medium | Larger prompts | Completeness, context precision | P1 | LlamaIndex AutoMergingRetriever
ADV-03 | Hybrid search | Broadly applicable | Dense + keyword fusion | Jargon, IDs, acronyms | Always test | - | Two indexes or hybrid-capable store | Analyzers | Medium | ~2x retrieval | Recall per query type | P1 | RRF paper
ADV-04 | Reranking | Broadly applicable | Second-stage relevance model | First-stage ordering noise | Always test | Tiny corpora where exact search + LLM suffices | Reranker service | - | Low-Medium | +latency per candidate | NDCG@10, MRR | P1 | RRK sheet
ADV-05 | Hierarchical indexes / summaries (RAPTOR-style) | Problem-triggered | Tree of cluster/section summaries | Broad, overview questions | Overview questions fail on baseline | Fact lookup workloads | Summary pipeline; ACL: summary must not mix documents with different ACLs | Summarisation | High | Ingestion LLM | Answer completeness on overview subset | P3 | arXiv:2401.18059
ADV-06 | Query decomposition | Problem-triggered | Split into sub-questions | Compound questions | Compound subset fails | Simple lookups | Planner (ADK agent) | - | Medium | +LLM calls | Completeness | P3 | -
ADV-07 | Query rewriting | Broadly applicable for chat | Standalone query from conversation | Follow-up questions | Multi-turn UX | Single-shot API calls | LLM; user-scoped memory | - | Low | +1 LLM call | Recall on conversational subset | P2 | -
ADV-08 | Multi-query retrieval | Problem-triggered | Multiple paraphrases, fused | Recall gaps on vague queries | Recall@K low on vague subset | Latency-critical paths | Fusion | - | Low | N x retrieval | Recall, P95 | P3 | -
ADV-09 | Metadata-aware / self-query retrieval | Broadly applicable (constrained) | LLM extracts structured filters from NL query (e.g. 'last month', 'in ServiceNow') | Users express filters in words | Filter-heavy queries | When UI already passes filters | Filter schema discovery (FR-FLT-03) | Typed metadata | Medium | +LLM call | Filter correctness | P2 | -
ADV-10 | Corrective RAG (CRAG) | Problem-triggered | Grade retrieved docs; re-retrieve or abstain if weak | Low-quality retrieval passes through | Insufficient-evidence rate high | Strong baseline retrieval | Grader model | - | Medium | +grader call | Unsupported-claim rate, abstention | P3 | arXiv:2401.15884
ADV-11 | Adaptive retrieval (retrieve-or-not / Self-RAG style) | Problem-triggered | Decide whether retrieval is needed | Unneeded retrieval on chit-chat | Mixed traffic | Pure knowledge-QA API | Router | - | Medium | Saves cost on non-KB queries | Routing accuracy | P4 | arXiv:2310.11511
ADV-12 | Iterative retrieval | Problem-triggered | Loop retrieve-read-retrieve | Chained facts | Multi-hop subset fails | Simple lookups | Agent loop with budget | - | High | Variable | Multi-hop accuracy | P4 | -
ADV-13 | GraphRAG | Problem-triggered | Entity graph + community summaries | Global / relationship questions | Proven relationship query needs | ACL-heterogeneous corpora (summaries cross ACL boundaries) | Graph store; per-node ACL | Entity extraction | Very high | High ingestion | Multi-hop, global question accuracy | P4 | arXiv:2404.16130
ADV-14 | Knowledge graph + entity linking | Problem-triggered | Link mentions to canonical entities (products, systems) | Ambiguous names, acronyms | Glossary alone insufficient | Small vocab | KG store; glossary (FR-GLO) | Entity dictionary | High | Medium | Disambiguation accuracy | P4 | -
ADV-15 | Multi-hop reasoning | Problem-triggered | Reason across multiple documents | Questions spanning sources | Proven need | - | Agent orchestration | - | High | High | Multi-hop accuracy | P4 | -
ADV-16 | Late-interaction retrieval (ColBERT) | Problem-triggered | Token-level MaxSim | Precision ceiling | Reranker alone insufficient | Storage-constrained | Multivector store | - | High | Storage heavy | NDCG | P4 | arXiv:2112.01488
ADV-17 | Multimodal RAG | Problem-triggered | Retrieve images/diagrams/scans | Facts in images | Visual content significant (AQ) | Text-only corpora | Multimodal embeddings / Gemini parsing | Image extraction | High | Higher | Recall on visual subset | P3 | EMB-02/05
ADV-18 | Table / structured-data retrieval (text-to-SQL) | Problem-triggered | Query structured sources directly (BigQuery / Cloud SQL) | Numeric / aggregate questions | FR-CON-03/04 structured sources in scope | Prose-only content | SQL tools with row-level security as end user | Schema docs | High | Medium | Execution accuracy | P3 | -
ADV-19 | Citation and provenance enforcement | Broadly applicable (MUST) | Every claim linked to returned source with deep link | FR-RET-02 | Always | - | Chunk -> doc -> source_url mapping; ACL check on cited docs | Stable IDs | Medium | Small | Citation correctness, coverage | P1 | -
ADV-20 | Grounded answer generation + check grounding | Broadly applicable | Constrain to context; optional Check Grounding API scoring | Hallucination | Always | - | Gemini; Check Grounding API (Discovery Engine) | - | Low-Medium | +1 call if used | Faithfulness, unsupported-claim rate | P1 | https://cloud.google.com/generative-ai-app-builder/docs/check-grounding
ADV-21 | Context compression | Problem-triggered | Remove irrelevant sentences before generation | Token cost / lost-in-the-middle | Long contexts degrade answers | Short contexts | Compressor model | - | Medium | Saves generation tokens | Faithfulness, cost/query | P3 | arXiv:2307.03172
ADV-22 | Long-context generation | Broadly applicable lever | Send more/larger context to long-context Gemini | Fragmented evidence | Parent-child insufficient | Cost-sensitive high QPS | Gemini context window | - | Low | Token cost grows linearly | Answer quality vs cost curve | P2 | Gemini model docs
ADV-23 | Caching (exact) | Broadly applicable | Cache embeddings of queries, retrieval results, answers | Cost, latency | Repeated queries | - | Cache key MUST include principal-set hash + acl_version + index version | - | Low | Saves cost | Hit rate; zero cross-user leakage | P2 | FR-SEC-05
ADV-24 | Semantic caching | Problem-triggered | Reuse answers for semantically similar queries | Cost at high QPS | High repeat-intent traffic | Personalised / permission-diverse users | Vector cache keyed by permission set | - | Medium | Saves generation | Hit precision; leakage tests | P3 | VDB-09
ADV-25 | Query routing | Problem-triggered | Route to data set / index / tool by intent | Multi-index architectures | Multiple indexes per type | Single index | Router (rules or classifier) | Labelled routing set | Medium | Small | Routing accuracy | P3 | -
ADV-26 | Confidence estimation | Broadly applicable | Score answer support from retrieval + grounding signals | Need for 'no-answer' flag (FR-API-07) | Always | - | Grounding scores, reranker scores | Calibration set | Medium | Small | Calibration error; abstention precision | P2 | -
ADV-27 | Abstention when evidence is insufficient | Broadly applicable (MUST) | Refuse/flag when context does not support answer | FR-RET-03 | Always | - | Prompt + threshold + grounding | Unanswerable test queries | Low | None | Correct abstention rate | P1 | -
ADV-28 | Prompt-injection defence for retrieved content | Broadly applicable (MUST) | Treat retrieved text as data; delimiters; Model Armor / safety filters; tool-call allow-lists | FR-RET-04 | Always | - | Content safety service; agent tool policies | Injection test corpus | Medium | Small | Injection success rate | P1 | https://cloud.google.com/security-command-center/docs/model-armor-overview
ADV-29 | Glossary-aware answering | Broadly applicable for this org | Add relevant glossary definitions to prompt | FR-GLO-04 | Glossary exists | - | Glossary service | Glossary curation | Low | Small tokens | Answer correctness on jargon subset | P2 | -
ADV-30 | Evaluation harness / regression gate | Broadly applicable (MUST) | Golden sets per app_id; automated runs before any change | FR-RET-05 | Always | - | Eval pipeline (Vertex Gen AI Eval / RAGAS / custom) | Golden sets | Medium | Eval cost | All metrics | P0 | https://cloud.google.com/vertex-ai/generative-ai/docs/models/evaluation-overview
ADV-31 | User feedback loop | Broadly applicable | Thumbs/comments against request ID feed eval sets | FR-RET-06 | Production | - | Feedback API + store | - | Low | None | Feedback-labelled precision | P2 | -

## 12_GCP_Access_Checklist
Access, IAM & infrastructure checklist (GCP separated from SharePoint/Entra and ServiceNow)
Checklist ID | Domain | Requirement | Why needed | Mandatory / conditional | Applicable architecture | Responsible team | Required access / permission | Suggested IAM role (verified role name; confirm scope) | Scope | Required configuration | Verification steps | Dependency | Status | Blocker severity | Notes
GCP-01 | GCP | Dedicated POC project (or folder) | Isolate POC billing, IAM, quotas | Mandatory | All | Cloud platform | Project creation under agreed folder | roles/resourcemanager.projectCreator (platform team only) | Folder | Labels: cost-center, env=poc | Project visible; org policies inherited | - | Not started | High | Do not run POC in production project
GCP-02 | GCP | Billing account link + budget alerts | Cost control | Mandatory | All | FinOps | Link billing; create budget | roles/billing.user (link); roles/billing.costsManager (budgets) | Billing account | Budget with 50/80/100% alerts; billing export to BigQuery | Alert test email received | GCP-01 | Not started | High | Billing export enables M-CO metrics
GCP-03 | GCP | Enable required APIs | Services unusable otherwise | Mandatory | All | Cloud platform | Enable services | roles/serviceusage.serviceUsageAdmin (platform team) | Project | aiplatform, discoveryengine, storage, run, pubsub, cloudscheduler, secretmanager, cloudkms, artifactregistry, cloudbuild, logging, monitoring, cloudtrace, documentai, dlp, iam, iamcredentials | gcloud services list --enabled | GCP-01 | Not started | High | Add alloydb / sqladmin / bigquery / container / compute / servicenetworking per option
GCP-04 | GCP | Vertex AI access (embeddings, Gemini, Ranking via Discovery Engine) | Core models | Mandatory | All | ML platform | Call models | roles/aiplatform.user (runtime SA) | Project | Region chosen per residency (AQ-13); model availability checked | Test call per model succeeds in chosen region | GCP-03 | Not started | High | Verify model IDs in Model Garden at start
GCP-05 | GCP | Discovery Engine access to current baseline | Baseline measurement (EXP-00) | Mandatory | A-* and all comparisons | App team | Read config; run search/answer as test users | roles/discoveryengine.viewer (read); roles/discoveryengine.user - To Verify exact role for querying | Project / data store | Read access to current app, data stores, serving configs | Export config JSON; run sample query | Existing project owner | Not started | High | Do not modify production data stores
GCP-06 | GCP | Service accounts per workload | Least privilege & audit | Mandatory | Custom options | Cloud platform | Create SAs: sa-ingest, sa-rag-api, sa-eval | roles/iam.serviceAccountAdmin (platform team only) | Project | One SA per workload; no user-managed keys | Policy shows SAs; key creation blocked | GCP-01 | Not started | High | Org policy iam.disableServiceAccountKeyCreation recommended
GCP-07 | GCP | Deployers can act as runtime SAs | CI/CD deploys Cloud Run with SA | Mandatory | Custom options | Cloud platform | actAs on specific SA | roles/iam.serviceAccountUser on the SA resource (not project) | Service account | Grant only on sa-rag-api / sa-ingest | Deploy succeeds | GCP-06 | Not started | Medium | -
GCP-08 | GCP | Cloud Storage buckets (raw / parsed / chunks / eval) | Staging & lineage | Mandatory | Custom options | Data engineering | Create buckets; read/write by ingest SA | roles/storage.objectAdmin for sa-ingest on POC buckets only; roles/storage.objectViewer for sa-eval | Bucket | Uniform bucket-level access; CMEK (GCP-15); retention + lifecycle; public access prevention | gsutil/gcloud storage ls with SA impersonation | GCP-06 | Not started | High | Delete copies when source deleted (EXP-ACL-07)
GCP-09 | GCP | Cloud Run (RAG API) + Cloud Run Jobs (ingestion) | Serverless compute | Conditional | B-*, D-* | Cloud platform | Deploy | roles/run.developer (deployers); roles/run.invoker for callers (ADK agent SA) | Service | Ingress internal / internal-and-cloud-load-balancing; min instances for latency tests | Invoke with ID token | GCP-07 | Not started | Medium | -
GCP-10 | GCP | Pub/Sub + Cloud Scheduler (+ Cloud Tasks) | Fan-out, retries, schedules | Conditional | Custom options | Data engineering | Publish/subscribe | roles/pubsub.publisher, roles/pubsub.subscriber (topic/subscription level) | Topic / subscription | Dead-letter topics; retry policy | Message round-trip test | GCP-06 | Not started | Medium | -
GCP-11 | GCP | AlloyDB cluster (or Cloud SQL for PostgreSQL) | Vector + FTS + ACL store | Conditional | B-01..B-04, B-11, C-07, D-01 | DBA | Create cluster; connect from Cloud Run | roles/alloydb.admin (DBA only); roles/alloydb.client + roles/alloydb.databaseUser for runtime SA (IAM DB auth) | Cluster | Private IP (PSA/PSC); vector + alloydb_scann extensions; RLS; backups | psql via Auth Proxy as SA; CREATE EXTENSION vector | GCP-16 | Not started | High | Cloud SQL equivalents: roles/cloudsql.client, roles/cloudsql.instanceUser
GCP-12 | GCP | Quotas: embeddings, Gemini, Ranking, Document AI, Vector Search | Ingestion throughput & load tests | Mandatory | All | Cloud platform | View/request quotas | roles/servicemanagement.quotaViewer; quota increase via console (platform team) | Project/region | Request increases before EXP-30/33 | Quotas page shows approved values | GCP-04 | Not started | High | gemini-embedding-001 is 1 input/request - plan request-rate quota
GCP-13 | GCP | Vertex AI Vector Search index + endpoint | ANN serving | Conditional | B-05, B-06 | ML platform | Create index/endpoint | roles/aiplatform.user (create/query - verify adequacy) | Project | Private endpoint (PSC); restricts namespaces for ACL tokens | Query endpoint with restrict | GCP-16 | Not started | Medium | Always-on endpoint cost - tear down between runs
GCP-14 | GCP | BigQuery datasets (eval results, billing export, audit, ground truth) | Analytics & offline exact search | Conditional | B-08 + evaluation for all | Data engineering | Create datasets; run jobs | roles/bigquery.dataEditor (dataset), roles/bigquery.jobUser (project) | Dataset | Location = residency region; CMEK | Query runs | GCP-01 | Not started | Medium | -
GCP-15 | GCP | Cloud KMS keys (CMEK) | Encryption policy compliance | Conditional (policy) | All storing data | Security | Use keys | roles/cloudkms.cryptoKeyEncrypterDecrypter for service agents on specific keys | Key | Keys for GCS, AlloyDB, BigQuery, Artifact Registry | Resource shows CMEK | Security decision | Not started | Medium | Confirm if CMEK is mandatory (AQ-16)
GCP-16 | GCP | VPC, Private Service Access/Connect, Serverless VPC access or Direct VPC egress | Private connectivity to DBs and endpoints | Conditional | Custom options | Network | Configure subnets/peering | roles/compute.networkAdmin (network team) | VPC | PSA range for AlloyDB; PSC for Vector Search; Cloud NAT for Graph/ServiceNow egress with static IP | Connectivity test from Cloud Run | - | Not started | High | ServiceNow IP allow-listing may need NAT static IP
GCP-17 | GCP | VPC Service Controls perimeter | Exfiltration protection for Vertex/BigQuery/GCS | Conditional (policy) | All | Security | Add project to perimeter | Access Context Manager admin (security team) | Organisation | Include aiplatform, discoveryengine, storage, bigquery, alloydb; ingress/egress rules for CI and Graph/ServiceNow egress | Dry-run mode logs reviewed | GCP-16 | Not started | Medium | Test in dry-run first
GCP-18 | GCP | Org policies review | Policies may block resources (regions, external IPs, SA keys) | Mandatory | All | Security | Read policies | roles/orgpolicy.policyViewer | Org / folder | gcp.resourceLocations aligned with residency | List effective policies | - | Not started | Medium | -
GCP-19 | GCP | Secret Manager | Store Graph cert / ServiceNow OAuth secrets | Mandatory | Custom options | Security | Create secrets; access by ingest SA | roles/secretmanager.secretAccessor on specific secrets | Secret | Rotation schedule; CMEK optional | SA can read only its secrets | GCP-06 | Not started | High | FR-CON-08
GCP-20 | GCP | Cloud Logging / Monitoring / Trace | Observability + audit | Mandatory | All | SRE | Write logs/metrics/traces | roles/logging.logWriter, roles/monitoring.metricWriter, roles/cloudtrace.agent (runtime SAs) | Project | Log buckets with restricted access for any content-bearing logs; exclusion filters; Data Access audit logs on | Spans visible; no content in logs (EXP-ACL-15) | - | Not started | High | FR-SEC-07/08
GCP-21 | GCP | Artifact Registry + Cloud Build (or existing CI/CD) | Build and store images | Mandatory | Custom options | DevOps | Push/pull images | roles/artifactregistry.writer (CI SA), roles/artifactregistry.reader (runtime) | Repository | Vulnerability scanning on | Image push/pull | - | Not started | Medium | -
GCP-22 | GCP | Document AI processors (Layout Parser, OCR) | Parsing experiments | Conditional | B-*, C-*, D-* | ML platform | Create processors; process documents | roles/documentai.apiUser (runtime); roles/documentai.editor (setup) - verify | Processor | Processor region matches residency (us/eu) | Test document processed | GCP-03 | Not started | Medium | -
GCP-23 | GCP | Sensitive Data Protection (DLP) | PII handling (FR-SEC-08) | Conditional (policy) | All custom | Security | Inspect/de-identify | roles/dlp.user | Project | InfoType templates per data-set policy | Inspect sample | - | Not started | Medium | -
GCP-24 | GCP | GKE cluster (+ GPU node pool) | OSS stores / self-hosted models | Conditional | C-*, E-*, B-06, B-11 (alt Cloud Run GPU) | Platform | Create cluster | roles/container.admin (platform team); workload identity for pods | Cluster | Private cluster; Workload Identity; GPU quota | kubectl access via IAP | GCP-16, GPU quota | Not started | Medium | Cloud Run GPU may avoid GKE for model serving
GCP-25 | GCP | Workforce Identity Federation (Entra ID) - current baseline config | Managed ACL identity mapping | Mandatory (baseline) | A-*, D-01, D-02 | Identity | Read WIF pool/provider config | roles/iam.workforcePoolViewer (org) | Organisation | Attribute mapping google.subject = email; groups mapping | Document mapping; test user search | - | Not started | High | ID-04
GCP-26 | GCP | Backup & DR for POC stores | Validate RTO/RPO assumptions | Conditional | Custom options | DBA / SRE | Configure backups | Service-specific admin roles | Resource | AlloyDB backups/PITR; GCS versioning; index rebuild runbook | Restore drill (M-CO-12) | GCP-11 | Not started | Low | -
GCP-27 | GCP | Gemini / ADK runtime for agent tests (Agent Engine, Cloud Run or existing host) | EXP-41, EXP-ACL-11/20 | Mandatory | All | App team | Deploy ADK 2.0.3 test agents | roles/aiplatform.user; roles/run.invoker to call RAG API | Project | Same ADK version as production; A2A endpoints internal only | Agent invokes RAG tool | GCP-09 | Not started | High | Confirm where current agents run (AQ-20)
SRC-01 | SharePoint / Entra | Entra app registration for ingestion | Read SharePoint content + permissions | Mandatory | Custom options | M365 / Identity admins | Admin consent | Graph application permission Sites.Selected (+ per-site grant) preferred; alternatively Sites.Read.All / Files.Read.All - security decision | Tenant / site | Certificate credential stored in Secret Manager; per-site 'read' grant for POC sites | Token acquired; can list POC site drives only | - | Not started | High | Separate from any user-facing app
SRC-02 | SharePoint / Entra | SharePoint REST access for role assignments & SP groups | Graph does not cover all SP group membership | Mandatory | Custom options | M365 admins | App-only access to SharePoint REST (certificate) | Same app; verify Sites.Selected covers REST role assignment reads | Site | - | GET /_api/web/roleassignments succeeds on POC site | SRC-01 | Not started | High | To Verify
SRC-03 | SharePoint / Entra | Directory read for group expansion | transitiveMemberOf, group delta | Mandatory | All custom | Identity admins | Admin consent for directory read | Graph application permission GroupMember.Read.All (and User.Read.All for identity map) | Tenant | Least privilege; consider restricting to POC user set via app role assignment | Expand test user groups | SRC-01 | Not started | High | -
SRC-04 | SharePoint / Entra | Entra app registration for RAG API (audience) + client app registrations | Validate end-user tokens; bind app_id to caller (FR-SEC-06) | Mandatory | All custom | Identity admins | Expose API scope; client apps get delegated permission | n/a - non-GCP permission (see Required access) | Tenant | Access token v2; audience = RAG API; app roles per app_id | Token from client accepted; others rejected | - | Not started | High | -
SRC-05 | SharePoint / Entra | On-Behalf-Of flow for authoritative checks | ENF-04 validation step | Conditional | ENF-03/04 options | Identity admins | Delegated Graph permissions (e.g. Files.Read.All / Sites.Read.All delegated) + consent | n/a - non-GCP permission (see Required access) | Tenant | OBO from RAG API audience to Graph | OBO token exchange works for test user | SRC-04 | Not started | Medium | Delegated rights never exceed the user's
SRC-06 | SharePoint / Entra | Graph change notifications endpoint | Near-real-time updates (optional) | Conditional | ING-03 | M365 + Network | Subscription creation | Same app permissions | Tenant | Public HTTPS endpoint with validation token + clientState secret | Notification received | GCP-09 | Not started | Low | Polling delta is acceptable for POC
SRC-07 | SharePoint / Entra | Test site + test users for ACL fixtures (DS-03) | Negative tests | Mandatory | All | M365 admins | Create site, groups, 10-20 test users | Tenant admin tasks | Tenant | Licences for test users; MFA policy exemptions handled by security | Truth table created | - | Not started | High | Never use real users' accounts
SRC-08 | ServiceNow | Integration user + OAuth client | Read KB, attachments, user criteria, membership tables | Mandatory | Custom options | ServiceNow platform team | Inbound OAuth application; integration user with least roles to read in-scope tables | n/a - non-GCP permission (see Required access) | Instance | Read ACLs for kb_knowledge, kb_knowledge_base, user_criteria, kb_uc_can_read_mtom, kb_uc_cannot_read_mtom, sys_user, sys_user_grmember, sys_user_has_role, sys_attachment | Table API calls succeed; writes denied | - | Not started | High | Role names instance-specific - To Verify
SRC-09 | ServiceNow | Per-user authorisation check capability | Evaluate user criteria incl. scripts; validate top-N | Mandatory | Custom options | ServiceNow platform team | Either KM API called with user identity (OAuth on behalf of user / SSO) or a scripted REST endpoint 'canRead(user, articles)' running UserCriteria evaluation server-side | n/a - non-GCP permission (see Required access) | Instance | Secure endpoint; audit; rate limits | Returns correct allow/deny for DS-03 users | SRC-08 | Not started | High | Design choice - ServiceNow team input needed
SRC-10 | ServiceNow | Rate limits & IP allow-listing | Avoid throttling / blocked egress | Mandatory | Custom options | ServiceNow platform team | Rate-limit rule for integration user; allow-list NAT IP | n/a - non-GCP permission (see Required access) | Instance | - | Load test within agreed limits | GCP-16 | Not started | Medium | -
SRC-11 | ServiceNow | Test KB + test users with criteria fixtures (DS-03) | Negative tests | Mandatory | All | ServiceNow platform team | Create test KB, criteria (incl. one scripted), users, roles | n/a - non-GCP permission (see Required access) | Instance (sub-prod preferred) | Mirror production criteria patterns | Truth table created | - | Not started | High | Prefer sub-production instance with cloned config
SRC-12 | ServiceNow / Entra | Identity mapping Entra -> sys_user | Resolve user for ServiceNow ACLs | Mandatory | All | Identity + ServiceNow | Read sys_user mapping attributes | n/a - non-GCP permission (see Required access) | Instance + tenant | Agreed join key (email / UPN / employee id) | Mapping coverage report (M-SEC-10) | SRC-08 | Not started | High | FR-SEC-02 open question

## 13_API_SDK_Inventory
API, SDK & integration inventory (agent orchestrates; RAG service owns ingestion, retrieval, ACL, context)
Item ID | Purpose area | Service / library | API or package | Language | Version (verified?) | Documentation URL | Authentication | Integration purpose | Compatibility notes | Limitations | Verification status | Date checked
API-01 | Embedding generation | Vertex AI | google-genai SDK (Vertex AI mode) / REST models:predict or embedContent | Python | Use latest stable; pin in requirements - To Verify | https://cloud.google.com/vertex-ai/generative-ai/docs/embeddings/get-text-embeddings | ADC / service account | gemini-embedding-001, text-embedding-005 | Older vertexai.language_models module superseded - verify deprecation | Per-request input limits (see EMB-01) | Verified (web check 2026-10-26) | 2026-10-26
API-02 | Generation | Vertex AI Gemini | google-genai SDK | Python | To Verify | https://cloud.google.com/vertex-ai/generative-ai/docs/models | ADC / SA | Answer generation, rewriting, judges | Model IDs change - read from config per app_id | Quotas per model/region | Documented - re-verify before use | 2026-10-26
API-03 | Managed retrieval (baseline) | Discovery Engine | google-cloud-discoveryengine (SearchService, ConversationalSearchService answer) | Python | To Verify | https://cloud.google.com/generative-ai-app-builder/docs/libraries | ADC; end-user identity for ACL'd data stores - verify mechanism (user credential / WIF token) | Baseline EXP-00; hybrid options | v1 vs v1beta/v1alpha features differ | ACL'd search requires user identity | Documented - re-verify before use | 2026-10-26
API-04 | Reranking | Discovery Engine Ranking API | RankServiceClient.rank (semantic-ranker-default-004 / fast-004) | Python | To Verify | https://cloud.google.com/generative-ai-app-builder/docs/ranking | ADC / SA | RRK-01 | Requires discoveryengine API enabled | Records per request limits | Verified (web check 2026-10-26) | 2026-10-26
API-05 | Grounding | Discovery Engine Check Grounding API | GroundedGenerationServiceClient.check_grounding | Python | To Verify | https://cloud.google.com/generative-ai-app-builder/docs/check-grounding | ADC / SA | ADV-20 | - | Claim-level scores are signals, not proofs | Documented - re-verify before use | 2026-10-26
API-06 | Vector indexing/retrieval | Vertex AI Vector Search | google-cloud-aiplatform (MatchingEngineIndex, MatchingEngineIndexEndpoint) | Python | To Verify | https://cloud.google.com/vertex-ai/docs/vector-search/overview | ADC / SA | B-05/B-06 | 2.0 collections use different API surface - verify | Restricts limits - verify | Documented - re-verify before use | 2026-10-26
API-07 | Vector + keyword (PostgreSQL) | AlloyDB / Cloud SQL | pgvector extension; psycopg 3 / asyncpg; alloydb-connector / cloud-sql-python-connector; langchain-google-alloydb-pg (optional) | Python / SQL | pgvector version available per service - To Verify (HNSW 2000-dim limit for vector type) | https://github.com/pgvector/pgvector | IAM DB auth via connector | B-01..B-04 | Iterative index scans need pgvector >= 0.8 - verify managed version | - | Documented - re-verify before use | 2026-10-26
API-08 | Offline exact search / eval | BigQuery | google-cloud-bigquery; VECTOR_SEARCH, CREATE VECTOR INDEX, ML.GENERATE_EMBEDDING | SQL / Python | n/a | https://cloud.google.com/bigquery/docs/vector-search-intro | ADC / SA | Ground truth, analytics | - | Latency not interactive | Documented - re-verify before use | 2026-10-26
API-09 | Document ingestion & parsing | Document AI | google-cloud-documentai (Layout Parser, OCR) | Python | To Verify | https://cloud.google.com/document-ai/docs/layout-parse-chunk | ADC / SA | ING-06/07/08 | Processor versions pinned | Page limits per request (online vs batch) | Documented - re-verify before use | 2026-10-26
API-10 | File extraction (OSS) | Docling / Unstructured / Apache Tika | docling, unstructured, tika | Python / Java | To Verify | https://github.com/docling-project/docling | n/a | E-01, EXP-32 | Licence check (MIT / Apache-2.0 - verify) | Quality varies by file type | OSS/Third-party - verify licence & version | 2026-10-26
API-11 | Keyword search | Elasticsearch | elasticsearch-py; retrievers (rrf, knn) | Python | 8.x/9.x - To Verify | https://www.elastic.co/guide/en/elasticsearch/reference/current/index.html | API key / SAML | C-02 | DLS requires appropriate subscription | - | OSS/Third-party - verify licence & version | 2026-10-26
API-12 | Keyword + vector | OpenSearch | opensearch-py; k-NN plugin; Security plugin | Python | To Verify | https://opensearch.org/docs/latest/ | Basic/OIDC | C-03 | - | - | OSS/Third-party - verify licence & version | 2026-10-26
API-13 | Vector DB | Qdrant | qdrant-client | Python | To Verify | https://qdrant.tech/documentation/ | API key / JWT | C-01, C-08 | - | - | OSS/Third-party - verify licence & version | 2026-10-26
API-14 | Vector DB | Weaviate / Milvus | weaviate-client v4; pymilvus | Python | To Verify | https://milvus.io/docs | API key / RBAC | C-04, C-05 | - | - | OSS/Third-party - verify licence & version | 2026-10-26
API-15 | ANN benchmarking | FAISS / hnswlib / ScaNN | faiss-cpu/gpu, hnswlib, scann | Python | To Verify | https://github.com/facebookresearch/faiss | n/a | AX experiments | ScaNN wheels platform support - verify | - | OSS/Third-party - verify licence & version | 2026-10-26
API-16 | OSS embeddings & rerankers | Sentence Transformers / HF TEI / vLLM | sentence-transformers; text-embeddings-inference; vllm | Python | To Verify | https://sbert.net | n/a | EMB-06..13, RRK-02..04 | GPU drivers on Cloud Run GPU / GKE | - | OSS/Third-party - verify licence & version | 2026-10-26
API-17 | RAG frameworks (optional) | LlamaIndex / LangChain / Haystack | llama-index, langchain, haystack-ai | Python | To Verify | https://docs.llamaindex.ai/ | n/a | C-07 | Fast-moving APIs; pin versions | Must not bypass server-side ACL filters | OSS/Third-party - verify licence & version | 2026-10-26
API-18 | Agent orchestration | Google ADK | google-adk 2.0.3 (Python) | Python | ADK 2.0 GA 2026-05-19; 2.x point releases through at least 2.12 (Oct 2026); confirm 2.0.3 API surface | https://adk.dev/2.0/ | n/a | Agent calls RAG service as FunctionTool / OpenAPIToolset / MCP toolset; RemoteA2aAgent for remote agents | ADK 2.0 changed agent API, event model and session schema (graph-based engine) - verify tool & auth APIs against 2.0.3 specifically | Later 2.x releases fixed A2A role mapping / part conversion - consider upgrade path | Verified (web check 2026-10-26) | 2026-10-26
API-19 | Agent communication | A2A protocol | a2a-sdk (Python); ADK A2A integration (to_a2a / RemoteA2aAgent) | Python | To Verify spec version used by ADK 2.0.3 | https://a2a-protocol.org/latest/specification/ | Agent Card securitySchemes (OAuth2 / OIDC / API key) | Remote agents; identity forwarding | Per-invocation auth headers for agent cards added in ADK 2.6.0 - may be absent in 2.0.3 | Do not put user tokens in message text | Verified (web check 2026-10-26) | 2026-10-26
API-20 | SharePoint content | Microsoft Graph | msgraph-sdk (Python) / REST v1.0: /sites, /drives/{id}/root/delta, /items/{id}/permissions | Python | v1.0 | https://learn.microsoft.com/en-us/graph/api/driveitem-delta | App-only certificate (MSAL) | SP-04..SP-11 | Beta endpoints not for production | Throttling (429) | Documented - re-verify before use | 2026-10-26
API-21 | SharePoint permissions | SharePoint REST | /_api/web/roleassignments, /_api/web/lists/.../items(id)/roleassignments, HasUniqueRoleAssignments, /_api/web/sitegroups | REST | n/a | https://learn.microsoft.com/en-us/sharepoint/dev/sp-add-ins/set-custom-permissions-on-a-list-by-using-the-rest-interface | App-only certificate | SP-10 | Docs written for add-ins; app-only access pattern for Entra apps - verify | List view threshold | To Verify | 2026-10-26
API-22 | Directory | Microsoft Graph | /users/{id}/transitiveMemberOf, /groups/delta, /groups/{id}/transitiveMembers | Python | v1.0 | https://learn.microsoft.com/en-us/graph/api/user-list-transitivememberof | App-only | ID-02 | - | Large tenants: paging | Documented - re-verify before use | 2026-10-26
API-23 | Delegated authorisation | MSAL Python | msal (OBO: acquire_token_on_behalf_of) | Python | To Verify | https://learn.microsoft.com/en-us/entra/identity-platform/v2-oauth2-on-behalf-of-flow | Confidential client | ID-03, ENF-04 | - | Consent requirements | Documented - re-verify before use | 2026-10-26
API-24 | Token validation | Entra ID | PyJWT / authlib with JWKS from Entra OpenID config | Python | To Verify | https://learn.microsoft.com/en-us/entra/identity-platform/access-tokens | n/a | ID-01 | v2 tokens; validate iss, aud, exp, signature | Groups overage claim | Documented - re-verify before use | 2026-10-26
API-25 | Delegated search (federated option) | Microsoft Graph Search API | POST /search/query (driveItem, listItem, site) | REST | v1.0 | https://learn.microsoft.com/en-us/graph/api/resources/search-api-overview | Delegated only | D-03 / validation | Results security-trimmed for the user | Paging and rate limits | Documented - re-verify before use | 2026-10-26
API-26 | ServiceNow content | ServiceNow Table & Attachment APIs | /api/now/table/kb_knowledge, /api/now/attachment | REST | Instance release - To Verify | https://developer.servicenow.com/dev.do#!/reference/api/latest/rest/c_TableAPI | OAuth 2.0 | SN-01..SN-05 | sysparm_display_value, sysparm_fields to limit payload | Rate limits per instance | Documented - re-verify before use | 2026-10-26
API-27 | ServiceNow knowledge (user-aware) | Knowledge Management REST API | /api/sn_km_api/knowledge/articles | REST | Plugin/release dependent - To Verify | https://developer.servicenow.com/dev.do#!/reference/api/latest/rest/knowledge-api | OAuth 2.0 as the user | SN-03 validation; D-03 | Evaluates access for calling user | Requires user-context auth path | To Verify | 2026-10-26
API-28 | ServiceNow user criteria evaluation | Scripted REST API (custom) | Custom endpoint using server-side user criteria evaluation | Server JS | n/a | ServiceNow docs (Scripted REST APIs) - To Verify | OAuth 2.0 (integration) | SN-07 resolution of user-criteria matches per user | Custom code owned by ServiceNow team | Must be performance-tested | Proposed pattern - validate in POC | 2026-10-26
API-29 | Observability | Cloud Logging / Trace / OpenTelemetry | google-cloud-logging; opentelemetry-sdk + Cloud Trace exporter | Python | To Verify | https://cloud.google.com/trace/docs/setup/python-ot | ADC | Stage-level latency, audit | ADK emits OTel spans (verify config in 2.0.3) | Do not log content | Documented - re-verify before use | 2026-10-26
API-30 | Evaluation | Vertex AI Gen AI evaluation service / RAGAS / custom | google-cloud-aiplatform (evaluation); ragas | Python | To Verify | https://cloud.google.com/vertex-ai/generative-ai/docs/models/evaluation-overview | ADC | M-AQ metrics | Judges must be calibrated (GD-09) | Judge cost | Documented - re-verify before use | 2026-10-26
API-31 | Content safety | Model Armor | Model Armor API (sanitize prompt/response) | REST / Python | To Verify | https://cloud.google.com/security-command-center/docs/model-armor-overview | ADC | ADV-28 / EXP-37 | Region availability - verify | Not a full injection guarantee | To Verify | 2026-10-26
API-32 | PII | Sensitive Data Protection | google-cloud-dlp | Python | To Verify | https://cloud.google.com/sensitive-data-protection/docs | ADC | ING-27 | - | Cost per GB | Documented - re-verify before use | 2026-10-26

## 14_Experiments
POC experiment matrix - one independent variable per experiment; ACL experiments are zero-tolerance gates
Experiment ID | Hypothesis | Architecture variant | Variable under test | Baseline configuration | Alternative configuration | Dataset / corpus | Query set | Ground-truth requirement | Controlled variables | Independent variable levels | Evaluation procedure | Metrics | Expected outcome (hypothesis) | Dependencies | Estimated effort (person-days, indicative) | Relative cost | Priority | Acceptance criteria | Result status | Actual results | Observations | Next action
EXP-00 | Establish managed baseline quality, latency, cost and ACL behaviour | A-01 | None (baseline) | Current production configuration | - | DS-01 | DS-02 | Graded relevance + reference answers | Same corpus snapshot | - | Run all golden queries through Search API and Answer API as test users; capture results, latency, citations | M-RQ-01..05, M-AQ-01..08, M-PF-01..03, M-CO-03 | Baseline numbers | GCP-01..08, DS-02 | 5 | Low | P0 | Baseline report signed off; reproducible run script | Not started
EXP-01 | Embedding model choice changes Recall@20 on our corpus | B-01 | Embedding model | EMB-01 @768 | EMB-03, EMB-06, EMB-07 (and EMB-01 @1536) | DS-01 | DS-02 dev | Chunk-level relevance | Identical chunks (CHK-06), exact search (no ANN), no reranker, same k | 4-5 models | Embed same chunk set per model; exact KNN; score per stratum | M-RQ-01, M-RQ-05, M-CO-02, M-PF-06 | Model differences visible by stratum, not uniform | EXP-07 baseline chunks | 5 | Medium | P1 | Pick top 2 models; difference significant (paired bootstrap p<0.05) | Not started
EXP-02 | A large OSS model sets a useful quality ceiling | C-08 | Embedding model | Best of EXP-01 | EMB-09 Qwen3-Embedding-8B | DS-01 | DS-02 dev | As EXP-01 | As EXP-01 | 2 | As EXP-01 | M-RQ-01/05, M-CO-02 | Ceiling informs whether embedding is the bottleneck | EXP-01, GPU quota | 3 | Medium | P3 | Documented gap vs best managed | Not started
EXP-03 | Higher dims do not necessarily improve recall | B-01/B-03 | Embedding dimensions | EMB-01 @768 | @1536, @3072 (halfvec) | DS-01 | DS-02 dev | As EXP-01 | Same model, chunks, exact search | 768 / 1536 / 3072 | Request output_dimensionality per level; exact KNN | M-RQ-01/05, storage GB, M-PF-01 | Diminishing returns beyond 768-1536 (to prove) | EXP-01 | 2 | Low | P1 | Choose smallest dims within 1 NDCG point of best | Not started
EXP-04 | Acronym/jargon queries are the main dense-retrieval failure | B-01 | Query stratum | Dense only | Dense + glossary expansion; hybrid | DS-01 | DS-02 acronym stratum | Chunk relevance | Same model/chunks | strata | Compare per-stratum recall | M-RQ-01 per stratum | Hybrid/glossary fix most misses | Glossary seed list | 2 | Low | P1 | Identify top failure strata | Not started
EXP-05 | Multilingual docs need a multilingual model (conditional) | B-01 | Embedding model | EMB-03 | EMB-01, EMB-07 | DS-01 non-English subset | Multilingual queries | As EXP-01 | Same chunks | 3 | Cross-lingual retrieval test | M-RQ-01 | Only run if AQ-06 confirms languages | AQ-06 | 2 | Low | P3 | Decision recorded | Not started
EXP-06 | Long documents benefit from long-context embedding or parent-child | B-01 | Max input / chunking | EMB-01 (2048 tokens) with CHK-06 | EMB-07 (8192) whole-section chunks; CHK-10 | DS-01 long-doc subset | Long-doc queries | As EXP-01 | Same corpus | 3 | Compare recall and completeness | M-RQ-01, M-AQ-06 | Parent-child matches long-context at lower cost | EXP-07 | 3 | Medium | P2 | Recommendation for long docs | Not started
EXP-07 | Structure-aware chunking beats recursive splitting | B-01 | Chunking strategy | CHK-05 recursive 512 tokens | CHK-06 heading-aware; CHK-03 sentence | DS-01 | DS-02 dev | Chunk relevance re-mapped to doc spans | Same embedding (best EXP-01 provisional), exact search | 3 strategies | Map relevance labels to spans so chunk boundaries do not bias labels | M-RQ-01/05, M-AQ-06 | CHK-06 better for SharePoint docs | Layout parser output | 4 | Low | P1 | Winner by >= 2 NDCG points or simpler option kept | Not started
EXP-08 | Parent-child improves completeness without hurting precision | B-01 | Context unit | CHK-06 chunks returned directly | CHK-10 child 256 / parent section | DS-01 | DS-02 dev | Reference answers | Same retrieval stack | 2 | End-to-end answer eval | M-AQ-06, M-AQ-03, generation tokens | Completeness up | EXP-07 | 3 | Low | P1 | Completeness up, faithfulness not down | Not started
EXP-09 | Chunk size has an optimum per corpus | B-01 | Chunk size | 512 tokens | 256, 1024 | DS-01 | DS-02 dev | Span-mapped relevance | Strategy, overlap, model fixed | 3 | CPX-01..03 | M-RQ-01/05, storage | Optimum around 256-512 for KB, larger for docs (hypothesis) | EXP-07 | 2 | Low | P1 | Select size per doc type | Not started
EXP-10 | Overlap gives small recall gain at storage cost | B-01 | Overlap | 0% | 10%, 20% | DS-01 | DS-02 dev | Span-mapped | Size fixed | 3 | CPX-04 | M-RQ-01, storage, M-CO-02 | Little gain with heading-aware chunks | EXP-09 | 1 | Low | P2 | Keep overlap only if >= 1 point recall | Not started
EXP-11 | ANN (HNSW) reaches >= 0.95 Recall@20 vs exact at target latency | B-01 | Exact vs ANN | Exact KNN | HNSW default params | DS-04 1M | DS-02 + synthetic queries | Exact results as ground truth | Same vectors | 2 | AX-01/02 | M-RQ-06, M-PF-01..03 | ANN recall high without filters | DS-04 | 3 | Low | P1 | Recall@20 >= hypothesis target with P95 within budget | Not started
EXP-12 | Index parameter tuning finds a recall/latency sweet spot | B-01/B-02/B-05 | ANN params / index type | HNSW defaults | HNSW sweep; ScaNN (AlloyDB); Tree-AH (Vector Search) | DS-04 | Synthetic | Exact GT | Vectors fixed | grid per AX sheet | AX-03..08 | M-RQ-06, M-PF-02, M-PF-07, memory | Pareto curve per platform | EXP-11 | 5 | Medium | P2 | Chosen config on Pareto frontier | Not started
EXP-13 | Hybrid (dense + BM25, RRF) beats either alone | B-01 | Retrieval mode | Dense only | BM25 only; Hybrid RRF k=60 | DS-01 | DS-02 dev (all strata) | Chunk relevance | Model, chunks fixed; no reranker | 3 | Per-stratum comparison | M-RQ-01/04/05 | Hybrid wins overall; BM25 wins IDs | EXP-07 | 3 | Low | P1 | Hybrid >= dense on every stratum within noise | Not started
EXP-14 | Learned sparse beats BM25 in hybrid | B-06/C-01 | Sparse representation | BM25 | bge-m3 sparse; SPLADE (licence permitting) | DS-01 | DS-02 dev | As EXP-13 | Dense fixed | 2-3 | As EXP-13 | M-RQ-01/05 | Marginal gain (to prove) | EXP-13 | 4 | Medium | P3 | Adopt only if >= 2 NDCG points | Not started
EXP-15 | Metadata filters return exactly the matching set | B-01, A-01 | Filter translation | No filter | source, type, date range, custom fields, in/not | DS-01 | Filter test queries | Expected IDs per filter | Same index | Filter cases | Compare result sets to SQL truth | M-RQ-08 | 100% correctness | Metadata mapping | 2 | Low | P1 | Filter correctness = 100% | Not started
EXP-16 | Glossary expansion improves acronym recall without precision loss | A-04, B-01 | Query expansion | No expansion | Acronym + synonym expansion; ambiguous handling by app scope | DS-01 | Acronym stratum + control | Chunk relevance | Retrieval stack fixed | 2-3 | Per-stratum | M-RQ-01, M-RQ-02 | Acronym recall up | Glossary seed (FR-GLO-01) | 3 | Low | P1 | Acronym recall up; control stratum not down | Not started
EXP-17 | LLM query rewriting fixes conversational follow-ups | B-01 | Query rewriting | Raw last turn | Gemini Flash standalone rewrite | DS-01 | Conversational stratum | Relevance | Retrieval fixed | 2 | Per-stratum | M-RQ-01, M-PF-02 | Big gain on follow-ups | Multi-turn test set | 2 | Low | P2 | Gain on conversational; latency within budget | Not started
EXP-18 | Multi-query retrieval improves recall on vague queries | B-01 | Multi-query | Single query | 3 paraphrases + RRF | DS-01 | Vague stratum | Relevance | - | 2 | - | M-RQ-01, M-PF-02, M-CO-03 | Small gain, higher cost | EXP-13 | 2 | Low | P3 | Adopt only for routed vague queries | Not started
EXP-19 | Reranking improves NDCG@10; depth has diminishing returns | A-03, B-01 | Reranker + depth | No reranker | RRK-01 default-004 / fast-004; RRK-02; depth 20/50/100 | DS-01 | DS-02 dev | Graded relevance | First stage fixed (best hybrid) | 3 rerankers x 3 depths | Rerank same candidate lists | M-RQ-05, M-RQ-04, M-PF-02, M-CO-08 | NDCG up; depth 50 sweet spot (hypothesis) | EXP-13 | 3 | Medium | P1 | NDCG uplift >= 2 points at acceptable P95 | Not started
EXP-20 | Contextual chunk enrichment improves recall | B-01 | Contextual retrieval (ADV-01) | Plain chunks | LLM-context-prefixed chunks (embed + BM25) | DS-01 | DS-02 dev | Relevance | Model, chunking fixed | 2 | Re-index variant | M-RQ-01, M-CO-01 | Recall gain on terse chunks | EXP-13 | 4 | Medium | P2 | Gain justifies ingestion cost | Not started
EXP-21 | Context assembly settings change answer quality | B-01 | Context size/order | Top-5 chunks, score order | Top-10, top-20, parent expansion, doc-grouped order | DS-01 | DS-02 dev | Reference answers | Retrieval fixed | 4 | End-to-end eval | M-AQ-01/06/07, generation tokens | More context helps until noise | EXP-19 | 3 | Medium | P1 | Choose smallest context meeting quality | Not started
EXP-22 | Grounding check + abstention reduce unsupported claims | A-03, B-01 | ADV-20/27 | No check | Check Grounding API threshold; prompt-level abstention | DS-01 | DS-02 + DS-05 unanswerable | Reference answers + unanswerable labels | Retrieval fixed | 3 | End-to-end | M-AQ-07, M-AQ-08 | Unsupported claims down; abstention up | - | 2 | Low | P1 | Unsupported-claim rate below hypothesis target; correct abstention up | Not started
EXP-23 | Citations are correct and complete | A-01, B-01 | Citation method | Managed citations | Custom chunk-ID citation mapping | DS-01 | DS-02 | Expected evidence | - | 2 | Human + automated check | M-AQ-04/05 | Custom >= managed | - | 2 | Low | P1 | Citation correctness >= hypothesis target | Not started
EXP-24 | Vector store choice matters less than embedding/chunking for quality but matters for latency/cost/ACL | B-01, B-05, C-01, C-02 | Vector store | AlloyDB (B-01) | Vector Search (B-05), Qdrant (C-01), Elastic (C-02) | DS-01 + DS-04 | DS-02 | Relevance + exact GT | Same chunks, embeddings, k, reranker off | 4 | Load same data; run quality + latency + ACL filter tests | M-RQ-01/06, M-PF-01..04, M-SEC-01, ops effort | Quality similar; latency/ops differ | EXP-11, EXP-ACL-04 | 10 | High | P2 | Shortlist 1-2 stores meeting ACL + latency | Not started
EXP-25 | Query decomposition helps compound questions | B-01 | ADV-06 | Single retrieval | ADK planner decomposes | DS-01 | Compound stratum | Reference answers | - | 2 | End-to-end | M-AQ-06, M-PF-02 | Gain only on compound stratum | EXP-21 | 3 | Medium | P3 | Adopt behind router if gain | Not started
EXP-26 | Iterative multi-hop retrieval answers chained questions | B-01 | ADV-12 | Single retrieval | Iterative loop with budget 3 | DS-01 | Multi-hop stratum | Reference answers | - | 2 | End-to-end | M-AQ-06, M-PF-03 | Gain with latency penalty | EXP-25 | 4 | Medium | P4 | Only if multi-hop queries are frequent | Not started
EXP-27 | Section/document summaries help overview queries | B-01 | ADV-05 / CHK-12 | Chunks only | + summary index routing | DS-01 | Overview stratum | Reference answers | - | 2 | End-to-end | M-RQ-07, M-AQ-06 | Gain on overview | - | 4 | Medium | P3 | Gain justifies summary cost | Not started
EXP-28 | Agentic retrieval via ADK improves complex tasks without ACL regressions | B-01 | ADV / RET-16 | Fixed pipeline tool | ADK agent with search + filter tools | DS-01 | Complex stratum + DS-03 | Reference + ACL truth | Identity propagation fixed | 2 | End-to-end + ACL tests | M-AQ-06, M-SEC-03 | Gains limited; variance higher | EXP-ACL-20 | 5 | Medium | P3 | No ACL regression; measurable gain | Not started
EXP-29 | Weighted fusion beats RRF after calibration | B-01 | Fusion method | RRF k=60 | alpha in {0.3,0.5,0.7} | DS-01 | DS-02 dev | Relevance | Both retrievers fixed | 4 | - | M-RQ-05 | Marginal | EXP-13 | 1 | Low | P2 | Adopt only if stable across strata | Not started
EXP-30 | Ingestion pipeline sustains target throughput within quotas | B-01/B-05 | Ingestion parallelism | 1 worker | 4 / 16 / 64 workers | DS-04 subset + DS-01 | - | Doc counts | Same parser/model | 4 | Measure docs/hour, 429s, cost per 10k docs | M-PF-05/06, M-CO-01, error rate | Throughput bounded by Graph/model quotas | Quotas GCP-12 | 4 | Medium | P1 | Full re-index of target corpus within agreed window (AQ-10) | Not started
EXP-31 | Incremental sync keeps content freshness within SLA | B-01 | Sync mode | Nightly batch | Hourly delta; webhook-triggered | DS-01 | Freshness probes | Timestamps | - | 3 | Edit/create docs; measure time to searchable | M-PF-08 | Delta meets SLA | ING-02 | 3 | Low | P1 | P95 freshness within SLA (AQ-11) | Not started
EXP-32 | Parser choice drives chunk quality for PDFs/Office | B-01 | Parser | Managed parser (A-01) | Document AI Layout Parser; Docling | DS-01 sample 200 files | Table/heading questions | Span-level truth | Chunking fixed | 3 | Manual + automated text-fidelity checks | Extraction accuracy, M-RQ-01 on table stratum, cost/page | Layout Parser best on tables (hypothesis) | - | 4 | Medium | P1 | Choose parser per file type | Not started
EXP-33 | Retrieval sustains peak concurrency with P95 within budget | B-01/B-05/C-01 | Concurrency | 1 QPS | 10 / 50 / peak QPS (AQ-07) | DS-04 | Synthetic replay | - | Config fixed | 4 | Locust/k6 load test against RAG API with ACL filters | M-PF-02/03/04, error rate, autoscaling | Bottleneck identified | EXP-12 | 4 | Medium | P1 | P95 within hypothesis budget at peak | Not started
EXP-34 | Quantisation / MRL / Flash model cut cost with small quality loss | B-01 | Cost levers | float32, 1536 dims, Pro model | int8/halfvec, 768 dims, Flash model | DS-01 | DS-02 | Relevance + answers | - | 3 levers | One lever at a time | M-CO-03/04, M-RQ-05, M-AQ-01 | Large savings, small loss | EXP-21 | 3 | Low | P2 | Cost per successful answer down with <= 1 point quality loss | Not started
EXP-35 | Best custom configuration beats managed baseline by a margin that justifies its TCO | A-01 vs best B/C/D | End-to-end architecture | A-01 | Winner of EXP-01..34 | DS-01 | DS-02 HELD-OUT | Full labels | Same corpus snapshot & users | 2-3 architectures | Blind evaluation; human + calibrated judge | All retrieval, answer, perf, cost, security metrics | Decision evidence | All P1 experiments + ACL gate passed | 5 | Medium | P0 | Pre-agreed improvement threshold (decision gate G4) met with zero ACL failures | Not started
EXP-36 | Streaming reduces time-to-first-token | B-01 | Streaming (FR-API-04) | Non-streaming | SSE streaming | DS-01 | DS-02 sample | - | - | 2 | Measure TTFT | M-PF-10 | TTFT reduced substantially | - | 1 | Low | P2 | TTFT within hypothesis target | Not started
EXP-37 | Prompt-injection in retrieved docs is neutralised | A-01, B-01 | Injection defences (ADV-28) | Plain prompt | Delimiting + Model Armor + tool allow-list | DS-05 | Injection set | Expected safe behaviour | - | 2 | Red-team run | M-SEC-12 | Injection success near zero | - | 3 | Low | P1 | No successful data exfiltration / instruction following | Not started
EXP-38 | Near-dup suppression improves context diversity | B-01 | RRK-09 / ING-12 | None | Doc-level collapse + cosine 0.95 | DS-01 | DS-02 | Relevance | - | 2 | - | Unique-doc ratio, M-AQ-06 | Better completeness | - | 1 | Low | P2 | No loss of authorised evidence | Not started
EXP-39 | ACL filter selectivity reduces ANN recall unless engine filters in-graph | B-01/B-05/C-01 | Filter selectivity | No filter | user sees 50% / 10% / 1% / 0.1% of corpus | DS-04 with synthetic ACLs | Synthetic | Exact filtered GT | Index fixed | 4 | AX-11 | M-RQ-06, M-PF-02 | Post-filter engines collapse at low selectivity | DS-04 | 4 | Medium | P1 | Filtered Recall@20 >= target at realistic selectivity | Not started
EXP-40 | Permission-aware semantic cache saves cost without leakage | B-01 | ADV-23/24 | No cache | Exact + semantic cache keyed by principal-set hash + acl_version | DS-01 | Replay with repeats | - | - | 2 | Replay with 2 users of different access | Hit rate, M-SEC-11 | Savings with zero leakage | EXP-ACL-10 | 3 | Low | P3 | Zero cross-user leakage | Not started
EXP-41 | RAG exposed to ADK/A2A adds acceptable overhead | B-01 | Integration path | ADK FunctionTool calling RAG API | Remote A2A agent wrapping RAG | DS-01 | DS-02 sample | - | Same RAG backend | 2 | Trace end-to-end | M-PF-02, identity propagation correctness | Overhead small vs generation | ADK 2.0.3 env | 3 | Low | P1 | Overhead within budget; identity propagated correctly | Not started
EXP-42 | Self-hosted embeddings beat managed on cost at our volume | B-11 vs B-01 | Embedding serving | EMB-01 API | EMB-06 on Cloud Run GPU | DS-04 subset | - | - | Same chunks | 2 | Throughput + cost per 1M tokens | M-PF-06, M-CO-02 | Break-even depends on volume | EXP-01 | 3 | Medium | P2 | Cost model updated with measured numbers | Not started
EXP-ACL-01 | Extracted ACLs match source truth (SharePoint) | B-01 + A-01 | ACL extraction | Source truth table (DS-03) | Custom extractor; managed connector | DS-03 | Per-user access checks | DS-03 truth table | - | 2 | Compare effective allowed principals per doc for each test user | M-SEC-08, discrepancy count | 100% match for supported semantics | DS-03 | 4 | Low | P0 | Zero false-allow; false-deny documented | Not started
EXP-ACL-02 | Every chunk resolves to its document ACL | B-01 | Chunk-ACL linkage | - | Chunking with ACL reference | DS-03 | - | Truth table | - | - | Audit all chunks for resolvable acl_version | M-SEC-08 | 100% | EXP-ACL-01 | 1 | Low | P0 | No orphan chunks | Not started
EXP-ACL-03 | Vector and keyword branches enforce identical ACLs | B-01/B-05/C-02 | Cross-store consistency | - | Consistency checker | DS-03 | Per-user queries on both branches | Truth table | - | - | Query both branches as each user | M-SEC-01, M-SEC-09 | Identical | EXP-ACL-01 | 2 | Low | P0 | Zero discrepancies | Not started
EXP-ACL-04 | Filtered retrieval never returns unauthorised content | All candidates | Enforcement | - | ENF-04 | DS-03 + DS-01 | Queries targeting restricted docs, run as allowed and denied users | Truth table | - | users x docs | Automated negative test suite | M-SEC-01..04 | Zero unauthorised | EXP-ACL-01 | 3 | Low | P0 | Zero tolerance | Not started
EXP-ACL-05 | Removing a user from an Entra/SP group revokes access within SLA | B-01, A-01 | Revocation | - | Group removal | DS-03 | Probe query every minute | Truth table | - | - | Remove user; measure time until no longer retrieved/cited/cached | M-SEC-06 | Within revocation SLA (AQ-15) | Cache TTLs | 2 | Low | P0 | P100 within SLA | Not started
EXP-ACL-06 | ServiceNow user-criteria / role change propagates within SLA | B-01, A-01 | Revocation (SN) | - | Remove role / group / criteria | DS-03 | Probe | Truth table | - | - | As EXP-ACL-05 | M-SEC-06 | Within SLA | SN admin access | 2 | Low | P0 | P100 within SLA | Not started
EXP-ACL-07 | Deleted / retired documents disappear from every path | All | Deletion | - | Delete in SP; retire KB article | DS-03 | Probe | Truth | - | - | Measure time until absent from retrieval, citations, caches, GCS copies | M-SEC-05, deletion lag | Within SLA | - | 2 | Low | P0 | Absent within SLA everywhere | Not started
EXP-ACL-08 | Missing/malformed ACL metadata fails closed | B-01 | Fail-closed | - | Inject docs with missing / malformed / stale ACL | DS-03 | Any user | Expect not returned | - | - | Fault injection | M-SEC-01 | Not retrievable by anyone | - | 1 | Low | P0 | Zero exposure | Not started
EXP-ACL-09 | No leakage via citations or inference from restricted docs | All | Answer channel | - | Queries designed to infer restricted facts; mixed authorised/unauthorised content | DS-03 + DS-05 | Adversarial | Truth | - | - | Red-team run as low-privilege user | M-SEC-03/04 | Zero disclosure | EXP-ACL-04 | 2 | Low | P0 | Zero tolerance | Not started
EXP-ACL-10 | Shared caches never serve another user's results | B-01 | Cache isolation | - | Enable caches | DS-03 | Same query by privileged then unprivileged user | Truth | - | - | Replay | M-SEC-11 | Zero leakage | EXP-40 | 1 | Low | P0 | Zero tolerance | Not started
EXP-ACL-11 | A2A agents cannot pass restricted content to other users' contexts | B-01 + ADK/A2A | Agent boundary | - | Multi-agent flow with restricted results | DS-03 | Agent scenarios | Truth | - | - | Attempt forwarding via A2A messages / shared state / memory | M-SEC-03 | Blocked | EXP-ACL-20 | 3 | Low | P0 | Zero tolerance | Not started
EXP-ACL-12 | Authoritative validation of top-N fits latency budget | B-01 (ENF-04) | Validation step | Pre-filter only | + Graph OBO / SN KM API checks on top-N | DS-03 + DS-01 | DS-02 sample | Truth | - | N = 5/10/20 | Measure added latency, throttling, error handling | M-SEC-07, M-PF-02 | Feasible for N<=10 (hypothesis) | ID-03, SN-03 | 4 | Low | P1 | Added P95 within budget; errors fail closed | Not started
EXP-ACL-13 | Reranker and query-processing services only see authorised candidates | B-01 | Reranker boundary | - | Instrument calls | DS-03 | Restricted-target queries | Truth | - | - | Inspect reranker request payloads in test | M-SEC-02 | Zero unauthorised in payloads | - | 1 | Low | P0 | Zero tolerance | Not started
EXP-ACL-14 | Dedup never merges content across different ACL sets | B-01 | Dedup boundary | - | Identical docs with different ACLs | DS-03 | Both users | Truth | - | - | Verify each user sees only own copy | M-SEC-01 | Correct | ING-12 | 1 | Low | P0 | Zero tolerance | Not started
EXP-ACL-15 | Logs, traces and metrics contain no restricted content | All | Observability | - | Run suite with log capture | DS-03 | All | - | - | - | Scan logs with DLP for fixture marker strings | Leak count | Zero | GCP-20 | 1 | Low | P0 | Zero restricted content in logs | Not started
EXP-ACL-16 | Concurrent users with different permissions get correct isolated results | B-01 | Concurrency + ACL | - | Parallel queries | DS-03 | Interleaved users | Truth | - | 50 parallel | Load test with assertions | M-SEC-01 | Zero cross-contamination | EXP-33 | 2 | Low | P0 | Zero tolerance | Not started
EXP-ACL-17 | Inherited vs unique SharePoint permissions are both honoured, incl. folder permission changes | B-01, A-01 | Inheritance | - | Break inheritance; change folder perms | DS-03 | Probe | Truth | - | - | Change folder permission; verify fan-out to all children | M-SEC-05/06 | Correct within SLA | SP-11 | 2 | Low | P0 | Zero false-allow | Not started
EXP-ACL-18 | ACL change without content change is detected | B-01 | ACL-only sync | - | Change permissions only | DS-03 | Probe | Truth | - | - | Measure detection lag | M-SEC-05 | Within SLA | ING-28 | 1 | Low | P0 | Within SLA | Not started
EXP-ACL-19 | Managed baseline honours ServiceNow user criteria and SharePoint sharing links as security expects | A-01 | Managed fidelity | - | Current connectors | DS-03 | Per-user | Truth | - | - | As EXP-ACL-01 on managed system | Discrepancies | Documented gaps (if any) | AQ-08 | 2 | Low | P0 | Gaps documented; decision if baseline itself is compliant | Not started
EXP-ACL-20 | End-user identity propagates ADK -> A2A -> RAG without spoofing | B-01 + ADK/A2A | Identity propagation | - | Token passing design | DS-03 | Spoof attempts | Truth | - | - | Try forged identity headers, replayed/expired tokens, service-account fallback | Spoof success count | Zero | ID-01 | 3 | Low | P0 | Zero successful spoofs; service account never used as end user | Not started
EXP-ACL-21 | Conflicting or stale permission records resolve to deny | B-01 | Conflict handling | - | Stale acl_updated_at; conflicting allow/deny | DS-03 | Probe | Expect deny | - | - | Fault injection | M-SEC-01 | Deny | - | 1 | Low | P0 | Deny in all cases | Not started

## 15_Metrics
Evaluation metrics - targets are HYPOTHESES to agree with the application team, except zero-tolerance security metrics
Metric ID | Category | Metric | Formula | Measurement method | Required test data | Interpretation | Limitations | Suggested acceptance criterion | Target type
M-RQ-01 | Retrieval quality | Recall@K | ¦relevant in top K¦ / ¦all relevant¦ (per query, averaged) | Offline run over golden set | DS-02 relevance labels | Coverage of evidence available to generator | Depends on label completeness (pooling) | Hypothesis: >= baseline A-01 on every stratum | Hypothesis - validate
M-RQ-02 | Retrieval quality | Precision@K | ¦relevant in top K¦ / K | Same | Same | Noise sent to LLM | Penalises queries with few relevant docs | Informational | Informational
M-RQ-03 | Retrieval quality | Hit Rate@K | share of queries with >= 1 relevant in top K | Same | Same | Simple sanity metric | Ignores rank and completeness | Hypothesis: >= baseline | Hypothesis - validate
M-RQ-04 | Retrieval quality | MRR | mean(1 / rank of first relevant) | Same | Same | How early first good result appears | Only first relevant counts | Informational | Informational
M-RQ-05 | Retrieval quality | NDCG@K | DCG@K / IDCG@K with graded gains (2^rel - 1) / log2(rank + 1) | Same | Graded labels 0-3 | Primary ranking metric | Needs graded labels | Hypothesis: >= baseline + agreed margin (gate G4) | Hypothesis - validate
M-RQ-06 | Retrieval quality | ANN Recall@K vs exact | ¦ANN top K intersect exact top K¦ / K | Same vectors, exact KNN ground truth | AX-01 ground truth | Isolates index loss from embedding quality | Not a relevance metric | Hypothesis: >= 0.95 at chosen config | Hypothesis - validate
M-RQ-07 | Retrieval quality | Relevant-document coverage | distinct relevant docs in top K / distinct relevant docs | Same | Doc-level labels | Diversity of evidence | - | Informational | Informational
M-RQ-08 | Retrieval quality | Filter correctness | results satisfying filter / results returned, and missed matches | Compare to SQL truth set | Filter test cases | Correct filter translation | - | 100% | Hard requirement
M-AQ-01 | Answer quality | Faithfulness / groundedness | supported claims / total claims | Claim extraction + entailment against context (human or calibrated judge; Check Grounding API score as signal) | Answers + contexts | Hallucination control | Judge errors; claim splitting variance | Hypothesis: >= baseline | Hypothesis - validate
M-AQ-02 | Answer quality | Answer relevance | judge score 1-5 vs question | Rubric-based judge + human sample | Reference answers | Is the question addressed | Verbosity bias | Hypothesis: >= baseline | Hypothesis - validate
M-AQ-03 | Answer quality | Context relevance / precision | relevant context chunks / context chunks | Labels or judge | Contexts | Context noise | - | Informational | Informational
M-AQ-04 | Answer quality | Citation correctness | citations that support their claim / citations | Human + judge | Expected evidence | FR-RET-02 | - | Hypothesis: >= 95% (validate) | Hypothesis - validate
M-AQ-05 | Answer quality | Citation coverage | claims with >= 1 valid citation / claims | Same | Same | Traceability | - | Hypothesis: >= 90% (validate) | Hypothesis - validate
M-AQ-06 | Answer quality | Completeness | covered reference facts / reference facts | Fact checklist per reference answer | Reference answers | Missing information | Needs good references | Hypothesis: >= baseline | Hypothesis - validate
M-AQ-07 | Answer quality | Unsupported-claim rate | unsupported claims / total claims | As M-AQ-01 | Same | Lower is better | - | Hypothesis: <= baseline | Hypothesis - validate
M-AQ-08 | Answer quality | Correct abstention rate | correct 'insufficient evidence' on unanswerable / unanswerable; plus false abstention on answerable | Run DS-05 unanswerable + answerable mix | Unanswerable labels | FR-RET-03 behaviour | Trade-off with helpfulness | Hypothesis: >= baseline with false abstention <= baseline | Hypothesis - validate
M-PF-01 | Performance | P50 latency | 50th percentile end-to-end and per stage | Cloud Trace spans per stage (auth, principal resolution, retrieval, rerank, generation) | Load/replay | Typical experience | Warm vs cold | Hypothesis per stage budget (AQ-07) | Hypothesis - validate
M-PF-02 | Performance | P95 latency | 95th percentile | Same | Same | Main SLO metric | Needs >= 1000 samples | Hypothesis (AQ-07) | Hypothesis - validate
M-PF-03 | Performance | P99 latency | 99th percentile | Same | Same | Tail behaviour | Noisy | Informational | Informational
M-PF-04 | Performance | Throughput / QPS | successful queries / second at P95 budget | Load test | DS-04 | Capacity | - | >= peak (AQ-07) x headroom | Hypothesis - validate
M-PF-05 | Performance | Ingestion throughput | documents (or pages) / hour end-to-end | Pipeline metrics | DS-04 | Re-index window feasibility | Bounded by source throttling | Full re-index within agreed window | Hypothesis - validate
M-PF-06 | Performance | Embedding throughput | tokens or chunks / second | Pipeline metrics | DS-04 | Quota planning | Quota-bound | Informational | Informational
M-PF-07 | Performance | Index build time | wall time to build index for N vectors | Platform metrics | DS-04 | Re-index agility | - | Informational | Informational
M-PF-08 | Performance | Index update / freshness time | time from source change to searchable | Probe documents | DS-01 | FR-GLO-06-like freshness | - | Within freshness SLA (AQ-11) | Hypothesis - validate
M-PF-09 | Performance | Resource utilisation | CPU/mem/GPU/DB utilisation at load | Cloud Monitoring | Load test | Right-sizing | - | Informational | Informational
M-PF-10 | Performance | Time to first token | time to first streamed token | Client-side timing | Streaming runs | FR-API-04 | - | Hypothesis | Hypothesis - validate
M-CO-01 | Cost & ops | Cost per document ingested | (extraction + parsing + embedding + indexing + storage cost for run) / docs | Billing export to BigQuery with labels per experiment | EXP-30 | Unit economics | Billing lag; shared resources | Informational | Informational
M-CO-02 | Cost & ops | Cost per embedding (per 1M tokens) | embedding spend / tokens embedded x 1e6 | Billing + token counts | EXP-30/42 | Managed vs self-hosted | - | Informational | Informational
M-CO-03 | Cost & ops | Cost per query | (retrieval + rerank + generation + infra share) / queries | Billing + request logs | Load tests | Run-rate | Fixed costs amortisation | Informational | Informational
M-CO-04 | Cost & ops | Cost per successful answer | cost / answers judged correct and grounded | Combine M-CO-03 with M-AQ | Golden set | Best value metric | - | Hypothesis: <= baseline | Hypothesis - validate
M-CO-05 | Cost & ops | Storage cost | GB x unit price per store | Billing | - | - | - | Informational | Informational
M-CO-06 | Cost & ops | Indexing cost | build/update charges + compute | Billing | - | - | - | Informational | Informational
M-CO-07 | Cost & ops | Generation cost | tokens in/out x unit price | Token counts | - | - | - | Informational | Informational
M-CO-08 | Cost & ops | Reranking cost | rerank requests x unit price or GPU hours | Billing | - | - | - | Informational | Informational
M-CO-09 | Cost & ops | Operational effort | engineer-hours per month for ops (sync failures, upgrades, incidents) | Time tracking during POC soak | - | TCO driver | POC underestimates prod | Informational | Informational
M-CO-10 | Cost & ops | Error rate | failed requests / requests | Logs | Load | Reliability | - | Hypothesis: < agreed SLO | Hypothesis - validate
M-CO-11 | Cost & ops | Availability | successful minutes / total minutes | Uptime checks | Soak | SLO | Short POC window | Hypothesis | Hypothesis - validate
M-CO-12 | Cost & ops | Recovery time (RTO) | time to restore service/index after failure | DR drill | Drill | DR readiness | - | Hypothesis (AQ-14) | Hypothesis - validate
M-SEC-01 | Security | Unauthorised retrieval rate | unauthorised docs returned by retrieval / test cases | Negative suite (EXP-ACL-04) | DS-03 truth table | Core security boundary | Only as good as test coverage | 0 (zero tolerance) | Zero tolerance
M-SEC-02 | Security | Unauthorised context inclusion rate | unauthorised chunks in LLM/reranker payloads / test cases | Payload inspection in test | DS-03 | Boundary before LLM | - | 0 (zero tolerance) | Zero tolerance
M-SEC-03 | Security | Unauthorised answer disclosure rate | answers revealing restricted facts / adversarial cases | Red-team + fixture marker strings | DS-03 + DS-05 | Inference leakage | Paraphrased leaks hard to detect - use unique marker facts | 0 (zero tolerance) | Zero tolerance
M-SEC-04 | Security | Citation authorisation failure rate | citations/links to unauthorised docs / citations | Automated | DS-03 | Link leakage | - | 0 (zero tolerance) | Zero tolerance
M-SEC-05 | Security | ACL synchronisation delay | time from source ACL change to index/policy store update (P50/P95/max) | Probe changes | DS-03 | Freshness of ACLs | - | Max <= revocation SLA (AQ-15) | Hard requirement (value To Confirm)
M-SEC-06 | Security | Permission revocation propagation time | time from revocation to no exposure on ALL paths (retrieval, cache, memory, citations) | EXP-ACL-05/06 | DS-03 | End-to-end revocation | - | Max <= revocation SLA | Hard requirement (value To Confirm)
M-SEC-07 | Security | Authorisation decision latency | added latency of principal resolution + validation | Trace spans | Load | Cost of security | - | Within stage budget | Hypothesis - validate
M-SEC-08 | Security | ACL metadata completeness | docs with valid, fresh ACL / indexed docs | Audit query | Full index | Must be 100% for indexed docs (others quarantined) | - | 100% | Hard requirement
M-SEC-09 | Security | ACL reconciliation discrepancy rate | docs whose stored ACL differs from source on full audit / docs audited | Nightly reconciliation | Full POC corpus | Drift detection | - | 0 false-allow discrepancies | Zero tolerance (false-allow)
M-SEC-10 | Security | Identity mapping coverage | users mapped across Entra / SP / SN / active users | Mapping table audit | Directory | Unmapped users get no source access | - | Informational (fail closed) | Informational
M-SEC-11 | Security | Cross-user cache leakage | cache hits served across different principal sets | EXP-ACL-10 | DS-03 | - | - | 0 (zero tolerance) | Zero tolerance
M-SEC-12 | Security | Prompt-injection success rate | successful injections / injection attempts | EXP-37 | DS-05 | - | - | 0 for data exfiltration | Zero tolerance (exfiltration)

## 15a_Datasets
Test datasets (sizes are hypotheses - confirm)
Dataset ID | Dataset | Contents | How to build | Size (hypothesis - confirm) | Owner | Sensitivity handling
DS-01 | POC corpus | Agreed SharePoint POC sites (2-5, mixed file types, both inherited and unique permissions) + ServiceNow KB subset (2-3 knowledge bases with varied user criteria) | Extract once into GCS raw zone; freeze a snapshot ID so every experiment uses identical content | 5k-50k documents (To Confirm - AQ-01/02) | Data engineering | Same controls as production data; CMEK bucket; restricted IAM
DS-02 | Golden query set | 300-500 queries stratified by source, doc type, query type (lookup, how-to, ID/acronym, multi-part, conversational, unanswerable) and app_id | Mine real queries from current app logs (with consent/redaction), SME-written questions, and LLM-drafted questions reviewed by SMEs; label relevant doc/chunk IDs with graded relevance (0-3) + expected evidence + reference answer | 300-500 (min 50 per major stratum) | Product + SMEs | Store queries without user identities
DS-03 | ACL test fixture corpus | Synthetic documents in a test SharePoint site and test ServiceNow KB with known permission matrix (unique perms, inheritance, SP groups, nested Entra groups, can/cannot-read criteria, scripted criteria, deleted, moved) | Create via admin scripts; record expected allow/deny truth table per test user | 50-200 docs, 10-20 test users | Security + platform admins | Synthetic content only - safe for logs
DS-04 | Scale corpus | DS-01 replicated/perturbed or synthetic up to target volume for ANN, ingestion and load tests | Duplicate with ID and light text perturbation; keep ACL distribution realistic | 1M / 10M chunks (To Confirm AQ-04) | Data engineering | Synthetic or masked
DS-05 | Adversarial & unanswerable set | Prompt-injection documents/queries, inference attempts on restricted docs, unanswerable questions | Security red team + SMEs | 100-200 | Security | Synthetic

## 15b_Golden_Set_Method
Golden dataset construction, human + automated evaluation, LLM-judge calibration
Step | Golden dataset construction step | Detail | Risk if skipped
GD-01 | Define strata | Source x doc type x query type x app_id; include acronym/jargon and unanswerable strata | Over-optimising for easy queries
GD-02 | Collect candidate queries | Real queries (redacted), SME-authored, LLM-generated then SME-reviewed | Synthetic-only bias
GD-03 | Pool candidates for labelling | Union of top-20 from baseline (A-01) + 2-3 custom variants (pooling as in TREC) to avoid baseline bias | Labels favour one system
GD-04 | Graded relevance labelling | 0 = irrelevant, 1 = related, 2 = relevant, 3 = answers fully; two annotators on 20% sample; compute agreement (Cohen kappa) | Noisy labels
GD-05 | Expected evidence + reference answer | Short reference answer and the spans that support it | Cannot score faithfulness/completeness
GD-06 | Per-user visibility labels | For ACL tests, mark which test users may see each relevant doc (DS-03) | Cannot measure leakage
GD-07 | Freeze and version | Golden set version id; never edit in place; changes = new version | Non-comparable results
GD-08 | Split | Dev split for tuning, held-out split for final decision (no tuning on it) | Overfitting to test set
GD-09 | Calibrate LLM judge | Compare LLM-as-judge scores with human labels on 100+ items; report agreement; fix rubric; re-calibrate on model change | Judge bias (verbosity, position, self-preference) silently skews results

## 16_Risks
Risk register - Severity = Likelihood x Impact
Risk ID | Category | Description | Likelihood (1-5) | Impact (1-5) | Mitigation | Validation test | Owner | Residual risk | Severity (calc) | Rating (calc)
R-01 | ACL | Stale permissions: ACL changes not synced before user queries | 4 | 5 | ACL-only sync; TTL caches; authoritative top-N validation; fail closed on stale acl_updated_at | EXP-ACL-05/06/18 | Security architect | Medium until SLA proven
R-02 | ACL | Identity mismatch between Entra, SharePoint and ServiceNow users | 3 | 5 | Identity map with coverage reporting; unmapped = no access | SRC-12, M-SEC-10 | Identity team | Low
R-03 | ACL | Incomplete inheritance handling (folder/site permission changes, broken inheritance) | 4 | 5 | Scope-based ACL references with fan-out; nightly reconciliation | EXP-ACL-17 | Data engineering | Medium
R-04 | ACL | Unauthorised retrieval due to filter bug or engine post-filtering | 2 | 5 | Server-side injected filters; negative test suite in CI; defence-in-depth validation | EXP-ACL-04 | RAG team | Low
R-05 | ACL | Cross-user cache leakage | 3 | 5 | Cache keys include principal-set hash + acl_versions; per-user conversation memory | EXP-ACL-10 | RAG team | Low
R-06 | ACL | A2A data leakage: agents forward restricted content to other users' sessions or agents | 3 | 5 | Identity-bound tool results; no shared state across users; A2A auth; output filtering | EXP-ACL-11 | Agent team | Medium
R-07 | ACL | Permission revocation delay exceeds acceptable window | 3 | 5 | Agree SLA (AQ-15); design TTLs to SLA; monitor M-SEC-06 | EXP-ACL-05 | Security | Medium
R-08 | ACL | ServiceNow scripted user criteria cannot be replicated statically | 4 | 4 | Index criteria IDs; evaluate matches per user in ServiceNow; requires_source_check flag | EXP-ACL-06, SRC-09 | ServiceNow team | Medium
R-09 | ACL | SharePoint sharing links / special claims mis-modelled (over-grant) | 3 | 5 | Conservative default (do not grant on org links) pending security decision | EXP-ACL-01 | Security | Low
R-10 | ACL | Managed baseline itself has ACL fidelity gaps | 2 | 5 | Measure baseline with same negative suite | EXP-ACL-19 | Security | Unknown until tested
R-11 | Security | Prompt injection from retrieved documents | 4 | 4 | Treat retrieved text as data; Model Armor; tool allow-lists; no tool execution from content | EXP-37 | RAG team | Medium
R-12 | Security | Malicious or malformed documents (parser exploits, zip bombs) | 2 | 4 | Sandboxed parsing; size/type limits; scanning | Fuzz sample | Data engineering | Low
R-13 | Security | PII exposure in answers or logs | 3 | 5 | DLP per data set; no content in logs; restricted log buckets | EXP-ACL-15 | Security | Low
R-14 | Security | Sensitive-data retention in GCS copies / embeddings after source deletion | 3 | 4 | Deletion propagation incl. GCS + caches; retention policies | EXP-ACL-07 | Data engineering | Low
R-15 | Security | Secret leakage (Graph cert, ServiceNow OAuth) | 2 | 5 | Secret Manager, rotation, no keys in code, VPC-SC | Audit | Security | Low
R-16 | Security | Over-privileged ingestion identity used for user queries | 2 | 5 | Separate SAs/app registrations; code review gate; tests | EXP-ACL-20 | RAG team | Low
R-17 | Security | Logging of sensitive content by frameworks (ADK, LangChain debug) | 3 | 4 | Disable payload logging; log scanning | EXP-ACL-15 | SRE | Low
R-18 | Governance | Data residency violation (model/region outside policy) | 2 | 5 | Pin regions; org policy resourceLocations; check model locations | GCP-18 | Cloud platform | Low
R-19 | Governance | Citation integrity: citations to wrong or unauthorised docs | 3 | 4 | Re-validate cited IDs; citation tests | EXP-23, EXP-ACL-09 | RAG team | Low
R-20 | Governance | Model access restrictions (unapproved models/providers used) | 2 | 3 | Allow-list per app_id (FR-CFG-02) | Config tests | Platform | Low
R-21 | Quality | Hallucination despite grounding | 3 | 4 | Grounding check, abstention, eval gate | EXP-22 | RAG team | Medium
R-22 | Quality | Retrieval failures on jargon/acronyms | 4 | 3 | Hybrid + glossary | EXP-04/16 | RAG team | Low
R-23 | Quality | Poisoned or low-quality source content | 3 | 3 | Source allow-lists; workflow_state=published; feedback loop | Feedback review | Content owners | Medium
R-24 | Quality | Golden set unrepresentative -> wrong decision | 3 | 4 | Stratified sampling; pooled labels; held-out split | GD-01..08 | Product | Medium
R-25 | Quality | Uncalibrated LLM judge biases results | 3 | 4 | Calibrate vs humans (GD-09) | Agreement report | Evaluation lead | Low
R-26 | Operations | Index inconsistency between vector, keyword and ACL stores | 3 | 5 | Single-store design or outbox + consistency checker | EXP-ACL-03 | RAG team | Low
R-27 | Operations | Source API throttling blocks ingestion and ACL sync | 4 | 3 | Back-off, off-peak windows, Sites.Selected scoping, agreed rate limits | EXP-30 | Data engineering | Medium
R-28 | Operations | Service outages (Vertex, Graph, ServiceNow) | 2 | 4 | Retries; degrade to fail-closed; status communication | Chaos test | SRE | Medium
R-29 | Operations | Rate limits / quotas on embeddings & Gemini | 4 | 3 | Quota requests early; batching; backoff | GCP-12 | Platform | Low
R-30 | Operations | Backup/restore gaps for custom stores | 2 | 3 | Backups + rebuild from GCS parsed zone | DR drill | DBA | Low
R-31 | Cost | Cost overruns (always-on endpoints, GPU, re-indexing) | 3 | 3 | Budgets/alerts; tear-down scripts; cost per experiment labels | M-CO metrics | FinOps | Low
R-32 | Strategy | Vendor lock-in (managed relevance, proprietary indexes) | 3 | 3 | Keep source of truth in GCS/PostgreSQL; portable embeddings | Decision matrix | Architect | Medium
R-33 | Strategy | OSS library maintenance / abandonment | 3 | 3 | Prefer widely adopted, permissive-licence projects; pin + monitor | Quarterly review | Architect | Low
R-34 | Strategy | Model deprecation forces re-embedding | 4 | 3 | Store embedding_model_version; blue/green re-index runbook; budget for re-embed | ING-22 | ML platform | Medium
R-35 | Strategy | ADK 2.0.3 incompatibilities (A2A auth headers, part conversion fixed in later 2.x) | 3 | 3 | Verify against 2.0.3; plan upgrade to latest 2.x if needed | EXP-41 | Agent team | Medium
R-36 | Strategy | Custom build cannot reach parity with managed connectors/ACLs in time | 4 | 4 | Hybrid options (AP-A2, AP-D); decision gates | Roadmap gates | Architect | Medium
R-37 | ACL | Conflicting or stale permission records treated as allow | 2 | 5 | Deny-on-conflict rule; status field | EXP-ACL-21 | RAG team | Low
R-38 | ACL | Encrypted/labelled files (sensitivity labels) indexed without label semantics | 3 | 4 | Exclude labelled/encrypted files until policy defined | SP-12 | Security | Low

## 17_Cost_Capacity
Configurable cost & capacity model (NOT a quotation)
Yellow = inputs (replace placeholders with confirmed values - AQ-04/07). Grey = formulas. Unit prices must be copied from the linked official pricing page; billing units differ by provider.
INPUT ASSUMPTIONS
Key | Input | Value | Source / owner
n_docs | Number of source documents | 50000 | AQ-04
avg_doc_mb | Average document size (MB) | 0.5 | AQ-04
avg_pages | Average pages per document (for parsing cost) | 8 | AQ-05
avg_text_tokens | Average extracted text per document (tokens) | 3000 | Profile DS-01
chunk_tokens | Chunk size (tokens) | 512 | EXP-09
overlap | Chunk overlap (fraction 0-1) | 0.1 | EXP-10
dims | Embedding dimensions | 768 | EXP-03
bytes_dim | Bytes per dimension (4 float32, 2 halfvec, 1 int8) | 4 | AX-07
idx_overhead | Index overhead factor vs raw vectors (hypothesis, e.g. HNSW graph) | 1.5 | Measure in AX-02
replicas | Replication / redundancy factor | 2 | HA design
meta_bytes | Metadata + ACL bytes per chunk | 2000 | Sheet 21
batch | Embedding batch size (inputs per request) | 1 | Model limit (EMB sheet)
reproc_docs | Documents re-processed per month | 5000 | AQ-10
daily_q | Daily query volume | 5000 | AQ-07
peak_conc | Peak concurrency (queries in flight) | 20 | AQ-07
cand | Retrieval candidate count per query | 50 | EXP-19
rerank_n | Reranking candidates per query | 50 | EXP-19
ctx_tokens | Average prompt/context tokens per answer | 6000 | EXP-21
gen_tokens | Average generated tokens per answer | 500 | EXP-21
answer_share | Share of queries that call Answer (0-1) | 0.6 | AQ-09
retention_days | Retention period for logs/eval data (days) | 90 | Policy
eng_weeks | Engineering effort for chosen option (person-weeks) | 0 | Roadmap / decision
eng_rate | Blended engineering cost per person-week | 0 | Finance
DERIVED WORKLOAD (formulas)
Key | Derived quantity | Value | Formula basis
src_gb | Total source data (GB) |  | docs x MB / 1024
chunks_doc | Chunks per document |  | tokens / (chunk x (1-overlap))
chunks | Total chunks |  | docs x chunks/doc
emb_tokens | Initial embedding tokens |  | chunks x chunk tokens
emb_requests | Initial embedding requests |  | chunks / batch
reemb_tokens | Monthly re-embedding tokens |  | re-processed docs x chunks/doc x chunk tokens
vec_gb | Raw vector storage (GB) |  | chunks x dims x bytes / 1e9
idx_gb | Index storage incl. overhead & replicas (GB) |  | raw x overhead x replicas
txt_gb | Chunk text + metadata storage (GB, ~4 bytes/token) |  | chunks x (tokens x 4 + meta) / 1e9
pages | Pages to parse (initial) |  | docs x pages
pages_m | Pages to parse per month (re-processing) |  | re-processed docs x pages
q_month | Queries per month |  | daily x 30
rr_month | Rerank records per month |  | queries x rerank candidates
ans_month | Answers per month |  | queries x answer share
gin_month | Generation input tokens per month |  | answers x context tokens
gout_month | Generation output tokens per month |  | answers x generated tokens
eng_cost | Engineering cost (one-time) |  | weeks x rate
COST COMPONENTS (unit price = INPUT from official page; blank = not yet verified)
Component | Applies to architectures | Cost type | Billing unit (verify on page) | Quantity per unit basis | Unit price (INPUT) | Estimated cost | Official pricing source
Embedding - initial corpus | B-*, C-07, D-* | One-time POC | per 1M input tokens (or per 1k chars - convert) |  |  |  | https://cloud.google.com/vertex-ai/generative-ai/pricing
Embedding - monthly re-processing | B-*, D-* | Ongoing monthly | per 1M input tokens |  |  |  | https://cloud.google.com/vertex-ai/generative-ai/pricing
Gemini input tokens | All custom generation | Ongoing monthly | per 1M input tokens (model-specific) |  |  |  | https://cloud.google.com/vertex-ai/generative-ai/pricing
Gemini output tokens | All custom generation | Ongoing monthly | per 1M output tokens (model-specific) |  |  |  | https://cloud.google.com/vertex-ai/generative-ai/pricing
Ranking API | A-03, B-*, D-* | Ongoing monthly | per 1k ranking records/requests - verify unit |  |  |  | https://cloud.google.com/generative-ai-app-builder/pricing
Vertex AI Search queries | A-*, D-01, D-02 | Ongoing monthly | per 1k queries (edition-specific) |  |  |  | https://cloud.google.com/generative-ai-app-builder/pricing
Vertex AI Search index storage | A-*, D-01, D-02 | Ongoing monthly | per GiB-month |  |  |  | https://cloud.google.com/generative-ai-app-builder/pricing
Vector Search serving nodes | B-05, B-06 | Ongoing monthly | per node-hour (machine type) x hours | 730 |  |  | https://cloud.google.com/vertex-ai/pricing
Vector Search index build/update | B-05, B-06 | One-time + monthly | per GiB processed |  |  |  | https://cloud.google.com/vertex-ai/pricing
AlloyDB compute | B-01..B-03, B-11, C-07, D-01 | Ongoing monthly | per vCPU-hour + GB-hour (enter blended per-hour price) | 730 |  |  | https://cloud.google.com/alloydb/pricing
AlloyDB storage | B-01..B-03, B-11, C-07, D-01 | Ongoing monthly | per GB-month |  |  |  | https://cloud.google.com/alloydb/pricing
Cloud SQL instance | B-04 | Ongoing monthly | per instance-hour (blended) | 730 |  |  | https://cloud.google.com/sql/pricing
Document AI parsing - initial | B-*, C-*, D-* | One-time POC | per 1k pages (processor-specific) |  |  |  | https://cloud.google.com/document-ai/pricing
Document AI parsing - monthly | B-*, C-*, D-* | Ongoing monthly | per 1k pages |  |  |  | https://cloud.google.com/document-ai/pricing
Cloud Storage (raw + parsed zones) | All custom | Ongoing monthly | per GB-month (class/region) |  |  |  | https://cloud.google.com/storage/pricing
BigQuery (eval / audit / ground truth) | B-08 + evaluation | Ongoing monthly | per TiB scanned or slot-hours | 1 |  |  | https://cloud.google.com/bigquery/pricing
Cloud Run (RAG API + jobs) | B-*, D-* | Ongoing monthly | per vCPU-s / GiB-s / requests (enter monthly estimate) | 1 |  |  | https://cloud.google.com/run/pricing
GKE + GPU nodes (self-hosted models/stores) | C-*, E-*, B-06, B-11 | Ongoing monthly | per node-hour / GPU-hour | 730 |  |  | https://cloud.google.com/kubernetes-engine/pricing
Third-party subscription (Elastic / Qdrant / Weaviate Cloud) | C-02, C-01, C-04 | Ongoing monthly | vendor-specific | 1 |  |  | Vendor pricing page - To Verify
Engineering effort | Chosen option | One-time | person-weeks x rate |  | 1 |  | Internal
Total one-time POC (entered prices only)
Total ongoing monthly (entered prices only)
Peak capacity check
Required QPS at peak (approx. = concurrency / P95 seconds) | P95 latency target (s) - INPUT | 3

## 18_Roadmap
POC roadmap - baseline and ACL gate before any advanced technique
Phase ID | Phase | Objectives | Tasks | Deliverables | Prerequisites | Dependencies | Estimated effort (indicative, person-weeks) | Responsible role | Entry criteria | Exit criteria | Risks | Decision gate
PH-01 | Discovery & requirements confirmation | Resolve critical unknowns | Workshops: data scope, ACL semantics, revocation SLA, latency/quality targets, residency; review Eva FRs | Signed assumptions log (sheet 20); in-scope sites/KBs | Stakeholder availability | - | 2 | Solution architect + product owner | Sponsor approval | All P0 'To Confirm' items resolved or owned | Scope creep | G0: proceed with POC scope
PH-02 | Access & environment readiness | Get every access needed before engineering starts | Execute checklist sheet 12 (GCP + SharePoint/Entra + ServiceNow) | POC project, SAs, apps, secrets, networking | PH-01 | Security, M365, ServiceNow teams | 2-4 (elapsed, mostly waiting) | Cloud platform lead | G0 passed | All 'High' blockers closed | Approval lead times | G1: environment ready
PH-03 | Baseline measurement | Quantify current managed RAG | EXP-00, EXP-ACL-19; document current config | Baseline report | PH-02, DS-02 draft | Discovery Engine access | 1-2 | RAG engineer + evaluation lead | G1 | Baseline metrics reproducible | Baseline config opaque | -
PH-04 | Representative dataset & golden set | Build DS-01..DS-05 | GD-01..GD-09 | Versioned datasets + labelling guide | PH-01 | SMEs | 2-3 (parallel with PH-02/03) | Evaluation lead + SMEs | G0 | Golden set v1 frozen; judge calibrated | SME time | -
PH-05 | Minimal custom RAG + ACL foundation | Thinnest end-to-end slice: extract -> ACL -> chunk -> embed -> AlloyDB hybrid -> Gemini, exposed as ADK tool | Implement B-01 with CHK-05/06, EMB-01@768; ACL model sheet 21; ENF-04 | Working slice + ACL negative suite in CI | PH-02 | PH-04 for eval | 3-4 | RAG engineers (2) + data engineer | G1 | EXP-ACL-01..04, 08, 10, 13, 20 pass | ACL extraction complexity | G2: ACL gate - any failure stops quality work
PH-06 | Embedding & chunking experiments | Find best model/chunking on our corpus | EXP-01, 03, 04, 06..10, 32 | Results + chosen config | G2 | Quotas | 2 | RAG engineer | G2 | Winners selected with significance | Confounded variables | -
PH-07 | Retrieval & ANN optimisation | Tune ANN under ACL filters | EXP-11, 12, 39; AX sheet | ANN config per platform | PH-06 | DS-04 | 2 | RAG engineer | PH-06 done | Filtered recall + P95 targets met | Filter-recall cliff | -
PH-08 | Hybrid search & reranking | Measure hybrid + rerank gains | EXP-13, 15, 16, 19, 21, 22, 23, 29; A-02/A-03 managed variants | Best pipeline config | PH-07 | Ranking API | 2 | RAG engineer | PH-07 done | Configuration frozen for comparison | - | G3: custom vs managed-improved comparison set
PH-09 | Advanced RAG (only problem-triggered) | Fix residual measured gaps | Select from EXP-17, 18, 20, 25..28 based on failure analysis | Targeted improvements | G3 | - | 1-3 | RAG engineer | Documented failure category | Gain or rejection recorded | Complexity creep | -
PH-10 | Performance, security & cost validation | Prove non-functional fitness | EXP-30, 31, 33, 34, 36, 37, 41, 42; remaining EXP-ACL-*; DR drill | NFR evidence pack; cost model with measured values | PH-08 | Load tooling | 2-3 | SRE + security + RAG | G3 | All zero-tolerance security metrics = 0 | Prod-unrepresentative load | -
PH-11 | Results review & architecture decision | Decide managed / hybrid / custom | EXP-35 held-out comparison; decision matrix (sheet 19); ADR | Architecture Decision Record + migration plan | PH-10 | All | 1 | Principal architect + sponsors | All prior gates passed | Decision recorded in log | Bias to sunk cost | G4: architecture decision

## 19_Decision_Matrix
Architecture decision matrix
Scores 1-5 (5 = most favourable). Block 1 = PRELIMINARY expert assessment (orange). Block 2 = MEASURED POC scores (fill in). Any 'Fail' gate => EXCLUDED regardless of score.
Mandatory gate | Description | Weight | A-01 | A-03 | B-01 | B-05 | C-02 | D-01 | D-03 | Evidence references | Confidence
Mandatory: zero unauthorised exposure on full ACL negative suite (EXP-ACL-*) |  |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Sheets 14, 20
Mandatory: data residency compliant (AQ-13) |  |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Sheets 14, 20
Mandatory: integrable with ADK 2.0.3 / A2A with end-user identity (EXP-41, EXP-ACL-20) |  |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Sheets 14, 20
Mandatory: operational owner assigned (AQ-24) |  |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Sheets 14, 20
Preliminary expert assessment | Description | Weight | A-01 | A-03 | B-01 | B-05 | C-02 | D-01 | D-03 | Evidence references | Confidence
Retrieval quality | NDCG/Recall on golden set | 12 | 3 | 4 | 3 | 3 | 3 | 4 | 2 | Expert judgement - see sheets 03, 07, 21b | Low
Answer quality | Faithfulness, completeness, citations | 12 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | Expert judgement - see sheets 03, 07, 21b | Low
Latency | P95 end-to-end | 8 | 4 | 3 | 3 | 4 | 3 | 3 | 1 | Expert judgement - see sheets 03, 07, 21b | Low
Scalability | Corpus + QPS growth | 6 | 4 | 4 | 3 | 5 | 4 | 3 | 2 | Expert judgement - see sheets 03, 07, 21b | Low
Cost | Run-rate cost per successful answer (5 = cheapest) | 8 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | Expert judgement - see sheets 03, 07, 21b | Low
Operational complexity | 5 = simplest to operate | 8 | 5 | 4 | 2 | 2 | 2 | 2 | 3 | Expert judgement - see sheets 03, 07, 21b | Low
Security (ACL fidelity) | Confidence in faithful source permission enforcement | 14 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | Expert judgement - see sheets 03, 07, 21b | Low
Data governance | Lineage, residency, audit | 6 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | Expert judgement - see sheets 03, 07, 21b | Low
Customisation flexibility | Control of chunking/embedding/ranking | 5 | 1 | 3 | 5 | 4 | 5 | 4 | 2 | Expert judgement - see sheets 03, 07, 21b | Low
Integration with ADK and A2A | Effort and fit | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | Expert judgement - see sheets 03, 07, 21b | Low
Migration effort | 5 = least effort | 5 | 5 | 4 | 2 | 2 | 2 | 2 | 3 | Expert judgement - see sheets 03, 07, 21b | Low
Maintainability | Long-term code/ops burden | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 3 | Expert judgement - see sheets 03, 07, 21b | Low
Vendor lock-in | 5 = least lock-in | 3 | 2 | 2 | 4 | 3 | 4 | 3 | 4 | Expert judgement - see sheets 03, 07, 21b | Low
Reliability | Availability, failure isolation | 4 | 4 | 4 | 3 | 4 | 3 | 3 | 2 | Expert judgement - see sheets 03, 07, 21b | Low
Weighted score (preliminary)
Measured POC scores | Description | Weight | A-01 | A-03 | B-01 | B-05 | C-02 | D-01 | D-03 | Evidence references | Confidence
Retrieval quality | NDCG/Recall on golden set
Answer quality | Faithfulness, completeness, citations
Latency | P95 end-to-end
Scalability | Corpus + QPS growth
Cost | Run-rate cost per successful answer (5 = cheapest)
Operational complexity | 5 = simplest to operate
Security (ACL fidelity) | Confidence in faithful source permission enforcement
Data governance | Lineage, residency, audit
Customisation flexibility | Control of chunking/embedding/ranking
Integration with ADK and A2A | Effort and fit
Migration effort | 5 = least effort
Maintainability | Long-term code/ops burden
Vendor lock-in | 5 = least lock-in
Reliability | Availability, failure isolation
Weighted score (measured)

## 20_Assumptions_Log
Assumptions, open questions & decision log - no values silently assumed
Item ID | Area | Item / question | Current assumption (if any) | Impact if wrong | How to resolve | Owner | Priority | Status | Decision / answer | Decision date
AQ-01 | SharePoint scope | Which SharePoint tenant, sites, libraries, lists and pages are in scope for the POC and for production? | 2-5 representative POC sites | Wrong corpus = unrepresentative results | Site inventory workshop with content owners | Product owner | P0 | To Confirm | - | -
AQ-02 | ServiceNow scope | Which instance, knowledge bases and tables beyond kb_knowledge (catalog items, resolved incidents)? (FR-CON-02 open question) | KB articles only in phase 1 | Incidents add PII + different ACLs | Workshop with ServiceNow owners | Product owner | P0 | To Confirm | - | -
AQ-03 | ServiceNow ACLs | Which record ACLs, data filtration, domain separation and scripted user criteria apply to in-scope KBs? | Some scripted criteria exist | Static ACL model under/over-grants | Export criteria + ACL configuration | ServiceNow team | P0 | To Confirm | - | -
AQ-04 | Volume | Document counts, sizes, growth rate per source (current + 2-year) | Unknown | ANN/store sizing and cost model | Source analytics reports | Data engineering | P0 | To Confirm | - | -
AQ-05 | Document types | File-type mix; share of scanned PDFs, tables, images, code | Mixed Office/PDF/HTML | Parser and chunking choices | Sample profiling of POC sites | Data engineering | P1 | To Confirm | - | -
AQ-06 | Languages | Which languages appear in content and queries? | Mostly English | Embedding model selection | Language detection on sample | Data engineering | P1 | To Confirm | - | -
AQ-07 | Load | Daily query volume, peak concurrency, latency objectives (P95) for Search and Answer APIs | Unknown | Capacity, cost, architecture | NFR sheet in Eva workbook + traffic logs | Product owner | P0 | To Confirm | - | -
AQ-08 | Current baseline | Exact Discovery Engine configuration: app type, data stores, connectors (mode), parser/chunking settings, ACL enabled?, WIF config, serving controls | Gemini Enterprise / Vertex AI Search with ACL-enabled connectors | Baseline misunderstood | Export configs via API; interview app team | App team | P0 | To Confirm | - | -
AQ-09 | Baseline usage | Which APIs are used today (search, answer, conversational), with what parameters? Is embedding/retrieval behaviour exposed? | Search + Answer | Baseline comparisons invalid | Code review of current app | App team | P1 | To Confirm | - | -
AQ-10 | Update frequency | Content change rate and required re-index window | Daily changes; weekly full reconciliation acceptable | Ingestion design | Source change analytics | Data engineering | P1 | To Confirm | - | -
AQ-11 | Freshness | Required content freshness SLA (time from edit to searchable) | Hours (FR-GLO-06 uses 15 min for glossary) | Batch vs streaming | Product decision | Product owner | P1 | To Confirm | - | -
AQ-12 | Data sensitivity | Data classification of in-scope content; PHI/PII presence; sensitivity labels/encryption | Confidential internal | DLP, logging, residency controls | Data classification review | Security / privacy | P0 | To Confirm | - | -
AQ-13 | Residency | Allowed GCP regions for data, models and processing | To Confirm | Model availability may differ by region | Compliance team | Compliance | P0 | To Confirm | - | -
AQ-14 | DR | RTO/RPO expectations | To Confirm | Store and backup choices | NFR review | SRE | P2 | To Confirm | - | -
AQ-15 | Revocation SLA | Maximum acceptable delay between permission revocation at source and enforcement in RAG | Must be explicit; no default assumed | Drives TTLs, sync cadence and need for live validation | Security team decision | Security architect | P0 | To Confirm | - | -
AQ-16 | Encryption | Is CMEK mandatory? Key location requirements? | To Confirm | Service eligibility | Security policy | Security | P1 | To Confirm | - | -
AQ-17 | Identity propagation | How does the end-user identity reach the current app and agents (token type, audience, groups claim)? | Entra ID tokens at the front-end | Cannot enforce per-user ACL | Review auth flow end to end | Identity + app team | P0 | To Confirm | - | -
AQ-18 | Identity mapping | Join key between Entra users and ServiceNow sys_user (FR-SEC-02 open question); mapping for SharePoint principals | Email/UPN | Unmapped users lose access or mis-map | Data comparison | Identity team | P0 | To Confirm | - | -
AQ-19 | Sharing links | Must SharePoint sharing-link permissions be honoured? (FR-CON-01 open question) | Not honoured for org-wide links (fail closed) until decided | Over/under-exposure | Security decision | Security architect | P0 | To Confirm | - | -
AQ-20 | ADK runtime | Where do ADK 2.0.3 agents run today (Agent Engine, Cloud Run, GKE)? Which A2A SDK/spec version? How are tools authenticated? | Unknown | Integration design | Review agent repo | Agent team | P1 | To Confirm | - | -
AQ-21 | API access | Is Graph application access (Sites.Selected) and ServiceNow OAuth integration approved for the POC? | Pending | Blocks custom options | Raise access requests early | Security + platform | P0 | To Confirm | - | -
AQ-22 | Budget | POC budget envelope and constraints on always-on resources / GPUs | To Confirm | Scope of experiments | Sponsor | Sponsor | P1 | To Confirm | - | -
AQ-23 | Deployment restrictions | Allowed compute (Cloud Run vs GKE), external SaaS (Elastic Cloud, Qdrant Cloud), OSS licences | GCP-native preferred | Option shortlist | Architecture board | Architect | P1 | To Confirm | - | -
AQ-24 | Ownership | Who will operate a custom RAG platform (on-call, upgrades, connector maintenance)? | No team assigned | Custom option may be infeasible regardless of quality | Org decision | Engineering manager | P0 | To Confirm | - | -
AQ-25 | Managed dependency tolerance | Which managed dependencies are acceptable long-term (Discovery Engine, Vector Search, Ranking API)? | Vertex AI acceptable | Option shortlist | Architecture board | Architect | P1 | To Confirm | - | -
AQ-26 | Quality bar | What improvement over baseline justifies migration (gate G4 margin)? | To Confirm (e.g. NDCG@10 + X points) | Decision without criteria | Sponsor + product | Product owner | P0 | To Confirm | - | -
AQ-27 | Other sources | Cloud SQL, BigQuery, Cloud Storage connectors (FR-CON-03..05) in scope for later phases? | Later phase | Architecture must not preclude | Roadmap review | Product owner | P2 | To Confirm | - | -
AQ-28 | Multi-tenancy | How many app_ids, and do any require isolation beyond data-set entitlement (FR-CFG-06)? | Few app_ids | Index partitioning design | Client inventory | Product owner | P1 | To Confirm | - | -
AQ-29 | Product naming | Is the baseline 'Gemini Enterprise' (app) on top of Vertex AI Search data stores, both via discoveryengine.googleapis.com? | Yes - same API family | Wrong API comparisons | Check app type in console | App team | P1 | To Confirm | - | -
AQ-30 | ADK version | Confirm ADK 2.0.3 is pinned in production and whether upgrade to later 2.x is acceptable | 2.0.3 pinned | A2A fixes in later versions unavailable | Check requirements lock file | Agent team | P1 | To Confirm | - | -

## 21_ACL_Data_Model
ACL-aware schema (adapt to chosen store; complex semantics kept in policy store)
Field | Level | Type | SharePoint source | ServiceNow source | Semantics / notes | Required | Stored in retrieval index?
document_id | Document | string (internal UUID) | Generated | Generated | Internal stable key | Yes | Yes
source_system | Document | enum (sharepoint, servicenow) | Constant | Constant | Drives source-specific rules | Yes | Yes
source_document_id | Document | string | driveId + itemId (or listId + itemId) | sys_id | Stable across renames | Yes | Yes
source_url | Document | url | webUrl (refresh on move) | instance URL + kb_view.do?sys_kb_id= | Deep link for citations (FR-API-01) | Yes | Yes (returned only after ACL check)
content_version | Document | string | eTag / version label | sys_mod_count / version | Replace chunks atomically | Yes | Yes
owner | Document | principal | createdBy / owner field | author / ownership group | Informational; not an access grant unless source says so | No | No
allowed_principal_ids | Document | array<string> | Entra users/groups, SP groups (sp:group:<siteId>:<id>), special claims | sn:uc:<criteria sys_id> (can-read), roles/groups only if materialised | Union of effective read grants after inheritance | Yes | Yes (filter field)
denied_principal_ids | Document | array<string> | Usually empty | sn:uc:<criteria sys_id> (cannot-read) | Deny overrides allow | Yes (may be empty) | Yes (exclusion filter)
visibility_class | Document | enum (restricted, org_wide, public) | Derived from claims like 'Everyone except external users' | KB with no criteria + instance default - To Verify | Never default to org_wide on missing data | Yes | Yes
source_acl_reference | Document | string | Permission scope id (site / list / folder with unique perms) | KB sys_id + criteria ids | Lets ACL changes on a container fan out to documents | Yes | No (policy store)
inheritance_metadata | Document | json | hasUniqueRoleAssignments, inheritedFrom path | KB-level vs article-level criteria | Explains effective ACL; supports audit | Yes | No (policy store)
requires_source_check | Document | bool | true if unsupported link types / labels | true if any criteria uses advanced script or record ACLs restrict | Forces authoritative validation before LLM | Yes | Yes
acl_version | Document | int / hash | Hash of normalised ACL | Hash of normalised ACL | Cache keys + revocation invalidation | Yes | Yes
content_updated_at | Document | timestamp | lastModifiedDateTime | sys_updated_on | Freshness metric | Yes | Yes
acl_updated_at | Document | timestamp | Time ACL last extracted | Time ACL last extracted | Stale ACL detection (fail closed if older than SLA) | Yes | Yes
synchronization_status | Document | enum (ok, stale, failed, quarantined, deleted) | Sync job | Sync job | Anything but 'ok' is excluded from retrieval | Yes | Yes
chunk_id | Chunk | string | hash(document_id, content_version, idx) | same | Idempotent upserts | Yes | Yes
chunk_text | Chunk | text | Parsed content | Parsed article text | Never logged in plaintext (FR-SEC-08) | Yes | Yes
document_metadata | Chunk | json | title, site, library, path, type, modified, language | KB, category, workflow_state, language | Filters (FR-FLT-01) | Yes | Yes
parent_chunk_id | Chunk | string | Parent-child chunking | same | Parent must belong to same document (same ACL) | If CHK-10 | Yes
principal_membership | Principal | table (principal_id, member_principal_id, source, updated_at) | SP group members; Entra nested groups | sys_user_grmember, roles | Used to expand a user into effective principal set | Yes | No (policy store / cache)
user_criteria_match | Principal | table (user_id, criteria_id, evaluated_at) | n/a | Evaluated in ServiceNow per user (handles scripts) | TTL-bound; drives sn:uc tokens per user | Yes | No (cache)
identity_map | Principal | table (entra_oid, upn, sp_login, sn_sys_id) | Entra oid | sys_user mapping | Unmapped = no access to that source | Yes | No

## 21a_ACL_Pipeline
ACL propagation & enforcement at every stage (fail closed)
Stage | What carries the ACL | Control | Failure behaviour (fail closed) | Test ID
Source extraction | Permission snapshot captured in same run as content (or ACL-only run) | Reject documents whose ACL extraction failed | Quarantine document; not indexed | EXP-ACL-01 / EXP-ACL-08
Document parsing | document_id + acl_version passed alongside parsed JSON | Parser cannot drop ACL fields (schema validation) | Quarantine | EXP-ACL-08
Content normalisation | Same | Dedup never merges across different acl_version sets | Keep separate copies | EXP-ACL-14
Chunking | Chunks reference document_id; ACL looked up (or copied atomically) from document | Chunk without resolvable document ACL is invalid | Not indexed | EXP-ACL-02
Embedding generation | No ACL needed by model; only authorised ingestion SA calls Vertex | Embedding requests contain text only; no logging of text | n/a | -
Vector & keyword indexing | allowed/denied principal fields + synchronization_status on every row in BOTH vector and keyword branches | Consistency checker compares ACL across stores | Rows with mismatched acl_version excluded | EXP-ACL-03
Metadata storage | Policy store tables (sheet 21) | Transactional updates; acl_version bump | Stale rows excluded | EXP-ACL-05
Query authentication | Entra access token validated at RAG API | Reject missing/invalid token; app_id bound to calling client | 401/403 | EXP-ACL-10
User & group identity resolution | Effective principal set (oid, transitive groups, SP groups, sn:uc matches) | TTL <= revocation SLA; resolution failure for a source = exclude that source | Exclude source | EXP-ACL-05/06
Authorisation filtering | Principal set as mandatory engine filter (allow ANY, deny NONE, status = ok) | Filter injected server-side; never from client input | No filter -> query refused | EXP-ACL-04
Candidate retrieval | Only authorised candidates returned by engine | Oversampling to keep top-k filled | - | EXP-ACL-04
Reranking | Only authorised candidates sent | Reranker called after trimming | - | EXP-ACL-13
Context assembly | Authoritative re-check of final docs where requires_source_check or acl_updated_at older than threshold | Drop unverified docs | Drop | EXP-ACL-12
LLM prompt construction | Only verified chunks | Prompt builder asserts every chunk passed check | Abort answer | EXP-ACL-12
Answer generation | Model sees only authorised context | Grounding + citation mapping | - | EXP-ACL-09
Citation generation | Citations only to verified documents | Re-validate cited doc IDs against trimmed set | Strip citation | EXP-ACL-09
Response delivery | Response tagged with acl_versions used | - | - | EXP-ACL-09
A2A / agent messages | Restricted content stays in the RAG tool result for the requesting user's session | Remote agents receive only what the end user may see; identity forwarded, never escalated | Block forwarding | EXP-ACL-11
Logging, tracing, observability | IDs and hashes, not content | Cloud Logging exclusion / DLP redaction; restricted log buckets | Redact | EXP-ACL-15
Caching & conversation memory | Cache key includes principal-set hash + acl_versions; memory per user | Revocation bumps invalidate | Miss | EXP-ACL-10

## 21b_ACL_Enforcement
ACL enforcement options - index replication vs policy service vs source delegation vs hybrid
Option ID | Enforcement option | How it works | Security guarantee | Freshness / revocation | Latency | Scale | Operational complexity | API dependency | Preliminary assessment
ENF-01 | Synchronised ACL-aware index (pre-filter) | Normalised principals stored with chunks; user principal set injected as filter inside retrieval | Strong if extraction + normalisation are faithful and sync is fresh | Bounded by ACL sync lag + principal cache TTL | Low | High | Medium-High (parallel authorisation model to keep consistent) | Bulk ACL APIs | Necessary foundation for any custom index
ENF-02 | Trusted policy service (query-time check) | Central authorisation service (e.g. ACL tables or ReBAC engine such as OpenFGA/SpiceDB) answers allowed docs for user | Strong; single place to audit | As fresh as the policy store | Medium (list-objects at scale is costly) | Medium | High | Bulk ACL APIs | Useful as the policy store behind ENF-01 rather than a replacement
ENF-03 | Delegate to source system | Ask SharePoint/ServiceNow as the user (Graph OBO GET, KM API) | Strongest semantic fidelity (source is truth) | Real time | High; fan-out per candidate | Low under concurrency (throttling) | Medium | Per-user delegated APIs | Use for validation of top-N and for requires_source_check docs, not as first-stage retrieval
ENF-04 | Hybrid: indexed pre-filter + authoritative validation before LLM | ENF-01 for recall-safe trimming; ENF-03 (or fresh policy check) on final N candidates | Strong + defence in depth | Revocation closes at validation step | Medium (N checks, parallel) | Medium-High | High | Both | PRELIMINARY RECOMMENDATION - confirm with EXP-ACL-12 latency and revocation SLA (AQ-15)
ENF-05 | Post-filter only | Retrieve without ACL filter, drop unauthorised results afterwards | WEAK: unauthorised content enters service memory, rerankers, logs; top-k under-fill; counts/relevance distorted; timing side channels | n/a | Low | High | Low | - | UNSUITABLE as the sole mechanism (fails FR-SEC-03 'trimming inside retrieval')
ENF-06 | Per-user index partitions | Materialise a partition per user | Strong isolation | Very poor (every membership change rewrites partitions) | Low | Very poor (users x docs) | Very high | - | UNSUITABLE at enterprise scale

## 22_Layer_Analysis
Per-layer analysis and cross-layer interactions
Layer | Problem solved | Implementation options (refs) | Key trade-offs | Prerequisites | Compatible combinations | Tunable variables | Experiments | Success metrics | Common failure modes | Initial POC scope | Evidence needed before production | Managed by GCP vs owned by us | Interactions with other layers
Source connectors | Get content + metadata + ACLs out of SharePoint/ServiceNow | Managed connectors; Graph/Table APIs; federated APIs (sheet 05a) | Effort vs control vs ACL fidelity | API access, app registrations | All | Sync cadence, scopes | EXP-30/31, EXP-ACL-01 | Completeness, freshness, ACL fidelity | Throttling; lost delta tokens; missed permission changes | POC sites + KBs only | Soak test of sync + reconciliation | Managed in AP-A; ours in AP-B/C/E | Determines ACL quality for every downstream layer
Parsing & normalisation | Turn files into clean, structured text | Managed parser; Document AI; Docling/Unstructured (ING-06..13) | Cost/page vs fidelity | File mix profile | All | Parser per type, OCR on/off | EXP-32 | Extraction fidelity; table recall | Lost tables/headings; boilerplate | Top 5 file types | Per-type fidelity report | Document AI managed; logic ours | Structure enables heading-aware/table chunking
Chunking | Units of retrieval and context | CHK-01..17 | Precision vs completeness; storage | Parsed structure | Any embedding/store | Size, overlap, strategy, parent size | EXP-07..10, CPX | Recall, NDCG, completeness | Fragmentation; duplicates | CHK-05 vs CHK-06 vs CHK-10 | Chosen per doc type with significance | Managed config in AP-A; ours otherwise | Chunk size must fit embedding max input; affects reranker input and context budget
Embedding | Semantic representation | EMB-01..20 | Quality vs cost vs residency vs ops | Quotas or GPUs | Store must support dims/sparse | Model, dims, task type, prefixes | EXP-01..06, 42 | Recall, cost/1M tokens | Prefix misuse; truncation; model mix in index | EMB-01/03/06/07 | Re-embed runbook; version pinning | Managed (Vertex) or ours (self-hosted) | Dims drive ANN memory; model drives chunk-size limit
Vector index / ANN | Fast nearest-neighbour search | VDB-*, ANN-* | Recall vs latency vs memory vs filtering | Corpus size | Must support ACL filtering | Index type + params, quantisation | EXP-11, 12, 39; AX | ANN recall, P95 | Filter-recall cliff; stale index | HNSW (AlloyDB) + Tree-AH (Vector Search) | Filtered recall at realistic selectivity | Managed service; tuning ours | ACL filter selectivity interacts with ANN recall
Keyword / sparse | Exact terms, IDs, acronyms | RET-02/03 | Analyzer tuning vs simplicity | Language info | Hybrid-capable store | Analyzers, field boosts, synonyms | EXP-13/14/16 | Recall on keyword strata | ACL drift vs vector branch | PostgreSQL FTS; Elastic | Same ACL predicate proven on both branches | Ours (or managed in AP-A) | Fusion weights depend on both branches
Authorisation | Users see only what they may see | ENF-01..06; sheet 21 | Freshness vs latency vs fidelity | Identity map, ACL extraction | All | TTLs, validation N, deny rules | EXP-ACL-* | Zero-tolerance metrics | Stale ACL; identity mismatch; cache leakage | ENF-04 | Zero failures across full negative suite + revocation within SLA | Managed in AP-A; ours otherwise | Constrains retrieval (filters), rerank inputs, caching, A2A
Fusion & reranking | Better ordering of candidates | RRK-01..12 | Quality vs latency vs cost | Trimmed candidates | All | Depth, model, fusion k/alpha | EXP-19, 29, 38 | NDCG@10, P95 | Over-deep rerank latency | RRF + Ranking API | Uplift stable on held-out set | Ranking API managed; logic ours | Depth multiplies latency; must follow ACL trimming
Query understanding | Better queries | RET-07..11; FR-GLO | Gains vs latency | Glossary, conversation memory | All | Expansion rules, rewrite prompt | EXP-16, 17, 18 | Recall per stratum | Over-expansion; drift | Glossary + rewrite | Per-stratum gains | Ours | Glossary shared by keyword and dense branches
Context assembly & generation | Grounded, cited answers | ADV-19..22, 27; Gemini | Context size vs cost vs faithfulness | Prompt registry per app_id | All | k, ordering, parent expansion, model tier | EXP-21, 22, 23, 34, 36 | Faithfulness, completeness, citation metrics | Lost-in-the-middle; unsupported claims | Gemini Flash vs Pro | Stable eval on held-out set | Model managed; prompts ours | Chunk size and rerank quality set context noise
Agent integration (ADK/A2A) | Expose RAG to agents safely | ADK FunctionTool / OpenAPI toolset / RemoteA2aAgent (API-18/19) | Simplicity vs flexibility | ADK 2.0.3 env | All | Tool contract, identity forwarding | EXP-41, EXP-ACL-11/20 | Overhead, zero leakage | Identity dropped -> service account used | RAG as tool with end-user token | Spoof tests pass | Ours | Agent orchestrates; RAG service owns ingestion, retrieval, ACL and context assembly
Evaluation & monitoring | Prove and keep quality/security | ADV-30/31; metrics sheet | Human cost vs automation | Golden sets | All | Judge rubric, sampling | EXP-35 | All metrics | Uncalibrated judge; test drift | Harness from day 1 | Regression gate in CI | Ours | Feeds every decision gate

## 23_FR_Traceability
Traceability to Eva Knowledge Engine functional requirements (from supplied FR sheet)
FR ID | Category | Requirement (Eva FR sheet) | Priority | Origin | How addressed in this plan | Related experiments / checks | Managed baseline coverage (hypothesis) | Custom-RAG implication
FR-API-01 | Core APIs | Search API (security-trimmed ranked chunks with title, deep link, snippet, score, source, modified date) | Must | Stated | RAG API contract over any retrieval option; fields from ACL model sheet 21 | EXP-ACL-04, EXP-23 | Covered by Search API | Build API layer
FR-API-02 | Core APIs | Answer API (grounded answer with inline citations) | Must | Stated | ADV-19/20; context assembly | EXP-21..23 | Covered by Answer API | Build generation + citation mapping
FR-API-03 | Core APIs | Answer reuses search results | Should | Recommended | Answer accepts result IDs (re-validated ACL) | EXP-ACL-12 | Partial - To Verify | Must re-check ACL on reused IDs
FR-API-04 | Core APIs | Streaming answers | Should | Recommended | SSE streaming | EXP-36 | Streaming support - To Verify | Build
FR-API-05 | Core APIs | Versioned, documented contract (OpenAPI) | Must | Recommended | Same contract for all back-ends enables side-by-side tests | EXP-41 | n/a (our API) | Build
FR-API-06 | Core APIs | Consistent errors and request tracing | Must | Recommended | Correlation ID through ADK/A2A/RAG; Cloud Trace | API-29 | n/a | Build
FR-API-07 | Core APIs | Answer metadata incl. 'no-answer' flag | Should | Recommended | ADV-26/27 | EXP-22 | Partial | Build
FR-CFG-01 | Client configuration | App ID registration | Must | Stated | app_id config store (data sets, models, prompt, retrieval settings) | AQ-28 | Partial (apps/engines) | Build
FR-CFG-02 | Client configuration | Model selection per request with allow-list | Must | Stated | Model allow-list per app_id | R-20 | Limited | Build
FR-CFG-03 | Client configuration | System prompt per app / request, versioned | Must | Stated | Prompt registry | A-02 | Partial | Build
FR-CFG-04 | Client configuration | Retrieval tuning per app | Should | Recommended | Per-app top_k, hybrid weights, rerank, chunk count | EXP-13/19/21 | Limited | Native in custom
FR-CFG-05 | Client configuration | Admin config API with audit | Should | Recommended | Config service with change history | - | n/a | Build
FR-CFG-06 | Client configuration | Data-set authorisation per app | Must | Recommended | App entitlement filter AND user ACL filter (both mandatory) | EXP-15, EXP-ACL-04 | Partial (data stores per app) | Build
FR-CON-01 | Connectors | SharePoint Online connector (incl. item-level permissions; open question on sharing links) | Must | Stated | Sheet 05a SP-01..13; AQ-19 | EXP-ACL-01/17 | Managed connector | Build extractor + ACL
FR-CON-02 | Connectors | ServiceNow connector (KB; user criteria) | Must | Stated | SN-01..11; AQ-02/03 | EXP-ACL-06 | Managed connector (criteria fidelity To Verify) | Build extractor + criteria evaluation
FR-CON-03 | Connectors | Cloud SQL connector | Must | Stated | Later phase (AQ-27); ADV-18 | - | Managed options - To Verify | Build
FR-CON-04 | Connectors | BigQuery connector (row-level security / authorized views) | Must | Stated | Later phase; B-08 | - | Managed BigQuery data stores | Build
FR-CON-05 | Connectors | Cloud Storage connector (bucket/object IAM) | Must | Stated | Later phase | - | Managed GCS data stores (ACL support documented) | Build
FR-CON-06 | Connectors | Common connector framework | Must | Recommended | ING-01..28 | EXP-30/31 | Managed | Build framework
FR-CON-07 | Connectors | Parsing, chunking, enrichment | Must | Recommended | Sheets 05, 06 | EXP-07..10, 32 | Managed | Build
FR-CON-08 | Connectors | Secure credential handling | Must | Recommended | Secret Manager, workload identities | GCP-19 | Managed | Build
FR-CON-09 | Connectors | Pluggable connector model | Could | Recommended | Connector interface in custom options | - | n/a | Build
FR-SEC-01 | Security & ACLs | Preserve source ACLs | Must | Stated | Sheet 21 ACL model | EXP-ACL-01/02 | Managed | Build
FR-SEC-02 | Security & ACLs | Entra ID identity mapping (open question: GCP/ServiceNow identities) | Must | Stated | ID-01..04; SRC-12; AQ-18 | EXP-ACL-20 | WIF-based | Build identity map
FR-SEC-03 | Security & ACLs | Query-time security trimming inside retrieval | Must | Stated | ENF-04; post-filter-only options marked unsuitable | EXP-ACL-04 | Managed | Build (pre-filter)
FR-SEC-04 | Security & ACLs | Deny by default | Must | Recommended | Fail-closed rules (sheet 21b) | EXP-ACL-08/21 | To Verify | Build
FR-SEC-05 | Security & ACLs | No leakage through answers or caches | Must | Recommended | Permission-keyed caches | EXP-ACL-10 | To Verify | Build
FR-SEC-06 | Security & ACLs | Client application authentication; app_id bound to caller | Must | Recommended | SRC-04 | EXP-ACL-20 | n/a | Build
FR-SEC-07 | Security & ACLs | Audit logging | Must | Recommended | GCP-20; lineage tables | - | Partial | Build
FR-SEC-08 | Security & ACLs | Sensitive data handling (PHI/PII) | Must | Recommended | ING-27, DLP | EXP-ACL-15 | Partial | Build
FR-FLT-01 | Filtering | Metadata filters | Must | Stated | RET-05; ING-09 | EXP-15 | Covered | Build filter DSL
FR-FLT-02 | Filtering | Same filters on both APIs | Must | Stated | Shared filter DSL | EXP-15 | Covered | Build
FR-FLT-03 | Filtering | Filter schema discovery | Should | Recommended | Schema endpoint per app_id/data set | - | Partial | Build
FR-FLT-04 | Filtering | Default filters per app | Should | Recommended | app_id config | - | Partial | Build
FR-FLT-05 | Filtering | Facets on trimmed result set | Could | Recommended | Facet counts computed after ACL trimming only | EXP-ACL-09 | Covered (facets) - verify trimming | Build
FR-GLO-01 | Acronyms & Synonyms | Company glossary store (global / data set / app scope) | Must | Stated | Glossary service shared by all options | EXP-16 | Limited | Build
FR-GLO-02 | Acronyms & Synonyms | Query expansion (keyword + vector) without re-index | Must | Stated | RET-07 | EXP-16 | Limited | Build
FR-GLO-03 | Acronyms & Synonyms | Ambiguous acronym handling | Should | Recommended | Scope-based sense selection; clarify option | EXP-16 | No | Build
FR-GLO-04 | Acronyms & Synonyms | Glossary-aware answers | Should | Recommended | ADV-29 | EXP-21 | No | Build
FR-GLO-05 | Acronyms & Synonyms | Glossary management (CSV import/export, versioning, approval) | Must | Stated | Admin API | - | No | Build
FR-GLO-06 | Acronyms & Synonyms | Fast propagation (15 min proposed target) | Should | Recommended | Expansion at query time - no re-index | EXP-16 | n/a | Build
FR-RET-01 | Retrieval & Answer Quality | Hybrid retrieval with re-ranking | Must | Recommended | RET-04, RRK-01/07 | EXP-13/19 | Covered (managed) | Build + tune
FR-RET-02 | Retrieval & Answer Quality | Grounded answers with citations | Must | Recommended | ADV-19/20 | EXP-22/23 | Covered | Build
FR-RET-03 | Retrieval & Answer Quality | Insufficient-evidence behaviour | Must | Recommended | ADV-27 | EXP-22 | Partial | Build
FR-RET-04 | Retrieval & Answer Quality | Prompt-injection and content safety guardrails | Must | Recommended | ADV-28 | EXP-37 | Partial | Build
FR-RET-05 | Retrieval & Answer Quality | Evaluation harness with golden sets per app_id | Should | Recommended | ADV-30; sheet 15a | EXP-35 | n/a (ours) | Build
FR-RET-06 | Retrieval & Answer Quality | User feedback capture | Should | Recommended | ADV-31 | - | n/a | Build

## 24_Source_Register
Source register (official docs first; click-check before citing)
Source ID | Topic | Title | URL | Type | Used in sheets | Verification status | Date checked
S-01 | Embeddings | Vertex AI - Get text embeddings | https://cloud.google.com/vertex-ai/generative-ai/docs/embeddings/get-text-embeddings | Official doc | 04, 13 | Verified (web check 2026-10-26) | 2026-10-26
S-02 | Embeddings | Vector Search 2.0 - Autogenerating embeddings (lists gemini-embedding-2-preview) | https://docs.cloud.google.com/vertex-ai/docs/vector-search-2/embeddings/autogenerating-embeddings | Official doc | 04, 07 | Verified (web check 2026-10-26) | 2026-10-26
S-03 | Embeddings | Vertex AI - Multimodal embeddings | https://cloud.google.com/vertex-ai/generative-ai/docs/embeddings/get-multimodal-embeddings | Official doc | 4 | Documented - re-verify before use | 2026-10-26
S-04 | Pricing | Vertex AI generative AI pricing | https://cloud.google.com/vertex-ai/generative-ai/pricing | Official pricing | 17 | Documented - re-verify before use | 2026-10-26
S-05 | Pricing | Vertex AI pricing (incl. Vector Search) | https://cloud.google.com/vertex-ai/pricing | Official pricing | 17 | Documented - re-verify before use | 2026-10-26
S-06 | Managed RAG | Vertex AI Search - data source access control | https://cloud.google.com/generative-ai-app-builder/docs/data-source-access-control | Official doc | 07, 05a, 03 | Verified (web check 2026-10-26) | 2026-10-26
S-07 | Managed RAG | Vertex AI Search - SharePoint Online connector | https://cloud.google.com/generative-ai-app-builder/docs/connect-sharepoint | Official doc | 05a | Documented - re-verify before use | 2026-10-26
S-08 | Managed RAG | Vertex AI Search - ServiceNow connector | https://cloud.google.com/generative-ai-app-builder/docs/connect-servicenow | Official doc | 05a | Documented - re-verify before use | 2026-10-26
S-09 | Managed RAG | Vertex AI Search - parse and chunk documents | https://cloud.google.com/generative-ai-app-builder/docs/parse-chunk-documents | Official doc | 6 | Documented - re-verify before use | 2026-10-26
S-10 | Managed RAG | Ranking API | https://cloud.google.com/generative-ai-app-builder/docs/ranking | Official doc | 10, 13 | Verified (web check 2026-10-26) | 2026-10-26
S-11 | Managed RAG | Launch blog: Vertex AI Ranking API (default-004 / fast-004) | https://cloud.google.com/blog/products/ai-machine-learning/launching-our-new-state-of-the-art-vertex-ai-ranking-api | Official blog | 10 | Verified (web check 2026-10-26) | 2026-10-26
S-12 | Managed RAG | Check grounding | https://cloud.google.com/generative-ai-app-builder/docs/check-grounding | Official doc | 11 | Documented - re-verify before use | 2026-10-26
S-13 | Pricing | AI Applications (Vertex AI Search) pricing | https://cloud.google.com/generative-ai-app-builder/pricing | Official pricing | 17 | Documented - re-verify before use | 2026-10-26
S-14 | Vector store | Vertex AI Vector Search overview | https://cloud.google.com/vertex-ai/docs/vector-search/overview | Official doc | 7 | Documented - re-verify before use | 2026-10-26
S-15 | Vector store | Vector Search filtering (restricts) | https://cloud.google.com/vertex-ai/docs/vector-search/filtering | Official doc | 07, 03 | Documented - re-verify before use | 2026-10-26
S-16 | Vector store | Vector Search hybrid search | https://cloud.google.com/vertex-ai/docs/vector-search/about-hybrid-search | Official doc | 07, 09 | Documented - re-verify before use | 2026-10-26
S-17 | Vector store | BigQuery vector search intro | https://cloud.google.com/bigquery/docs/vector-search-intro | Official doc | 7 | Documented - re-verify before use | 2026-10-26
S-18 | Pricing | BigQuery pricing | https://cloud.google.com/bigquery/pricing | Official pricing | 17 | Documented - re-verify before use | 2026-10-26
S-19 | Vector store | AlloyDB - store, index and query vectors | https://cloud.google.com/alloydb/docs/ai/store-index-query-vectors | Official doc | 07, 08 | Documented - re-verify before use | 2026-10-26
S-20 | Pricing | AlloyDB pricing | https://cloud.google.com/alloydb/pricing | Official pricing | 17 | Documented - re-verify before use | 2026-10-26
S-21 | Vector store | Cloud SQL for PostgreSQL - work with vectors | https://cloud.google.com/sql/docs/postgres/work-with-vectors | Official doc | 7 | Documented - re-verify before use | 2026-10-26
S-22 | Pricing | Cloud SQL pricing | https://cloud.google.com/sql/pricing | Official pricing | 17 | Documented - re-verify before use | 2026-10-26
S-23 | Vector store | Spanner - approximate nearest neighbours | https://cloud.google.com/spanner/docs/find-approximate-nearest-neighbors | Official doc | 7 | Documented - re-verify before use | 2026-10-26
S-24 | Vector store | Firestore vector search | https://cloud.google.com/firestore/docs/vector-search | Official doc | 7 | Documented - re-verify before use | 2026-10-26
S-25 | Managed RAG | Vertex AI RAG Engine overview | https://cloud.google.com/vertex-ai/generative-ai/docs/rag-engine/rag-overview | Official doc | 07, 03a | Documented - re-verify before use | 2026-10-26
S-26 | Parsing | Document AI Layout Parser | https://cloud.google.com/document-ai/docs/layout-parse-chunk | Official doc | 05, 06 | Documented - re-verify before use | 2026-10-26
S-27 | Security | Workforce Identity Federation | https://cloud.google.com/iam/docs/workforce-identity-federation | Official doc | 05a, 12 | Documented - re-verify before use | 2026-10-26
S-28 | Security | VPC Service Controls | https://cloud.google.com/vpc-service-controls/docs/overview | Official doc | 12 | Documented - re-verify before use | 2026-10-26
S-29 | Security | IAM predefined roles reference | https://cloud.google.com/iam/docs/understanding-roles | Official doc | 12 | Documented - re-verify before use | 2026-10-26
S-30 | Security | Sensitive Data Protection | https://cloud.google.com/sensitive-data-protection/docs | Official doc | 05, 13 | Documented - re-verify before use | 2026-10-26
S-31 | Security | Model Armor | https://cloud.google.com/security-command-center/docs/model-armor-overview | Official doc | 11, 13 | To Verify | 2026-10-26
S-32 | Evaluation | Vertex AI Gen AI evaluation service | https://cloud.google.com/vertex-ai/generative-ai/docs/models/evaluation-overview | Official doc | 15 | Documented - re-verify before use | 2026-10-26
S-33 | Agents | ADK 2.0 documentation | https://adk.dev/2.0/ | Official doc | 13 | Verified (web check 2026-10-26) | 2026-10-26
S-34 | Agents | ADK Python releases | https://github.com/google/adk-python/releases | Official repo | 13, 16 | Verified (web check 2026-10-26) | 2026-10-26
S-35 | Agents | A2A protocol specification | https://a2a-protocol.org/latest/specification/ | Official spec | 13 | Documented - re-verify before use | 2026-10-26
S-36 | SharePoint | Graph driveItem delta | https://learn.microsoft.com/en-us/graph/api/driveitem-delta | Official doc | 05a, 13 | Documented - re-verify before use | 2026-10-26
S-37 | SharePoint | Graph list driveItem permissions | https://learn.microsoft.com/en-us/graph/api/driveitem-list-permissions | Official doc | 05a | Documented - re-verify before use | 2026-10-26
S-38 | SharePoint | Graph Sites.Selected overview | https://learn.microsoft.com/en-us/graph/permissions-selected-overview | Official doc | 05a, 12 | To Verify | 2026-10-26
S-39 | SharePoint | Avoid throttling in SharePoint Online | https://learn.microsoft.com/en-us/sharepoint/dev/general-development/how-to-avoid-getting-throttled-or-blocked-in-sharepoint-online | Official doc | 05a | Documented - re-verify before use | 2026-10-26
S-40 | Entra ID | transitiveMemberOf | https://learn.microsoft.com/en-us/graph/api/user-list-transitivememberof | Official doc | 05a | Documented - re-verify before use | 2026-10-26
S-41 | Entra ID | On-Behalf-Of flow | https://learn.microsoft.com/en-us/entra/identity-platform/v2-oauth2-on-behalf-of-flow | Official doc | 05a, 13 | Documented - re-verify before use | 2026-10-26
S-42 | Entra ID | Access tokens | https://learn.microsoft.com/en-us/entra/identity-platform/access-tokens | Official doc | 13 | Documented - re-verify before use | 2026-10-26
S-43 | SharePoint | Graph Search API overview | https://learn.microsoft.com/en-us/graph/api/resources/search-api-overview | Official doc | 13 | Documented - re-verify before use | 2026-10-26
S-44 | ServiceNow | Table API reference | https://developer.servicenow.com/dev.do#!/reference/api/latest/rest/c_TableAPI | Official doc | 05a, 13 | Documented - re-verify before use | 2026-10-26
S-45 | ServiceNow | Knowledge Management REST API | https://developer.servicenow.com/dev.do#!/reference/api/latest/rest/knowledge-api | Official doc | 05a, 13 | To Verify | 2026-10-26
S-46 | ServiceNow | Knowledge user criteria (product docs - path is release-specific) | https://www.servicenow.com/docs/ | Official doc portal | 05a | To Verify | 2026-10-26
S-47 | OSS | pgvector | https://github.com/pgvector/pgvector | OSS | 07, 08 | OSS/Third-party - verify licence & version | 2026-10-26
S-48 | OSS | FAISS | https://github.com/facebookresearch/faiss | OSS | 07, 08 | OSS/Third-party - verify licence & version | 2026-10-26
S-49 | OSS | hnswlib | https://github.com/nmslib/hnswlib | OSS | 8 | OSS/Third-party - verify licence & version | 2026-10-26
S-50 | OSS | Qdrant docs | https://qdrant.tech/documentation/ | OSS | 7 | OSS/Third-party - verify licence & version | 2026-10-26
S-51 | OSS | Weaviate docs | https://weaviate.io/developers/weaviate | OSS | 7 | OSS/Third-party - verify licence & version | 2026-10-26
S-52 | OSS | Milvus docs | https://milvus.io/docs | OSS | 7 | OSS/Third-party - verify licence & version | 2026-10-26
S-53 | OSS | Elasticsearch document-level security | https://www.elastic.co/guide/en/elasticsearch/reference/current/document-level-security.html | Vendor doc | 7 | OSS/Third-party - verify licence & version | 2026-10-26
S-54 | OSS | OpenSearch k-NN | https://opensearch.org/docs/latest/search-plugins/knn/index/ | OSS | 7 | OSS/Third-party - verify licence & version | 2026-10-26
S-55 | OSS | Sentence Transformers | https://sbert.net | OSS | 4 | OSS/Third-party - verify licence & version | 2026-10-26
S-56 | OSS | LlamaIndex | https://docs.llamaindex.ai/ | OSS | 13 | OSS/Third-party - verify licence & version | 2026-10-26
S-57 | OSS | MTEB leaderboard (public benchmarks - do not rely on alone) | https://huggingface.co/spaces/mteb/leaderboard | Benchmark | 4 | OSS/Third-party - verify licence & version | 2026-10-26
S-58 | Paper | HNSW (Malkov & Yashunin) | https://arxiv.org/abs/1603.09320 | Paper | 8 | Documented - re-verify before use | 2026-10-26
S-59 | Paper | ScaNN - anisotropic vector quantisation | https://arxiv.org/abs/1908.10396 | Paper | 8 | Documented - re-verify before use | 2026-10-26
S-60 | Paper | Product quantisation (Jegou et al.) | https://ieeexplore.ieee.org/document/5432202 | Paper | 8 | Documented - re-verify before use | 2026-10-26
S-61 | Paper | DiskANN | https://www.microsoft.com/en-us/research/publication/diskann-fast-accurate-billion-point-nearest-neighbor-search-on-a-single-node/ | Paper | 8 | Documented - re-verify before use | 2026-10-26
S-62 | Paper | Reciprocal Rank Fusion (Cormack et al. 2009) | https://dl.acm.org/doi/10.1145/1571941.1572114 | Paper | 10 | Documented - re-verify before use | 2026-10-26
S-63 | Paper | MMR (Carbonell & Goldstein 1998) | https://dl.acm.org/doi/10.1145/290941.291025 | Paper | 10 | Documented - re-verify before use | 2026-10-26
S-64 | Paper | ColBERT | https://arxiv.org/abs/2004.12832 | Paper | 10, 11 | Documented - re-verify before use | 2026-10-26
S-65 | Paper | Matryoshka representation learning | https://arxiv.org/abs/2205.13147 | Paper | 8 | Documented - re-verify before use | 2026-10-26
S-66 | Paper | RAPTOR | https://arxiv.org/abs/2401.18059 | Paper | 11 | Documented - re-verify before use | 2026-10-26
S-67 | Paper | GraphRAG (Edge et al.) | https://arxiv.org/abs/2404.16130 | Paper | 11 | Documented - re-verify before use | 2026-10-26
S-68 | Paper | Corrective RAG | https://arxiv.org/abs/2401.15884 | Paper | 11 | Documented - re-verify before use | 2026-10-26
S-69 | Paper | Self-RAG | https://arxiv.org/abs/2310.11511 | Paper | 11 | Documented - re-verify before use | 2026-10-26
S-70 | Paper | Lost in the Middle | https://arxiv.org/abs/2307.03172 | Paper | 11 | Documented - re-verify before use | 2026-10-26
S-71 | Article | Contextual Retrieval (Anthropic) | https://www.anthropic.com/news/contextual-retrieval | Vendor article | 11 | Documented - re-verify before use | 2026-10-26
S-72 | Model | BAAI/bge-m3 | https://huggingface.co/BAAI/bge-m3 | Model card | 4 | OSS/Third-party - verify licence & version | 2026-10-26
S-73 | Model | EmbeddingGemma | https://ai.google.dev/gemma/docs/embeddinggemma | Model docs | 4 | OSS/Third-party - verify licence & version | 2026-10-26

## Lists (hidden)
Verification | Priority | Status | ResultStatus | Severity | Mandatory | AQStatus | Gate | Confidence
Verified (web check 2026-10-26) | P0 | Not started | Not started | High | Mandatory | To Confirm | Pass | Low
Documented - re-verify before use | P1 | In progress | Running | Medium | Conditional | In progress | Fail | Medium
Preview/Experimental - re-verify | P2 | Blocked | Passed | Low | Conditional (policy) | Confirmed | Unknown | High
OSS/Third-party - verify licence & version | P3 | Done | Failed |  | Mandatory (baseline) | Decided
Proposed pattern - validate in POC | P4 | N/A | Inconclusive |  |  | Deferred
Assumption - confirm with team | Excluded |  | Cancelled
To Verify